## Fakeeh BD
ALUSYSTEMS FACTORY Co.
PROGRESS REPORT # 4 -Breakdown - Fakeeh Hospital
PROJECT NO & NAME : Dr. Sulaiman Fakeeh Hospital / Al Madinah
[6 empty] | 216.3744 | 1204772.7
| Date: | 2024-01-21
SN | Type | CODE | DESCRIPTION | UNIT | BOQ Qty. | BOQ Size |  |  | Actual QTY | Actual Area | UNIT PRICE | TOTAL PRICE | Frames Deliv. & Installation |  |  | Glass/ACP Delivery |  |  | Glass Installation |  |  | Sealant & Finishing + Hardware |  |  | Handing Over |  |  | VALUE OF WORK DONE ( DELIVERY ) 25% |  |  | VALUE OF WORK DONE ( INSTALLATION ) 75% |  |  | VALUE OF WORK DONE | Completion percentage %
[13 empty] | Frames Deliv. & Installation |  | 30% | Glass/ACP Delivery |  | 25% | Glass Installation |  | 30% | Sealant & Finishing |  | 10% | H.over |  | 5%
[6 empty] | W | H | M2 |  | M2 |  |  | Previous | Current | Total | Previous | Current | Total | Previous | Current | Total | Previous | Current | Total | Previous | Current | Total | PREVIOUS | CURRENT | TOTAL | PREVIOUS | CURRENT | TOTAL | TOTAL
1 | CW | CW01 | FOUR SIDED FIXED STR'L GLAZED CURTAIN WALL | M2 | 5568 | [5 empty] | 721.248 | 4015909 | 4278.8968 | 638.6032 | 4917.5 | 4229 | 93 | 4322 | 2755 | 1354.9 | 4109.9 |  | 0 |  |  | 0 |  | 762539.4738 | 16769.0166 | 779308.4904 | 1521955.2517 | 431343.073 | 1953298.3247 | 2732606.8151 | 68.04%
2 | CW | CW01 (A) | FOUR SIDED FIXED STR'L GLAZED CURVED CURTAIN WALL | M2 | 197 | [5 empty] | 1828.2487 | 360165 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
3 | CW | CW01- OPENINGS | ADDITIONAL PRICE FOR CURTAIN WALL FOR OPERABLE PANEL DUE TO ADDITIONAL THERMAL BREAK PROFILES FOR ALUMINUM FRAME, ALUMINUM LEAF AND ACCESSORIES & HARDWARE | NO. | 209 | [5 empty] | 640 | 133760 | 46 | 104 | 150 | 204 | 0 | 204 | 46 | 104 | 150 |  | 0 |  |  | 0 |  | 32640 | 0 | 32640 | 17664 | 39936 | 57600 | 90240 | 67.46%
4 | CW | CW02 | FOUR SIDED FIXED STR'L GLAZED CURTAIN WALL | M2 | 1005 | [5 empty] | 640.9791 | 644184 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
5 | CW | EXTERNAL STEEL SUPPORT FOR (CW01-CW02 ) | SUPPLY , FABRICATION & INSTALLATION FOR EXTERNAL STEEL STRUCTURE SUPORT BEAMS | TON | 3.9 | [5 empty] | 10380 | 40482 | 3.9 | 0 | 3.9 | 3.9 | 0 | 3.9 | 3.9 | 0 | 3.9 | 3.9 | 0 | 3.9 |  | 0 |  | 10120.5 | 0 | 10120.5 | 28337.4 | 0 | 28337.4 | 38457.9 | 95%
6 | ACP | ACP-01 | 4MM ALUMINUM COMPOSITE PANEL CLADDING ON SECONDARY STEEL ONLY SUB FRAME - STEEL TUBE SIZE 40X20X1.5MM | M2 | 3400 | [5 empty] | 320 | 1088000 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
7 | ACP | ACP-01(A) | 4MM ALUMINUM COMPOSITE PANEL CLADDING ON ALUPCO ALUMINUM CURTAIN WALL SYSTEM | M2 | 1430 | [5 empty] | 495 | 707850 | 1415.7 | 1928.3 | 3344 |  | 890 | 890 |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 110137.5 | 110137.5 | 210231.45 | 286352.55 | 496584 | 606721.5 | 85.71%
8 | ACP | ACP-02 | 4MM ALUMINUM COMPOSITE PANEL CLADDING ON SECONDARY STEEL ONLY SUB FRAME - STEEL TUBE SIZE 40X20X1.5MM | M2 | 4555 | [5 empty] | 320 | 1457600 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Windows | W01 | SINGLE PANEL FIXED WINDOW | NO. | 7 | [5 empty] | 436 | 3052 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Windows | W02 | SINGLE PANEL FIXED WINDOW | NO. | 9 | [5 empty] | 338 | 3042 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Windows | W03 | SINGLE PANEL FIXED WINDOW | NO. | 7 | [5 empty] | 523 | 3661 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Windows | W04 | SINGLE PANEL FIXED WINDOW | NO. | 2 | [5 empty] | 935 | 1870 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| CW | W05 | FIXED CURTAIN WALL | NO. | 359 | [5 empty] | 2047 | 734873 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| FRAMELESS | W06 | SINGLE PANEL FIXED FRAMLEES WINDOW | NO. | 7 | [5 empty] | 29523 | 206661 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| FRAMELESS | W07 | SINGLE PANEL FIXED FRAMLEES WINDOW | NO. | 1 | [5 empty] | 29967 | 29967 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Aut. Doors | GD01 | DOUBLE PANEL AUTOMATIC SLIDING BREAK OUT DOOR | NO. | 3 | [5 empty] | 27288 | 81864 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Aut. Doors | GD02 | DOUBLE PANEL AUTOMATIC SLIDING BREAK OUT DOOR | NO. | 1 | [5 empty] | 27170 | 27170 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Doors | GD03 | DOUBLE PANEL HINGED DOOR | NO. | 18 | [5 empty] | 3722 | 66996 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Doors | GD04 | SINGLE PANEL HINGED DOOR | NO. | 14 | [5 empty] | 2209 | 30926 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Aut. Doors | GD05 | DOUBLE PANEL AUTOMATIC SLIDING BREAK OUT DOOR | NO. | 14 | [5 empty] | 27052 | 378728 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Doors | GD06 | DOUBLE PANEL HINGED DOOR | NO. | 1 | [5 empty] | 2821 | 2821 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Doors | GD07 | DOUBLE PANEL HINGED DOOR | NO. | 15 | [5 empty] | 2733 | 40995 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Aut. Doors | GD08 | SINGLE PANEL AUTOMATIC SLIDING DOOR - STANDARD SLIDING SYSTEM - (NOT BREAK OUT ) | NO. | 28 | [5 empty] | 15414 | 431592 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Doors | GD09 | SINGLE PANEL HINGED DOOR | NO. | 2 | [5 empty] | 1864 | 3728 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Doors | GD10 | SINGLE PANEL HINGED DOOR | NO. | 70 | [5 empty] | 1689 | 118230 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Doors | GD11 | DOUBLE PANEL HINGED DOOR | NO. | 4 | [5 empty] | 2886 | 11544 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| FRAMELESS | G01 | FIXED FRAMELESS SINGLE GLASS PARTITION | M2 | 1225 | [5 empty] | 371 | 454475 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| FRAMELESS | G02 | FIXED FRAMELESS SINGLE GLASS PARTITION | M2 | 880 | [5 empty] | 371 | 326480 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Louver | LV | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM SANDTRAP LOUVER | M2 | 505 | [5 empty] | 1133 | 572165 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Louver | L01 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM SANDTRAP LOUVER | NO. | 3 | [5 empty] | 13426 | 40278 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Louver | L02 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM PERFORMANCE LOUVER | NO. | 3 | [5 empty] | 13726 | 41178 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Louver | L03 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM SANDTRAP LOUVER | NO. | 2 | [5 empty] | 14712 | 29424 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Louver | L04 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM SANDTRAP LOUVER | NO. | 1 | [5 empty] | 6539 | 6539 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Louver | L05 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM SANDTRAP LOUVER | NO. | 1 | [5 empty] | 4087 | 4087 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Louver | L06 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM PERFORMANCE LOUVER | NO. | 1 | [5 empty] | 15686 | 15686 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Louver | L07 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM LOUVER | NO. | 2 | [5 empty] | 14222 | 28444 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Louver | L08 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM PERFORMANCE LOUVER | NO. | 1 | [5 empty] | 1464 | 1464 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Louver | L09 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM PERFORMANCE LOUVER | NO. | 1 | [5 empty] | 5647 | 5647 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Louver | L10 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM SANDTRAP LOUVER | NO. | 3 | [5 empty] | 5492 | 16476 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Louver | L11 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM SANDTRAP LOUVER | NO. | 3 | [5 empty] | 7323 | 21969 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
9 | Louver | L12 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM PERFORMANCE LOUVER | NO. | 51 | [5 empty] | 4118 | 210018 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | GRAND TOTAL | [8 empty] | 12400000 | [15 empty] | 805299.9738 | 126906.5166 | 932206.4904 | 1778188.1017 | 757631.623 | 2535819.7247 | 3468026.2151 | 27.97%
[29 empty] | 0 | 7.518% |  | 0 | 20.45%
For Alusystems Factory CO. | [26 empty] | For Al Kuraiji Co. |  |  |  |  | 884538.1395
Eng. Radhwan M. Al Attar
Project Manager

## مستخلص
INTERIM PAYMENT CERTIFICATE # 4
شركة مصنع انظمة الالمنيوم الانشائي المحدوده |  |  |  |  | Aluminum Construction Systems Factory Co. LTD
المنطقة الصناعية حي المشاعل - السلي |  |  |  |  | Al-Masheel Industrial Area,Exit 18-Souli
الرياض - المملكه العربية السعوديه |  |  |  |  | Riyadh - KSA
جوال :- 0567233335 - 0500058734 |  |  |  |  | Mobile :- 0567233335 - 0500058734
البريد الالكتروني:- ayman@alusystems.com.sa |  |  |  |  | E-Mail:- ayman@alusystems.com.sa
رقم التسجيل بضريبة القيمة المضافة :- 310131187300003 |  |  |  |  | VAT registration No. 310131187300003
Sulaiman Fakeeh Hospital
Al Khuraiji Contracting Co.
INVOICE DATE: 31-12-2023
No. | DESCRIPTION ITEM |  | EXCUTED WORK DONE
|  |  | PREVIOUS |  | THIS PERIOD |  | TOTAL
|  |  | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT
ORIGINAL CONTRACT
A | Delivery Aluminum & Glazing Works | 25% | 0 | 805299.9738 | 7.518% | 126906.5166 | 7.518% | 932206.4904
B | Installation Aluminum & Glazing Works | 75% | 0 | 1778188.1017 | 20.45% | 757631.623 | 20.45% | 2535819.7247
ORIGINAL CONTRACT TOTAL |  | 100% |  | 2583488.0756 | 27.97% | 884538.1395 | 27.97% | 3468026.2151
VARIATION ORDERS
A | Delivery Elements |  | 0 | 0 |  | 0 |  | 0
B | Installation Elements |  | 0 | 0 |  | 0 |  | 0
VARIATION TOTAL |  |  |  | 0 |  | 0 |  | 0
| GRAND TOTAL |  |  | 2583488.0756 |  | 884538.1395 |  | 3468026.2151
Deduct Advance payment |  | 5% |  | 129174.4038 |  | 44226.907 |  | 173401.3108 | 26010.1966
Deduct SHD & Approvals payment |  | 20% |  | 516697.6151 |  | 176907.6279 |  | 693605.243 | 104040.7865
| TOTAL Before VAT |  |  | 1937616.0567 |  | 663403.6047 |  | 2601019.6613
| VAT | 15% |  | 290642.4085 |  | 99510.5407 |  | 390152.9492
Retention |  | 10% |  | 258348.8076 |  | 88453.814 |  | 346802.6215
Deduction Previous Value |  |  |  | 1969909.6576 |  |  |  | 2644369.989
Total net amount | [7 empty] | 674460.3314 |  | 3988230.1474
TOTAL NET AMOUNT CERTIFIED
* NOTE: Detailed work Progress is attached
| Prepared By: |  |  |  |  | Approved By
CONTARACTOR | [5 empty] | Client
Alusystems Co. | [5 empty] | Al Khraiji
Eng. Radhwan M. Al Attar (Project Manager)

## Fakeeh BD (Frames)
ALUSYSTEMS FACTORY Co.
PROGRESS REPORT # 4 -Breakdown - Fakeeh Hospital
PROJECT NO & NAME : Dr. Sulaiman Fakeeh Hospital / Al Madinah
| Date: | 2024-01-21
SN | Type | CODE | DESCRIPTION | UNIT | BOQ Qty. | BOQ Size |  |  | Actual QTY | Actual Area | UNIT PRICE | TOTAL PRICE | Frames Deliv. & Installation |  |  | Glass/ACP Delivery |  |  | Glass Installation |  |  | Sealant & Finishing + Hardware |  |  | Handing Over |  |  | VALUE OF WORK DONE ( DELIVERY ) 25% |  |  | VALUE OF WORK DONE ( INSTALLATION ) 75% |  |  | VALUE OF WORK DONE | Completion percentage %
[13 empty] | Frames Deliv. & Installation |  | 30% | Glass/ACP Delivery |  | 25% | Glass Installation |  | 30% | Sealant & Finishing |  | 10% | H.over |  | 5%
[6 empty] | W | H | M2 |  | M2 |  |  | Previous | Current | Total | Previous | Current | Total | Previous | Current | Total | Previous | Current | Total | Previous | Current | Total | PREVIOUS | CURRENT | TOTAL | PREVIOUS | CURRENT | TOTAL | TOTAL
1 | CW | CW01 | FOUR SIDED FIXED STR'L GLAZED CURTAIN WALL | M2 | 5568 | [5 empty] | 721.248 | 4015909 | 4278.8968 | 638.6032 | 4917.5 | 4229 | 93 | 4322 | 2755 | 1354.9 | 4109.9 |  | 0 |  |  | 0 |  | 762539.4738 | 16769.0166 | 779308.4904 | 1521955.2517 | 431343.073 | 1953298.3247 | 2732606.8151 | 68.04%
2 | CW | CW01 (A) | FOUR SIDED FIXED STR'L GLAZED CURVED CURTAIN WALL | M2 | 197 | [5 empty] | 1828.2487 | 360165 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
3 | CW | CW01- OPENINGS | ADDITIONAL PRICE FOR CURTAIN WALL FOR OPERABLE PANEL DUE TO ADDITIONAL THERMAL BREAK PROFILES FOR ALUMINUM FRAME, ALUMINUM LEAF AND ACCESSORIES & HARDWARE | NO. | 209 | [5 empty] | 640 | 133760 | 46 | 104 | 150 | 204 | 0 | 204 | 46 | 104 | 150 |  | 0 |  |  | 0 |  | 32640 | 0 | 32640 | 17664 | 39936 | 57600 | 90240 | 67.46%
4 | CW | CW02 | FOUR SIDED FIXED STR'L GLAZED CURTAIN WALL | M2 | 1005 | [5 empty] | 640.9791 | 644184 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
5 | CW | EXTERNAL STEEL SUPPORT FOR (CW01-CW02 ) | SUPPLY , FABRICATION & INSTALLATION FOR EXTERNAL STEEL STRUCTURE SUPORT BEAMS | TON | 3.9 | [5 empty] | 10380 | 40482 | 3.9 | 0 | 3.9 | 3.9 | 0 | 3.9 | 3.9 | 0 | 3.9 | 3.9 | 0 | 3.9 |  | 0 |  | 10120.5 | 0 | 10120.5 | 28337.4 | 0 | 28337.4 | 38457.9 | 95%
6 | ACP | ACP-01 | 4MM ALUMINUM COMPOSITE PANEL CLADDING ON SECONDARY STEEL ONLY SUB FRAME - STEEL TUBE SIZE 40X20X1.5MM | M2 | 3400 | [5 empty] | 320 | 1088000 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
7 | ACP | ACP-01(A) | 4MM ALUMINUM COMPOSITE PANEL CLADDING ON ALUPCO ALUMINUM CURTAIN WALL SYSTEM | M2 | 1430 | [5 empty] | 495 | 707850 | 1415.7 | 1928.3 | 3344 |  | 890 | 890 |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 110137.5 | 110137.5 | 210231.45 | 286352.55 | 496584 | 606721.5 | 85.71%
8 | ACP | ACP-02 | 4MM ALUMINUM COMPOSITE PANEL CLADDING ON SECONDARY STEEL ONLY SUB FRAME - STEEL TUBE SIZE 40X20X1.5MM | M2 | 4555 | [5 empty] | 320 | 1457600 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Windows | W01 | SINGLE PANEL FIXED WINDOW | NO. | 7 | [5 empty] | 436 | 3052 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Windows | W02 | SINGLE PANEL FIXED WINDOW | NO. | 9 | [5 empty] | 338 | 3042 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Windows | W03 | SINGLE PANEL FIXED WINDOW | NO. | 7 | [5 empty] | 523 | 3661 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Windows | W04 | SINGLE PANEL FIXED WINDOW | NO. | 2 | [5 empty] | 935 | 1870 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| CW | W05 | FIXED CURTAIN WALL | NO. | 359 | [5 empty] | 2047 | 734873 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| FRAMELESS | W06 | SINGLE PANEL FIXED FRAMLEES WINDOW | NO. | 7 | [5 empty] | 29523 | 206661 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| FRAMELESS | W07 | SINGLE PANEL FIXED FRAMLEES WINDOW | NO. | 1 | [5 empty] | 29967 | 29967 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Aut. Doors | GD01 | DOUBLE PANEL AUTOMATIC SLIDING BREAK OUT DOOR | NO. | 3 | [5 empty] | 27288 | 81864 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Aut. Doors | GD02 | DOUBLE PANEL AUTOMATIC SLIDING BREAK OUT DOOR | NO. | 1 | [5 empty] | 27170 | 27170 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Doors | GD03 | DOUBLE PANEL HINGED DOOR | NO. | 18 | [5 empty] | 3722 | 66996 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Doors | GD04 | SINGLE PANEL HINGED DOOR | NO. | 14 | [5 empty] | 2209 | 30926 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Aut. Doors | GD05 | DOUBLE PANEL AUTOMATIC SLIDING BREAK OUT DOOR | NO. | 14 | [5 empty] | 27052 | 378728 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Doors | GD06 | DOUBLE PANEL HINGED DOOR | NO. | 1 | [5 empty] | 2821 | 2821 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Doors | GD07 | DOUBLE PANEL HINGED DOOR | NO. | 15 | [5 empty] | 2733 | 40995 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Aut. Doors | GD08 | SINGLE PANEL AUTOMATIC SLIDING DOOR - STANDARD SLIDING SYSTEM - (NOT BREAK OUT ) | NO. | 28 | [5 empty] | 15414 | 431592 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Doors | GD09 | SINGLE PANEL HINGED DOOR | NO. | 2 | [5 empty] | 1864 | 3728 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Doors | GD10 | SINGLE PANEL HINGED DOOR | NO. | 70 | [5 empty] | 1689 | 118230 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Doors | GD11 | DOUBLE PANEL HINGED DOOR | NO. | 4 | [5 empty] | 2886 | 11544 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| FRAMELESS | G01 | FIXED FRAMELESS SINGLE GLASS PARTITION | M2 | 1225 | [5 empty] | 371 | 454475 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| FRAMELESS | G02 | FIXED FRAMELESS SINGLE GLASS PARTITION | M2 | 880 | [5 empty] | 371 | 326480 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Louver | LV | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM SANDTRAP LOUVER | M2 | 505 | [5 empty] | 1133 | 572165 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Louver | L01 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM SANDTRAP LOUVER | NO. | 3 | [5 empty] | 13426 | 40278 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Louver | L02 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM PERFORMANCE LOUVER | NO. | 3 | [5 empty] | 13726 | 41178 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Louver | L03 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM SANDTRAP LOUVER | NO. | 2 | [5 empty] | 14712 | 29424 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Louver | L04 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM SANDTRAP LOUVER | NO. | 1 | [5 empty] | 6539 | 6539 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Louver | L05 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM SANDTRAP LOUVER | NO. | 1 | [5 empty] | 4087 | 4087 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Louver | L06 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM PERFORMANCE LOUVER | NO. | 1 | [5 empty] | 15686 | 15686 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Louver | L07 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM LOUVER | NO. | 2 | [5 empty] | 14222 | 28444 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Louver | L08 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM PERFORMANCE LOUVER | NO. | 1 | [5 empty] | 1464 | 1464 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Louver | L09 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM PERFORMANCE LOUVER | NO. | 1 | [5 empty] | 5647 | 5647 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Louver | L10 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM SANDTRAP LOUVER | NO. | 3 | [5 empty] | 5492 | 16476 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Louver | L11 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM SANDTRAP LOUVER | NO. | 3 | [5 empty] | 7323 | 21969 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
9 | Louver | L12 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM PERFORMANCE LOUVER | NO. | 51 | [5 empty] | 4118 | 210018 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | GRAND TOTAL | [8 empty] | 12400000 | [15 empty] | 805299.9738 | 126906.5166 | 932206.4904 | 1778188.1017 | 757631.623 | 2535819.7247 | 3468026.2151 | 27.97%
[29 empty] | 0 | 7.518% |  | 0 | 20.45%
For Alusystems Factory CO. | [26 empty] | For Al Kuraiji Co. |  |  |  |  | 884538.1395
Eng. Radhwan M. Al Attar
Project Manager

## Sheet2
ALUSYSTEMS FACTORY Co.
PROGRESS REPORT # 4 -Breakdown - Fakeeh Hospital
PROJECT NO & NAME : Dr. Sulaiman Fakeeh Hospital / Al Madinah
| Date: | 45311
SN | Type | CODE | DESCRIPTION | UNIT |  | BOQ Qty. | BOQ Size |  |  | Actual QTY | Actual Area | UNIT PRICE |  |  |  | TOTAL PRICE | Frames Deliv. & Installation |  |  | Glass/ACP Delivery |  |  | Glass Installation |  |  | Sealant & Finishing + Hardware |  |  | Handing Over |  |  | VALUE OF WORK DONE ( DELIVERY ) 25% |  |  | VALUE OF WORK DONE ( INSTALLATION ) 75% |  |  | VALUE OF WORK DONE | Completion percentage %
[17 empty] | Frames Deliv. & Installation |  | 0.3 | Glass/ACP Delivery |  | 0.85 | Glass Installation |  | 0.25 | Sealant & Finishing |  | 0.1 | H.over |  | 0.05
[7 empty] | W | H | M2 |  | M2 | [5 empty] | Previous | Current | Total | Previous | Current | Total | Previous | Current | Total | Previous | Current | Total | Previous | Current | Total | PREVIOUS | CURRENT | TOTAL | PREVIOUS | CURRENT | TOTAL | TOTAL
[13 empty] | 1204772.7 | 3413522.65 | 1003977.25
1 | CW | CW01 | FOUR SIDED FIXED STR'L GLAZED CURTAIN WALL | M2 | 1078 | 5568 | [5 empty] | 721.248 | 216.3744 | 613.0608 | 180.312 | 4015909 | 4278.8968 | 638.6032 | 4917.5 | 4229 | 93 | 4322 | 2755 | 1354.9 | 4109.9 |  | 0 |  |  | 0 |  | 762539.4738 | 16769.0166 | 779308.4904 | 1521955.2517 | 431343.073 | 1953298.3247 | 2732606.8151 | 0.68045
2 | CW | CW01 (A) | FOUR SIDED FIXED STR'L GLAZED CURVED CURTAIN WALL | M2 |  | 197 | [5 empty] | 1828.2487 | 548.4746 |  |  | 360165 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CW | CW01- OPENINGS | ADDITIONAL PRICE FOR CURTAIN WALL FOR OPERABLE PANEL DUE TO ADDITIONAL THERMAL BREAK PROFILES FOR ALUMINUM FRAME, ALUMINUM LEAF AND ACCESSORIES & HARDWARE | NO. |  | 209 | [5 empty] | 640 | 480 | 100320 |  | 133760 | 46 | 104 | 150 | 204 | 0 | 204 | 46 | 104 | 150 |  | 0 |  |  | 0 |  | 32640 | 0 | 32640 | 17664 | 39936 | 57600 | 90240 | 0.67464
4 | CW | CW02 | FOUR SIDED FIXED STR'L GLAZED CURTAIN WALL | M2 |  | 1005 | [5 empty] | 640.9791 |  |  |  | 644184 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | CW | EXTERNAL STEEL SUPPORT FOR (CW01-CW02 ) | SUPPLY , FABRICATION & INSTALLATION FOR EXTERNAL STEEL STRUCTURE SUPORT BEAMS | TON |  | 3.9 | [5 empty] | 10380 | 9861 | 38457.9 |  | 40482 | 3.9 | 0 | 3.9 | 3.9 | 0 | 3.9 | 3.9 | 0 | 3.9 | 3.9 | 0 | 3.9 |  | 0 |  | 10120.5 | 0 | 10120.5 | 28337.4 | 0 | 28337.4 | 38457.9 | 0.95
6 | ACP | ACP-01 | 4MM ALUMINUM COMPOSITE PANEL CLADDING ON SECONDARY STEEL ONLY SUB FRAME - STEEL TUBE SIZE 40X20X1.5MM | M2 |  | 3400 | [5 empty] | 320 | 96 |  |  | 1088000 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | ACP | ACP-01(A) | 4MM ALUMINUM COMPOSITE PANEL CLADDING ON ALUPCO ALUMINUM CURTAIN WALL SYSTEM | M2 |  | 1430 | [5 empty] | 495 | 49.5 | 70785 |  | 707850 | 1415.7 | 1928.3 | 3344 |  | 890 | 890 |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 110137.5 | 110137.5 | 210231.45 | 286352.55 | 496584 | 606721.5 | 0.85713
8 | ACP | ACP-02 | 4MM ALUMINUM COMPOSITE PANEL CLADDING ON SECONDARY STEEL ONLY SUB FRAME - STEEL TUBE SIZE 40X20X1.5MM | M2 |  | 4555 | [5 empty] | 320 | 96 |  |  | 1457600 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Windows | W01 | SINGLE PANEL FIXED WINDOW | NO. |  | 7 | [5 empty] | 436 |  |  |  | 3052 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Windows | W02 | SINGLE PANEL FIXED WINDOW | NO. |  | 9 | [5 empty] | 338 |  |  |  | 3042 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Windows | W03 | SINGLE PANEL FIXED WINDOW | NO. |  | 7 | [5 empty] | 523 |  |  |  | 3661 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Windows | W04 | SINGLE PANEL FIXED WINDOW | NO. |  | 2 | [5 empty] | 935 |  |  |  | 1870 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| CW | W05 | FIXED CURTAIN WALL | NO. |  | 359 | [5 empty] | 2047 |  |  |  | 734873 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FRAMELESS | W06 | SINGLE PANEL FIXED FRAMLEES WINDOW | NO. |  | 7 | [5 empty] | 29523 |  |  |  | 206661 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FRAMELESS | W07 | SINGLE PANEL FIXED FRAMLEES WINDOW | NO. |  | 1 | [5 empty] | 29967 |  |  |  | 29967 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Aut. Doors | GD01 | DOUBLE PANEL AUTOMATIC SLIDING BREAK OUT DOOR | NO. |  | 3 | [5 empty] | 27288 |  |  |  | 81864 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Aut. Doors | GD02 | DOUBLE PANEL AUTOMATIC SLIDING BREAK OUT DOOR | NO. |  | 1 | [5 empty] | 27170 |  |  |  | 27170 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Doors | GD03 | DOUBLE PANEL HINGED DOOR | NO. |  | 18 | [5 empty] | 3722 |  |  |  | 66996 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Doors | GD04 | SINGLE PANEL HINGED DOOR | NO. |  | 14 | [5 empty] | 2209 |  |  |  | 30926 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Aut. Doors | GD05 | DOUBLE PANEL AUTOMATIC SLIDING BREAK OUT DOOR | NO. |  | 14 | [5 empty] | 27052 |  |  |  | 378728 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Doors | GD06 | DOUBLE PANEL HINGED DOOR | NO. |  | 1 | [5 empty] | 2821 |  |  |  | 2821 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Doors | GD07 | DOUBLE PANEL HINGED DOOR | NO. |  | 15 | [5 empty] | 2733 |  |  |  | 40995 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Aut. Doors | GD08 | SINGLE PANEL AUTOMATIC SLIDING DOOR - STANDARD SLIDING SYSTEM - (NOT BREAK OUT ) | NO. |  | 28 | [5 empty] | 15414 |  |  |  | 431592 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Doors | GD09 | SINGLE PANEL HINGED DOOR | NO. |  | 2 | [5 empty] | 1864 |  |  |  | 3728 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Doors | GD10 | SINGLE PANEL HINGED DOOR | NO. |  | 70 | [5 empty] | 1689 |  |  |  | 118230 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Doors | GD11 | DOUBLE PANEL HINGED DOOR | NO. |  | 4 | [5 empty] | 2886 |  |  |  | 11544 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FRAMELESS | G01 | FIXED FRAMELESS SINGLE GLASS PARTITION | M2 |  | 1225 | [5 empty] | 371 |  |  |  | 454475 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FRAMELESS | G02 | FIXED FRAMELESS SINGLE GLASS PARTITION | M2 |  | 880 | [5 empty] | 371 |  |  |  | 326480 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Louver | LV | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM SANDTRAP LOUVER | M2 |  | 505 | [5 empty] | 1133 |  |  |  | 572165 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Louver | L01 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM SANDTRAP LOUVER | NO. |  | 3 | [5 empty] | 13426 |  |  |  | 40278 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Louver | L02 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM PERFORMANCE LOUVER | NO. |  | 3 | [5 empty] | 13726 |  |  |  | 41178 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Louver | L03 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM SANDTRAP LOUVER | NO. |  | 2 | [5 empty] | 14712 |  |  |  | 29424 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Louver | L04 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM SANDTRAP LOUVER | NO. |  | 1 | [5 empty] | 6539 |  |  |  | 6539 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Louver | L05 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM SANDTRAP LOUVER | NO. |  | 1 | [5 empty] | 4087 |  |  |  | 4087 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Louver | L06 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM PERFORMANCE LOUVER | NO. |  | 1 | [5 empty] | 15686 |  |  |  | 15686 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Louver | L07 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM LOUVER | NO. |  | 2 | [5 empty] | 14222 |  |  |  | 28444 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Louver | L08 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM PERFORMANCE LOUVER | NO. |  | 1 | [5 empty] | 1464 |  |  |  | 1464 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Louver | L09 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM PERFORMANCE LOUVER | NO. |  | 1 | [5 empty] | 5647 |  |  |  | 5647 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Louver | L10 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM SANDTRAP LOUVER | NO. |  | 3 | [5 empty] | 5492 |  |  |  | 16476 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Louver | L11 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM SANDTRAP LOUVER | NO. |  | 3 | [5 empty] | 7323 |  |  |  | 21969 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Louver | L12 | SUPPLY , FABRICATION & INSTALLATION FOR FIXED ALUMINUM PERFORMANCE LOUVER | NO. |  | 51 | [5 empty] | 4118 | 1235.4 |  |  | 210018 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | GRAND TOTAL | [12 empty] | 12400000 | [15 empty] | 805299.9738 | 126906.5166 | 932206.4904 | 1778188.1017 | 757631.623 | 2535819.7247 | 3468026.2151 | 0.27968
[33 empty] | 0 | 0.075178 |  | 0 | 0.2045
For Alusystems Factory CO. | [30 empty] | For Al Kuraiji Co. |  |  |  |  | 884538.1395
Eng. Radhwan M. Al Attar
Project Manager

## Sheet1
| 1.1134 | T-Price | U-Price | QTTY | SPECs | Item Description | Item Code | T-Price | U-Price | QTTY | SPECs | Item Description | Item Code
1082006.965 | 194.326 | 1204773 | 216.37 | 5568 | Zone A Front elevation | Aluminum Frames Delivery & Installation | CW01-W01 | 1204773 | 216.37 | 5568 | Zone A Front elevation | Aluminum Frames Delivery & Installation | CW01-W01
3065444.699 | 550.5468 | 3413523 | 613 | 5568 | Hinged Window Inside curtainwall – ALUPCO 56D Alupco-AT-1500-Length 5100-Hight FOUR SIDED FIXED STR'L GLAZED CURTAIN WALL | Glass/ACP Delivery | CW01-W01 | 3413523 | 613 | 5568 | Hinged Window Inside curtainwall – ALUPCO 56D Alupco-AT-1500-Length 5100-Hight FOUR SIDED FIXED STR'L GLAZED CURTAIN WALL | Glass/ACP Delivery | CW01-W01
900130.5805 | 161.6614 | 1003977 | 180 | 5568 |  | Glass Installation | CW01-W01 | 1003977 | 180 | 5568 |  | Glass Installation | CW01-W01
30033.0925 | 143.699 | 33440 | 160 | 209 | ADDITIONAL PRICE FOR CURTAIN WALL FOR OPERABLE PANEL DUE TO ADDITIONAL THERMAL BREAK PROFILES FOR ALUMINUM FRAME, ALUMINUM LEAF AND ACCESSORIES & HARDWARE | Window Delivery | CW01- OPENINGS | 33440 | 160 | 209 | ADDITIONAL PRICE FOR CURTAIN WALL FOR OPERABLE PANEL DUE TO ADDITIONAL THERMAL BREAK PROFILES FOR ALUMINUM FRAME, ALUMINUM LEAF AND ACCESSORIES & HARDWARE | Window Delivery | CW01- OPENINGS
90099.2774 | 431.097 | 100320 | 480 | 209 |  | Window Delivery & Install | CW01- OPENINGS | 100320 | 480 | 209 |  | Window Delivery & Install | CW01- OPENINGS
0 | 0
190720.0166 | 133.3706 | 212355 | 148.5 | 1430 | 4MM ALUMINUM COMPOSITE PANEL CLADDING ON ALUPCO ALUMINUM CURTAIN WALL SYSTEM | Aluminum Frames Delivery & Installation | ACP-01(A) | 212355 | 148.5 | 1430 | 4MM ALUMINUM COMPOSITE PANEL CLADDING ON ALUPCO ALUMINUM CURTAIN WALL SYSTEM | Aluminum Frames Delivery & Installation | ACP-01(A)
381440.0332 | 266.7413 | 424710 | 297 | 1430 |  | Aluminum Cladding Delivery & Installation | ACP-01(A) | 424710 | 297 | 1430 |  | Aluminum Cladding Delivery & Installation | ACP-01(A)
63573.3389 | 44.4569 | 70785 | 49.5 | 1430 |  | Aluminum Cladding Delivery | ACP-01(A) | 70785 | 49.5 | 1430 |  | Aluminum Cladding Delivery | ACP-01(A)
34539.7628 | 8856.3494 | 38458 | 9861 | 3.9 | SUPPLY , FABRICATION & INSTALLATION FOR EXTERNAL STEEL STRUCTURE SUPORT BEAMS | EXTERNAL STEEL SUPPORT FOR (CW01-CW02 ) | CW01-CW02 | 38458 | 9861 | 3.9 | SUPPLY , FABRICATION & INSTALLATION FOR EXTERNAL STEEL STRUCTURE SUPORT BEAMS | EXTERNAL STEEL SUPPORT FOR (CW01-CW02 ) | CW01-CW02
5837987.7657 | 10782.2484 | [6 empty] | 6502341