## Sales & Estimation
First stage
Project opportunity
second Stage
Inquiry
Third Stage
Quotation

## Sheet1
6
2.1
1.5
1.2
1.2

## Sales
Stage 4
Purchase order /or contractor

## Account
Incoming
Purchase Order or contract
Contarct registration
outgoing:
Sending proceed order with all project data to:
Project Dept
Technical office
Operation
sales

## Technical office
Incoming
1- Project proceed order |  | all data will be collected by sales Dept and sent to technical office
2- contract copy
3- project B.O.Q without price
4- Project specification
5- Project IFC drawing
6- Site Survey if frequired
7- Design report if required
8- Submittal format
9-BIM Documents
outgoing:
to client:
1- submittal log for both material , samples and shop drawing |  |  | Alert to project manage /operation and Tech
2- Material Submittal |  |  | Alert to project manage /operation and Tech
3- Sample submittal |  |  | Alert to project manage /operation and Tech
4- shop drawing submittal |  |  | Alert to project manage /operation and Tech
5- Structural calculation |  |  | Alert to project manage /operation and Tech
6- RFI request
once above approved issue the following:
1- M.T.O (material Take off) |  |  | Alert to store/ purchase/project manager/operation /tech/production
2- Cutting list (4 types of cutting list) |  |  | Alert to production/project/operation/tech
SCL (steel cutting list issed for the steel Dept)
ACL (Aluminum cutting list issued for Aluminum Dep)
GCL ( issued for Glass dept)
M.T.O and ACL list will be in the same email

## Purchase
Incoming
M.T.O | (showing required material/ avialable reserved material)
Outgoing
Request for quotation |  | alert (project/operation/tech)
quotation from supplier |  | alert (project/operation/tech)
quotation comparison |  | protect/ operation
purchase order |  | alert (project/operation/tech/stores)
supplier invoices |  | Alert account/operation
Supplier Delivery note |  | alert (project/operation/tech/stores/account/production)

## Production
incoming
1- Cutting List
2- M.T.O
3- Production route
Outgoing
1- material request from store | [5 empty] | Alert (store/project/operation)
2- Production status (showing the staus on production route | [5 empty] | Alert (project/operation/ tech
3- Notice of completion | [5 empty] | Alert (logestic/project/operation/account)
Production route Example
Production Route and 3M costing
| Project | Curtain wall size (50 X 10 ) mt
A | The route start as follows:
Manpower
S.N | Process | Machine | Labour | Technician | Time (hour) | Total Manhour
1 | Tape Cutting | Single head | 1 |  | 1 | 1
2 | Taping | Manual | 1 | 1 | 4 | 8
3 | Mullion & Transom cutting | Double Head | 1 | 1 | 4 | 8
4 | Cleat cutting | Angle Automatic cutting |  | 1 | 4 | 4
5 | Cleat drilling | Vertical drill |  | 1 | 8 | 8
6 | Mullion Marking | Manual | 1 | 1 | 12 | 24
7 | Transom notching | End Milling Machine |  | 1 | 8 | 8
8 | Bracket cutting | Single head |  | 1 | 8 | 8
9 | Bracket Milling | 4 axis Machine |  | 1 | 16 | 16
10 | Cleat fixing on Mullion | Manual | 1 | 1 | 8 | 16
11 | U insert cutting | Single head |  | 1 | 2 | 2
12 | Glass toggle cutting | Single head |  | 1 | 2 | 2
13 | Glass toggle drlling | Vertical drill | 1 |  | 2 | 2
14 | Glass Support Cutting | Single head |  | 1 | 2 | 2
14 | Gasket cutting & fixing | Manual | 4 |  | 8 | 32
| Totak Manhour |  | 10 | 12 |  | 141
B | Total Cost (3M) | Total Material cost | Total manpower cost |  | Total Machine hour rate

## Logestic
Incoming
production complition notice |  | (imginary finish good store)
Project material request |  | Raw material store
Project tool request |  | Tool Store
outgoing
Delivery note | Alert to Project/production/account/operation

## Project
incoming
1- project contract
2-project B.O.Q with price
3- project schedule
4- approved material submittal
5- approved shop drawing
6- cutting list
7- M.T.O
8- Delivery note
9- detial project report from all depts showing all process and it is status
Outgoing
1- as built survey if required by technical office
1. Subcontractor detail and financial follow up and their cost reflection on the project cost
2. Out sourced hired labor and their cost reflected on the project
3. Rented equipment and reflected cost
4. Variation order and status up date
5. Incoming and outgoing letters
6. Project schedule status update
7. Alert for any delayed item based on project schedule
8. Payment certificate submittal and updated status
project reports
1- daily report
2- weekly report
3- monthly report
4- yearly report