## Sheet1
Badget | Start | End | Planned | Particular | Theoretical | Achievement
Project Managment Material - Planning Budget | 2023-01-10 | 06/26/2025 | -5827864 | -1729.16 | -1248172.45 | 0.14%
Project Managment Manpower - Planning Budget | 2023-01-10 | 06/26/2025 | -976118 | 0 | -209058.34 | 0%
Project Managment Machines - Planning Budget | 2023-01-10 | 06/26/2025 | -300344 | 0 | -64325.64 | 0%
Project Managment Services (Subcontractors) - Planning Budget | 2023-01-10 | 06/26/2025 | -150172 | -3405.88 | -32162.82 | 10.59%
Project Managment Miscellanious - Planning Budget | 2023-01-10 | 06/26/2025 | -75086 | -28830.42 | -16081.41 | 179.3%
Aluminum Factory Material - Planning Budget | 2023-01-10 | 01/22/2025 | -8659765 | -2725.07 | -2453600.08 | 0.11%
Aluminum Factory Manpower - Planning Budget | 2023-01-10 | 01/22/2025 | -1450438 | 0 | -410957.43 | 0%
Aluminum Factory Machines - Planning Budget | 2023-01-10 | 01/22/2025 | -446289 | 0 | -126448.55 | 0%
Aluminum Factory Services (Subcontractors) - Planning Budget | 2023-01-10 | 01/22/2025 | -223144 | 0 | -63224.13 | 0%
Aluminum Factory Miscellanious - Planning Budget | 2023-01-10 | 01/22/2025 | -111572 | 0 | -31612.07 | 0%
Steel Factory Material - Planning Budget | 2023-01-10 | 2024-01-12 | -35760 | -3258.47 | -11362.99 | 28.68%
Steel Factory Manpower - Planning Budget | 2023-01-10 | 2024-01-12 | -5990 | 0 | -1903.36 | 0%
Steel Factory Machines - Planning Budget | 2023-01-10 | 2024-01-12 | -1843 | 0 | -585.63 | 0%
Steel Factory Services (Subcontractors) - Planning Budget | 2023-01-10 | 2024-01-12 | -921 | 0 | -292.65 | 0%
Steel Factory Miscellanious - Planning Budget | 2023-01-10 | 2024-01-12 | -461 | 0 | -146.49 | 0%
Painting Factory Material - Planning Budget | 2023-01-10 | 2024-01-10 | -358419 | -2514.8 | -132820.12 | 1.89%
Painting Factory Manpower - Planning Budget | 2023-01-10 | 2024-01-10 | -60032 | 0 | -22246.19 | 0%
Painting Factory Machines - Planning Budget | 2023-01-10 | 2024-01-10 | -18471 | 0 | -6844.84 | 0%
Painting Factory Services (Subcontractors) - Planning Budget | 2023-01-10 | 2024-01-10 | -9236 | 0 | -3422.6 | 0%
Painting Factory Miscellanious - Planning Budget | 2023-01-10 | 2024-01-10 | -4618 | 0 | -1711.3 | 0%
Wood Factory COGS - FP Budget | 2023-01-10 | 2024-01-10 | 0 | 0 | 0 | 0%
Wood Factory Sales - Planning Budget | 2023-01-10 | 2024-01-10 | 0 | 0 | 0 | 0%
Wood Factory Material - Planning Budget | 2023-01-10 | 2024-01-10 | 0 | 0 | 0 | 0%
Wood Factory Manpower - Planning Budget | 2023-01-10 | 2024-01-10 | 0 | 0 | 0 | 0%
Wood Factory Machines - Planning Budget | 2023-01-10 | 2024-01-10 | 0 | 0 | 0 | 0%
Aluminum Factory Services (Subcontractors) - Planning Budget | 2023-01-10 | 01/22/2025 | -223144 | 0 | -63224.13 | 0%
Aluminum Factory Miscellanious - Planning Budget | 2023-01-10 | 01/22/2025 | -111572 | 0 | -31612.07 | 0%
Aluminum Factory Material - Planning Budget | 2023-01-10 | 01/22/2025 | -8659765 | -2725.07 | -2453600.08 | 0.11%
Aluminum Factory Manpower - Planning Budget | 2023-01-10 | 01/22/2025 | -1450438 | 0 | -410957.43 | 0%
Aluminum Factory Machines - Planning Budget | 2023-01-10 | 01/22/2025 | -446289 | 0 | -126448.55 | 0%
|  |  | -29607751 | -45188.87 | -7922821.35 | 7.36%