## Parents-Tasks
id | task_name | parent_task_id | company_id | project_id | partner_id | planned_date_begin | date_deadline | my_activity_date_deadline | stage_id | state | priority | progress | allocated_days | effective_days | subtask_effective_days | total_days_spent | remaining_days | closed_subtask_count | allow_milestones | milestone_id | rating_active | task_properties | rating_last_text | recurrence_id | sequence | user_ids | personal_stage_type_id | subtask_count | tag_ids | timesheet_ids | activity_ids | date_last_stage_update
| General |  | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-10-01 | 2025-07-26 |  | New Orders |  | Low |  | 665 | [7 empty] | TRUE
| Section / Contract Milestones - General | General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-24 | 2025-07-26 |  | New Orders |  | Low |  | 550 | [7 empty] | TRUE
| Mochup / Benchmark - Section / Contract Milestones - General | Section / Contract Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-24 | 2024-01-24 |  | New Orders |  | Low |  | 1 | [7 empty] | TRUE
| The Mound - Section / Contract Milestones - General | Section / Contract Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-23 | 2025-01-16 |  | New Orders |  | Low |  | 239 | [7 empty] | TRUE
| The Ring - Section / Contract Milestones - General | Section / Contract Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-28 | 2025-04-08 |  | New Orders |  | Low |  | 316 | [7 empty] | TRUE
| The Beach - Section / Contract Milestones - General | Section / Contract Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-08-19 | 2024-08-19 |  | New Orders |  | Low |  | 1 | [7 empty] | TRUE
| The Tail - Section / Contract Milestones - General | Section / Contract Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-05-01 | 2025-05-11 |  | New Orders |  | Low |  | 11 | [7 empty] | TRUE
| Time for Completion - Section / Contract Milestones - General | Section / Contract Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-07-26 | 2025-07-26 |  | New Orders |  | Low |  | 1 | [7 empty] | TRUE
| Key / Control Milestones - General | General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-24 | 2025-05-11 |  | New Orders |  | Low |  | 474 | [7 empty] | TRUE
| Mochup / Benchmark - Key / Control Milestones - General | Key / Control Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-24 | 2024-01-24 |  | New Orders |  | Low |  | 1 | [7 empty] | TRUE
| The Mound - Key / Control Milestones - General | Key / Control Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-09 | 2025-01-16 |  | New Orders |  | Low |  | 283 | [7 empty] | TRUE
| Level 01 - The Mound - Key / Control Milestones - General | The Mound - Key / Control Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-02 | 2025-01-02 |  | New Orders |  | Low |  | 1 | [7 empty] | TRUE
| Level 02 - The Mound - Key / Control Milestones - General | The Mound - Key / Control Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-09 | 2024-05-23 |  | New Orders |  | Low |  | 45 | [7 empty] | TRUE
| Level 03 - The Mound - Key / Control Milestones - General | The Mound - Key / Control Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-06-01 | 2024-07-14 |  | New Orders |  | Low |  | 44 | [7 empty] | TRUE
| Level 04 - The Mound - Key / Control Milestones - General | The Mound - Key / Control Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-06-12 | 2024-07-18 |  | New Orders |  | Low |  | 37 | [7 empty] | TRUE
| Level 05 & 06 - The Mound - Key / Control Milestones - General | The Mound - Key / Control Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-12 | 2025-01-16 |  | New Orders |  | Low |  | 36 | [7 empty] | TRUE
| The Ring - Key / Control Milestones - General | Key / Control Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-02 | 2025-04-08 |  | New Orders |  | Low |  | 342 | [7 empty] | TRUE
| Level 00 - The Ring - Key / Control Milestones - General | The Ring - Key / Control Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-02 | 2025-02-27 |  | New Orders |  | Low |  | 302 | [7 empty] | TRUE
| Level 01 - The Ring - Key / Control Milestones - General | The Ring - Key / Control Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-04 | 2025-04-08 |  | New Orders |  | Low |  | 340 | [7 empty] | TRUE
| The Beach - Key / Control Milestones - General | Key / Control Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-07-08 | 2024-08-19 |  | New Orders |  | Low |  | 43 | [7 empty] | TRUE
| Level 00 - The Beach - Key / Control Milestones - General | The Beach - Key / Control Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-07-08 | 2024-08-19 |  | New Orders |  | Low |  | 43 | [7 empty] | TRUE
| The Tail - Key / Control Milestones - General | Key / Control Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-05-01 | 2025-05-11 |  | New Orders |  | Low |  | 11 | [7 empty] | TRUE
| Level 01 - The Tail - Key / Control Milestones - General | The Tail - Key / Control Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-05-01 | 2025-05-01 |  | New Orders |  | Low |  | 1 | [7 empty] | TRUE
| Level 02 - The Tail - Key / Control Milestones - General | The Tail - Key / Control Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-05-11 | 2025-05-11 |  | New Orders |  | Low |  | 1 | [7 empty] | TRUE
| Mobilization - General | General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-10-08 | 2023-12-18 |  | New Orders |  | Low |  | 72 | [7 empty] | TRUE
| Contractor's Submissions - Mobilization - General | Mobilization - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-10-08 | 2023-12-10 |  | New Orders |  | Low |  | 64 | [7 empty] | TRUE
| Mobilization & Site Establishment - Mobilization - General | Mobilization - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-11 | 2023-12-18 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| Interface Milestones - General | General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2025-03-25 |  | New Orders |  | Low |  | 421 | [7 empty] | TRUE
| Procurement - Interface Milestones - General | Interface Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-20 | 2024-04-20 |  | New Orders |  | Low |  | 1 | [7 empty] | TRUE
| Approval of Detailed Engineering - Interface Milestones - General | Interface Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-09-09 | 2024-09-09 |  | New Orders |  | Low |  | 1 | [7 empty] | TRUE
| Manufacturing & Delivery - Interface Milestones - General | Interface Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-17 | 2024-12-17 |  | New Orders |  | Low |  | 1 | [7 empty] | TRUE
| Construction of Facilities - Interface Milestones - General | Interface Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2025-03-25 |  | New Orders |  | Low |  | 421 | [7 empty] | TRUE
| The Mound - Construction of Facilities - Interface Milestones - General | Construction of Facilities - Interface Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-11-26 |  | New Orders |  | Low |  | 302 | [7 empty] | TRUE
| Level 01 (Spa & Fitness) - The Mound - Construction of Facilities - Interface Milestones - General | The Mound - Construction of Facilities - Interface Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-10-19 | 2024-11-26 |  | New Orders |  | Low |  | 39 | [7 empty] | TRUE
| Level 02 - The Mound - Construction of Facilities - Interface Milestones - General | The Mound - Construction of Facilities - Interface Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-04-09 |  | New Orders |  | Low |  | 71 | [7 empty] | TRUE
| Level 03 - The Mound - Construction of Facilities - Interface Milestones - General | The Mound - Construction of Facilities - Interface Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-06 | 2024-06-01 |  | New Orders |  | Low |  | 88 | [7 empty] | TRUE
| Level 04 - The Mound - Construction of Facilities - Interface Milestones - General | The Mound - Construction of Facilities - Interface Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-05 | 2024-06-03 |  | New Orders |  | Low |  | 60 | [7 empty] | TRUE
| The Ring - Construction of Facilities - Interface Milestones - General | Construction of Facilities - Interface Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2025-02-19 |  | New Orders |  | Low |  | 387 | [7 empty] | TRUE
| Level 00 - The Ring - Construction of Facilities - Interface Milestones - General | The Ring - Construction of Facilities - Interface Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-04-16 |  | New Orders |  | Low |  | 78 | [7 empty] | TRUE
| Level 00 (Leave out Area) - The Ring - Construction of Facilities - Interface Milestones - General | The Ring - Construction of Facilities - Interface Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-10 | 2025-01-18 |  | New Orders |  | Low |  | 40 | [7 empty] | TRUE
| Level 01 - The Ring - Construction of Facilities - Interface Milestones - General | The Ring - Construction of Facilities - Interface Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-05-04 |  | New Orders |  | Low |  | 96 | [7 empty] | TRUE
| Level 01 (Leave out Area) - The Ring - Construction of Facilities - Interface Milestones - General | The Ring - Construction of Facilities - Interface Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-24 | 2025-02-19 |  | New Orders |  | Low |  | 58 | [7 empty] | TRUE
| The Beach - Construction of Facilities - Interface Milestones - General | Construction of Facilities - Interface Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-29 | 2024-07-08 |  | New Orders |  | Low |  | 71 | [7 empty] | TRUE
| Level 00 - The Beach - Construction of Facilities - Interface Milestones - General | The Beach - Construction of Facilities - Interface Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-29 | 2024-07-08 |  | New Orders |  | Low |  | 71 | [7 empty] | TRUE
| The Tail - Construction of Facilities - Interface Milestones - General | Construction of Facilities - Interface Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-15 | 2025-03-25 |  | New Orders |  | Low |  | 70 | [7 empty] | TRUE
| Level 01 - The Tail - Construction of Facilities - Interface Milestones - General | The Tail - Construction of Facilities - Interface Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-15 | 2025-03-17 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Level 02 - The Tail - Construction of Facilities - Interface Milestones - General | The Tail - Construction of Facilities - Interface Milestones - General | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-29 | 2025-03-25 |  | New Orders |  | Low |  | 56 | [7 empty] | TRUE
| Engineering - |  | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-10-22 | 2024-10-14 |  | New Orders |  | Low |  | 359 | [7 empty] | TRUE
| BIM Models - Engineering | Engineering | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-10-22 | 2024-08-26 |  | New Orders |  | Low |  | 310 | [7 empty] | TRUE
| Facade - BIM Models - Engineering | BIM Models - Engineering | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-10-22 | 2024-08-26 |  | New Orders |  | Low |  | 310 | [7 empty] | TRUE
| Preparation & Submission - Facade - BIM Models - Engineering | Facade - BIM Models - Engineering | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-10-22 | 2024-08-12 |  | New Orders |  | Low |  | 296 | [7 empty] | TRUE
| Hotel Rooms - Preparation & Submission - Facade - BIM Models - Engineering | Preparation & Submission - Facade - BIM Models - Engineering | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-10-22 | 2024-08-12 |  | New Orders |  | Low |  | 296 | [7 empty] | TRUE
| Buildings - Preparation & Submission - Facade - BIM Models - Engineering | Preparation & Submission - Facade - BIM Models - Engineering | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-14 | 2024-07-31 |  | New Orders |  | Low |  | 231 | [7 empty] | TRUE
| Site Wide - Preparation & Submission - Facade - BIM Models - Engineering | Preparation & Submission - Facade - BIM Models - Engineering | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-18 | 2024-01-29 |  | New Orders |  | Low |  | 12 | [7 empty] | TRUE
| Review & Approval by DAR / TRSDC - Facade - BIM Models - Engineering | Facade - BIM Models - Engineering | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-02 | 2024-08-26 |  | New Orders |  | Low |  | 299 | [7 empty] | TRUE
| Hotel Rooms - Review & Approval by DAR / TRSDC - Facade - BIM Models - Engineering | Review & Approval by DAR / TRSDC - Facade - BIM Models - Engineering | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-02 | 2024-08-26 |  | New Orders |  | Low |  | 299 | [7 empty] | TRUE
| Buildings - Review & Approval by DAR / TRSDC - Facade - BIM Models - Engineering | Review & Approval by DAR / TRSDC - Facade - BIM Models - Engineering | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-26 | 2024-08-14 |  | New Orders |  | Low |  | 233 | [7 empty] | TRUE
| Site Wide - Review & Approval by DAR / TRSDC - Facade - BIM Models - Engineering | Review & Approval by DAR / TRSDC - Facade - BIM Models - Engineering | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-02-12 |  | New Orders |  | Low |  | 14 | [7 empty] | TRUE
| Shop Drawings - Engineering | Engineering | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-16 | 2024-09-19 |  | New Orders |  | Low |  | 309 | [7 empty] | TRUE
| Facade - Shop Drawings - Engineering | Shop Drawings - Engineering | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-16 | 2024-09-19 |  | New Orders |  | Low |  | 309 | [7 empty] | TRUE
| Preparation & Submission - Facade - Shop Drawings - Engineering | Facade - Shop Drawings - Engineering | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-16 | 2024-09-07 |  | New Orders |  | Low |  | 297 | [7 empty] | TRUE
| Hotel Rooms - Preparation & Submission - Facade - Shop Drawings - Engineering | Preparation & Submission - Facade - Shop Drawings - Engineering | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-16 | 2024-09-07 |  | New Orders |  | Low |  | 297 | [7 empty] | TRUE
| Buildings - Preparation & Submission - Facade - Shop Drawings - Engineering | Preparation & Submission - Facade - Shop Drawings - Engineering | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-09 | 2024-08-26 |  | New Orders |  | Low |  | 231 | [7 empty] | TRUE
| Site Wide - Preparation & Submission - Facade - Shop Drawings - Engineering | Preparation & Submission - Facade - Shop Drawings - Engineering | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-13 | 2024-02-25 |  | New Orders |  | Low |  | 13 | [7 empty] | TRUE
| Review & Approval by DAR / TRSDC - Facade - Shop Drawings - Engineering | Facade - Shop Drawings - Engineering | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-28 | 2024-09-19 |  | New Orders |  | Low |  | 297 | [7 empty] | TRUE
| Hotel Rooms - Review & Approval by DAR / TRSDC - Facade - Shop Drawings - Engineering | Review & Approval by DAR / TRSDC - Facade - Shop Drawings - Engineering | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-28 | 2024-09-19 |  | New Orders |  | Low |  | 297 | [7 empty] | TRUE
| Buildings - Review & Approval by DAR / TRSDC - Facade - Shop Drawings - Engineering | Review & Approval by DAR / TRSDC - Facade - Shop Drawings - Engineering | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-21 | 2024-09-09 |  | New Orders |  | Low |  | 233 | [7 empty] | TRUE
| Site Wide - Review & Approval by DAR / TRSDC - Facade - Shop Drawings - Engineering | Review & Approval by DAR / TRSDC - Facade - Shop Drawings - Engineering | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-26 | 2024-03-10 |  | New Orders |  | Low |  | 14 | [7 empty] | TRUE
| Method Statements - Engineering | Engineering | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-09-10 | 2024-10-14 |  | New Orders |  | Low |  | 35 | [7 empty] | TRUE
| Facade - Method Statements - Engineering | Method Statements - Engineering | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-09-10 | 2024-10-14 |  | New Orders |  | Low |  | 35 | [7 empty] | TRUE
| Preparation & Submission - Facade - Method Statements - Engineering | Facade - Method Statements - Engineering | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-09-10 | 2024-10-05 |  | New Orders |  | Low |  | 26 | [7 empty] | TRUE
| Review & Approval by DAR / TRSDC - Facade - Method Statements - Engineering | Facade - Method Statements - Engineering | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-09-18 | 2024-10-14 |  | New Orders |  | Low |  | 27 | [7 empty] | TRUE
| Materials Procurement - |  | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-10-10 | 2024-12-17 |  | New Orders |  | Low |  | 435 | [7 empty] | TRUE
| Materials Submission - Materials Procurement | Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-10-10 | 2024-02-20 |  | New Orders |  | Low |  | 134 | [7 empty] | TRUE
| Facade - Materials Submission - Materials Procurement | Materials Submission - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-10-10 | 2024-02-20 |  | New Orders |  | Low |  | 134 | [7 empty] | TRUE
| Preparation & Submission - Facade - Materials Submission - Materials Procurement | Facade - Materials Submission - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-10-10 | 2024-02-06 |  | New Orders |  | Low |  | 120 | [7 empty] | TRUE
| Review & Approval by DAR / TRSDC - Facade - Materials Submission - Materials Procurement | Facade - Materials Submission - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-10-18 | 2024-02-20 |  | New Orders |  | Low |  | 126 | [7 empty] | TRUE
| Purchase materials - Materials Procurement | Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-04-20 |  | New Orders |  | Low |  | 165 | [7 empty] | TRUE
| Batch No.01 (Mackup / Benchmark) - Purchase materials - Materials Procurement | Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2023-12-09 |  | New Orders |  | Low |  | 32 | [7 empty] | TRUE
| The Ring - Batch No.01 (Mackup / Benchmark) - Purchase materials - Materials Procurement | Batch No.01 (Mackup / Benchmark) - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2023-12-09 |  | New Orders |  | Low |  | 32 | [7 empty] | TRUE
| Level 00 - The Ring - Batch No.01 (Mackup / Benchmark) - Purchase materials - Materials Procurement | The Ring - Batch No.01 (Mackup / Benchmark) - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2023-12-09 |  | New Orders |  | Low |  | 32 | [7 empty] | TRUE
| Zone R2 - Level 00 - The Ring - Batch No.01 (Mackup / Benchmark) - Purchase materials - Materials Procurement | Level 00 - The Ring - Batch No.01 (Mackup / Benchmark) - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2023-12-09 |  | New Orders |  | Low |  | 32 | [7 empty] | TRUE
| R2 / J0 - Zone R2 - Level 00 - The Ring - Batch No.01 (Mackup / Benchmark) - Purchase materials - Materials Procurement | Zone R2 - Level 00 - The Ring - Batch No.01 (Mackup / Benchmark) - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2023-12-09 |  | New Orders |  | Low |  | 32 | [7 empty] | TRUE
| Level 01 - The Ring - Batch No.01 (Mackup / Benchmark) - Purchase materials - Materials Procurement | The Ring - Batch No.01 (Mackup / Benchmark) - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2023-12-09 |  | New Orders |  | Low |  | 32 | [7 empty] | TRUE
| Zone R2 - Level 01 - The Ring - Batch No.01 (Mackup / Benchmark) - Purchase materials - Materials Procurement | Level 01 - The Ring - Batch No.01 (Mackup / Benchmark) - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2023-12-09 |  | New Orders |  | Low |  | 32 | [7 empty] | TRUE
| R2 / J1 - Zone R2 - Level 01 - The Ring - Batch No.01 (Mackup / Benchmark) - Purchase materials - Materials Procurement | Zone R2 - Level 01 - The Ring - Batch No.01 (Mackup / Benchmark) - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2023-12-09 |  | New Orders |  | Low |  | 32 | [7 empty] | TRUE
| Batch No.02 - Purchase materials - Materials Procurement | Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-18 |  | New Orders |  | Low |  | 72 | [7 empty] | TRUE
| The Mound - Batch No.02 - Purchase materials - Materials Procurement | Batch No.02 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-08 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Level 02 - The Mound - Batch No.02 - Purchase materials - Materials Procurement | The Mound - Batch No.02 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-08 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Zone M1 - Level 02 - The Mound - Batch No.02 - Purchase materials - Materials Procurement | Level 02 - The Mound - Batch No.02 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-08 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Zone M3 - Level 02 - The Mound - Batch No.02 - Purchase materials - Materials Procurement | Level 02 - The Mound - Batch No.02 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-08 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Level 03 - The Mound - Batch No.02 - Purchase materials - Materials Procurement | The Mound - Batch No.02 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-08 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Zone M1 - Level 03 - The Mound - Batch No.02 - Purchase materials - Materials Procurement | Level 03 - The Mound - Batch No.02 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-08 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Level 04 - The Mound - Batch No.02 - Purchase materials - Materials Procurement | The Mound - Batch No.02 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-08 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Zone M1 - Level 04 - The Mound - Batch No.02 - Purchase materials - Materials Procurement | Level 04 - The Mound - Batch No.02 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-08 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| The Ring - Batch No.02 - Purchase materials - Materials Procurement | Batch No.02 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-18 |  | New Orders |  | Low |  | 72 | [7 empty] | TRUE
| Level 00 - The Ring - Batch No.02 - Purchase materials - Materials Procurement | The Ring - Batch No.02 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-18 |  | New Orders |  | Low |  | 72 | [7 empty] | TRUE
| Zone R1 - Level 00 - The Ring - Batch No.02 - Purchase materials - Materials Procurement | Level 00 - The Ring - Batch No.02 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-08 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Zone R2 - Level 00 - The Ring - Batch No.02 - Purchase materials - Materials Procurement | Level 00 - The Ring - Batch No.02 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-08 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Zone R3 - Level 00 - The Ring - Batch No.02 - Purchase materials - Materials Procurement | Level 00 - The Ring - Batch No.02 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-18 |  | New Orders |  | Low |  | 72 | [7 empty] | TRUE
| Zone R4 - Level 00 - The Ring - Batch No.02 - Purchase materials - Materials Procurement | Level 00 - The Ring - Batch No.02 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-08 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Level 01 - The Ring - Batch No.02 - Purchase materials - Materials Procurement | The Ring - Batch No.02 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-08 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Zone R1 - Level 01 - The Ring - Batch No.02 - Purchase materials - Materials Procurement | Level 01 - The Ring - Batch No.02 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-08 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Zone R2 - Level 01 - The Ring - Batch No.02 - Purchase materials - Materials Procurement | Level 01 - The Ring - Batch No.02 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-08 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Zone R3 - Level 01 - The Ring - Batch No.02 - Purchase materials - Materials Procurement | Level 01 - The Ring - Batch No.02 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-08 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Zone R4 - Level 01 - The Ring - Batch No.02 - Purchase materials - Materials Procurement | Level 01 - The Ring - Batch No.02 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-08 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Batch No.03 - Purchase materials - Materials Procurement | Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-03-04 |  | New Orders |  | Low |  | 118 | [7 empty] | TRUE
| The Mound - Batch No.03 - Purchase materials - Materials Procurement | Batch No.03 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-03-04 |  | New Orders |  | Low |  | 118 | [7 empty] | TRUE
| Level 02 - The Mound - Batch No.03 - Purchase materials - Materials Procurement | The Mound - Batch No.03 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-03-04 |  | New Orders |  | Low |  | 118 | [7 empty] | TRUE
| Zone M2 - Level 02 - The Mound - Batch No.03 - Purchase materials - Materials Procurement | Level 02 - The Mound - Batch No.03 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-08 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Zone M4 - Level 02 - The Mound - Batch No.03 - Purchase materials - Materials Procurement | Level 02 - The Mound - Batch No.03 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-03-04 |  | New Orders |  | Low |  | 118 | [7 empty] | TRUE
| Level 03 - The Mound - Batch No.03 - Purchase materials - Materials Procurement | The Mound - Batch No.03 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-03-04 |  | New Orders |  | Low |  | 118 | [7 empty] | TRUE
| Zone M2 - Level 03 - The Mound - Batch No.03 - Purchase materials - Materials Procurement | Level 03 - The Mound - Batch No.03 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-08 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Zone M3 - Level 03 - The Mound - Batch No.03 - Purchase materials - Materials Procurement | Level 03 - The Mound - Batch No.03 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-08 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Zone M4 - Level 03 - The Mound - Batch No.03 - Purchase materials - Materials Procurement | Level 03 - The Mound - Batch No.03 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-03-04 |  | New Orders |  | Low |  | 118 | [7 empty] | TRUE
| Level 04 - The Mound - Batch No.03 - Purchase materials - Materials Procurement | The Mound - Batch No.03 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-08 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Zone M2 - Level 04 - The Mound - Batch No.03 - Purchase materials - Materials Procurement | Level 04 - The Mound - Batch No.03 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-08 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Zone M3 - Level 04 - The Mound - Batch No.03 - Purchase materials - Materials Procurement | Level 04 - The Mound - Batch No.03 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-01-08 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| The Beach - Batch No.03 - Purchase materials - Materials Procurement | Batch No.03 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-02-22 |  | New Orders |  | Low |  | 107 | [7 empty] | TRUE
| Level 00 - The Beach - Batch No.03 - Purchase materials - Materials Procurement | The Beach - Batch No.03 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-02-22 |  | New Orders |  | Low |  | 107 | [7 empty] | TRUE
| Zone B1 - Level 00 - The Beach - Batch No.03 - Purchase materials - Materials Procurement | Level 00 - The Beach - Batch No.03 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-02-10 |  | New Orders |  | Low |  | 95 | [7 empty] | TRUE
| Zone B2 - Level 00 - The Beach - Batch No.03 - Purchase materials - Materials Procurement | Level 00 - The Beach - Batch No.03 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-02-10 |  | New Orders |  | Low |  | 95 | [7 empty] | TRUE
| Zone B3 - Level 00 - The Beach - Batch No.03 - Purchase materials - Materials Procurement | Level 00 - The Beach - Batch No.03 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-02-10 |  | New Orders |  | Low |  | 95 | [7 empty] | TRUE
| Zone B5 - Level 00 - The Beach - Batch No.03 - Purchase materials - Materials Procurement | Level 00 - The Beach - Batch No.03 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-01 | 2024-02-22 |  | New Orders |  | Low |  | 84 | [7 empty] | TRUE
| Batch No.04 - Purchase materials - Materials Procurement | Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-04-20 |  | New Orders |  | Low |  | 165 | [7 empty] | TRUE
| The Mound - Batch No.04 - Purchase materials - Materials Procurement | Batch No.04 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-04-08 |  | New Orders |  | Low |  | 153 | [7 empty] | TRUE
| Level 01 - The Mound - Batch No.04 - Purchase materials - Materials Procurement | The Mound - Batch No.04 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-04-08 |  | New Orders |  | Low |  | 153 | [7 empty] | TRUE
| Zone M3 - Level 01 - The Mound - Batch No.04 - Purchase materials - Materials Procurement | Level 01 - The Mound - Batch No.04 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-04-08 |  | New Orders |  | Low |  | 153 | [7 empty] | TRUE
| Level 04 - The Mound - Batch No.04 - Purchase materials - Materials Procurement | The Mound - Batch No.04 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-03-16 |  | New Orders |  | Low |  | 130 | [7 empty] | TRUE
| Zone M4 - Level 04 - The Mound - Batch No.04 - Purchase materials - Materials Procurement | Level 04 - The Mound - Batch No.04 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-03-16 |  | New Orders |  | Low |  | 130 | [7 empty] | TRUE
| Level 05 & 06 - The Mound - Batch No.04 - Purchase materials - Materials Procurement | The Mound - Batch No.04 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-01 | 2024-04-08 |  | New Orders |  | Low |  | 130 | [7 empty] | TRUE
| Zone M2 - Level 05 & 06 - The Mound - Batch No.04 - Purchase materials - Materials Procurement | Level 05 & 06 - The Mound - Batch No.04 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-01 | 2024-04-08 |  | New Orders |  | Low |  | 130 | [7 empty] | TRUE
| Zone M4 - Level 05 & 06 - The Mound - Batch No.04 - Purchase materials - Materials Procurement | Level 05 & 06 - The Mound - Batch No.04 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-01 | 2024-04-08 |  | New Orders |  | Low |  | 130 | [7 empty] | TRUE
| The Beach - Batch No.04 - Purchase materials - Materials Procurement | Batch No.04 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-04-20 |  | New Orders |  | Low |  | 165 | [7 empty] | TRUE
| Level 00 - The Beach - Batch No.04 - Purchase materials - Materials Procurement | The Beach - Batch No.04 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-04-20 |  | New Orders |  | Low |  | 165 | [7 empty] | TRUE
| Zone B3 - Level 00 - The Beach - Batch No.04 - Purchase materials - Materials Procurement | Level 00 - The Beach - Batch No.04 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-04-20 |  | New Orders |  | Low |  | 165 | [7 empty] | TRUE
| Zone B4 - Level 00 - The Beach - Batch No.04 - Purchase materials - Materials Procurement | Level 00 - The Beach - Batch No.04 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-04-20 |  | New Orders |  | Low |  | 165 | [7 empty] | TRUE
| Batch No.05 - Purchase materials - Materials Procurement | Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-03-16 |  | New Orders |  | Low |  | 130 | [7 empty] | TRUE
| The Ring - Batch No.05 - Purchase materials - Materials Procurement | Batch No.05 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-03-16 |  | New Orders |  | Low |  | 130 | [7 empty] | TRUE
| Level 00 - The Ring - Batch No.05 - Purchase materials - Materials Procurement | The Ring - Batch No.05 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-03-16 |  | New Orders |  | Low |  | 130 | [7 empty] | TRUE
| Zone R2 (Leave out Area) - Level 00 - The Ring - Batch No.05 - Purchase materials - Materials Procurement | Level 00 - The Ring - Batch No.05 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-03-16 |  | New Orders |  | Low |  | 130 | [7 empty] | TRUE
| Zone R3 (Leave out Area) - Level 00 - The Ring - Batch No.05 - Purchase materials - Materials Procurement | Level 00 - The Ring - Batch No.05 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-03-16 |  | New Orders |  | Low |  | 130 | [7 empty] | TRUE
| Level 01 - The Ring - Batch No.05 - Purchase materials - Materials Procurement | The Ring - Batch No.05 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-03-16 |  | New Orders |  | Low |  | 130 | [7 empty] | TRUE
| Zone R2 (Leave out Area) - Level 01 - The Ring - Batch No.05 - Purchase materials - Materials Procurement | Level 01 - The Ring - Batch No.05 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-03-16 |  | New Orders |  | Low |  | 130 | [7 empty] | TRUE
| Zone R3 (Leave out Area) - Level 01 - The Ring - Batch No.05 - Purchase materials - Materials Procurement | Level 01 - The Ring - Batch No.05 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-03-16 |  | New Orders |  | Low |  | 130 | [7 empty] | TRUE
| The Tail - Batch No.05 - Purchase materials - Materials Procurement | Batch No.05 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-03-16 |  | New Orders |  | Low |  | 130 | [7 empty] | TRUE
| Level 01 - The Tail - Batch No.05 - Purchase materials - Materials Procurement | The Tail - Batch No.05 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-03-16 |  | New Orders |  | Low |  | 130 | [7 empty] | TRUE
| Zone T1 - Level 01 - The Tail - Batch No.05 - Purchase materials - Materials Procurement | Level 01 - The Tail - Batch No.05 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-03-16 |  | New Orders |  | Low |  | 130 | [7 empty] | TRUE
| Level 02 - The Tail - Batch No.05 - Purchase materials - Materials Procurement | The Tail - Batch No.05 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-03-16 |  | New Orders |  | Low |  | 130 | [7 empty] | TRUE
| Zone T2 - Level 02 - The Tail - Batch No.05 - Purchase materials - Materials Procurement | Level 02 - The Tail - Batch No.05 - Purchase materials - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-11-08 | 2024-03-16 |  | New Orders |  | Low |  | 130 | [7 empty] | TRUE
| Materials Fabrication & Delivery to Site - Materials Procurement | Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-12 | 2024-12-17 |  | New Orders |  | Low |  | 372 | [7 empty] | TRUE
| Batch No.01 (Mackup / Benchmark) - Materials Fabrication & Delivery to Site - Materials Procurement | Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-12 | 2023-12-18 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| The Ring - Batch No.01 (Mackup / Benchmark) - Materials Fabrication & Delivery to Site - Materials Procurement | Batch No.01 (Mackup / Benchmark) - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-12 | 2023-12-18 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| Level 00 - The Ring - Batch No.01 (Mackup / Benchmark) - Materials Fabrication & Delivery to Site - Materials Procurement | The Ring - Batch No.01 (Mackup / Benchmark) - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-12 | 2023-12-18 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| Zone R2 - Level 00 - The Ring - Batch No.01 (Mackup / Benchmark) - Materials Fabrication & Delivery to Site - Materials Procurement | Level 00 - The Ring - Batch No.01 (Mackup / Benchmark) - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-12 | 2023-12-18 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| R2 / J0 - Zone R2 - Level 00 - The Ring - Batch No.01 (Mackup / Benchmark) - Materials Fabrication & Delivery to Site - Materials Procurement | Zone R2 - Level 00 - The Ring - Batch No.01 (Mackup / Benchmark) - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-12 | 2023-12-18 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| Level 01 - The Ring - Batch No.01 (Mackup / Benchmark) - Materials Fabrication & Delivery to Site - Materials Procurement | The Ring - Batch No.01 (Mackup / Benchmark) - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-12 | 2023-12-18 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| Zone R2 - Level 01 - The Ring - Batch No.01 (Mackup / Benchmark) - Materials Fabrication & Delivery to Site - Materials Procurement | Level 01 - The Ring - Batch No.01 (Mackup / Benchmark) - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-12 | 2023-12-18 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| R2 / J1 - Zone R2 - Level 01 - The Ring - Batch No.01 (Mackup / Benchmark) - Materials Fabrication & Delivery to Site - Materials Procurement | Zone R2 - Level 01 - The Ring - Batch No.01 (Mackup / Benchmark) - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-12 | 2023-12-18 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-07 | 2024-03-02 |  | New Orders |  | Low |  | 56 | [7 empty] | TRUE
| The Mound - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-07 | 2024-03-02 |  | New Orders |  | Low |  | 56 | [7 empty] | TRUE
| Level 02 - The Mound - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | The Mound - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-07 | 2024-01-21 |  | New Orders |  | Low |  | 15 | [7 empty] | TRUE
| Zone M1 - Level 02 - The Mound - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 02 - The Mound - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-07 | 2024-01-14 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| Zone M3 - Level 02 - The Mound - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 02 - The Mound - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-13 | 2024-01-21 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| Level 03 - The Mound - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | The Mound - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-22 | 2024-01-30 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| Zone M1 - Level 03 - The Mound - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 03 - The Mound - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-22 | 2024-01-30 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| Level 04 - The Mound - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | The Mound - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-28 | 2024-03-02 |  | New Orders |  | Low |  | 4 | [7 empty] | TRUE
| Zone M1 - Level 04 - The Mound - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 04 - The Mound - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-28 | 2024-03-02 |  | New Orders |  | Low |  | 4 | [7 empty] | TRUE
| The Ring - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-13 | 2024-02-17 |  | New Orders |  | Low |  | 36 | [7 empty] | TRUE
| Level 00 - The Ring - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | The Ring - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-13 | 2024-02-11 |  | New Orders |  | Low |  | 30 | [7 empty] | TRUE
| Zone R1 - Level 00 - The Ring - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 00 - The Ring - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-17 | 2024-01-24 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| Zone R2 - Level 00 - The Ring - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 00 - The Ring - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-13 | 2024-01-18 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| Zone R3 - Level 00 - The Ring - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 00 - The Ring - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-17 | 2024-01-22 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| Zone R3/Speciality Restaurant - Level 00 - The Ring - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 00 - The Ring - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-02 | 2024-02-11 |  | New Orders |  | Low |  | 10 | [7 empty] | TRUE
| Zone R4 - Level 00 - The Ring - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 00 - The Ring - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-17 | 2024-01-24 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| Level 01 - The Ring - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | The Ring - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-13 | 2024-02-17 |  | New Orders |  | Low |  | 36 | [7 empty] | TRUE
| Zone R1 - Level 01 - The Ring - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 01 - The Ring - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-06 | 2024-02-17 |  | New Orders |  | Low |  | 12 | [7 empty] | TRUE
| Zone R2 - Level 01 - The Ring - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 01 - The Ring - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-13 | 2024-01-18 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| Zone R3 - Level 01 - The Ring - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 01 - The Ring - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-06 | 2024-02-16 |  | New Orders |  | Low |  | 11 | [7 empty] | TRUE
| Zone R4 - Level 01 - The Ring - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 01 - The Ring - Batch No.02 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-06 | 2024-02-16 |  | New Orders |  | Low |  | 11 | [7 empty] | TRUE
| Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-12 | 2024-04-05 |  | New Orders |  | Low |  | 54 | [7 empty] | TRUE
| The Mound - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-12 | 2024-04-03 |  | New Orders |  | Low |  | 52 | [7 empty] | TRUE
| Level 02 - The Mound - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | The Mound - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-12 | 2024-03-24 |  | New Orders |  | Low |  | 42 | [7 empty] | TRUE
| Zone M2 - Level 02 - The Mound - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 02 - The Mound - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-23 | 2024-03-06 |  | New Orders |  | Low |  | 13 | [7 empty] | TRUE
| Zone M4 - Level 02 - The Mound - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 02 - The Mound - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-12 | 2024-03-24 |  | New Orders |  | Low |  | 42 | [7 empty] | TRUE
| Level 03 - The Mound - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | The Mound - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-20 | 2024-04-01 |  | New Orders |  | Low |  | 42 | [7 empty] | TRUE
| Zone M2 - Level 03 - The Mound - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 03 - The Mound - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-26 | 2024-03-10 |  | New Orders |  | Low |  | 14 | [7 empty] | TRUE
| Zone M2/Gourmet Bistro Café - Level 03 - The Mound - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 03 - The Mound - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-22 | 2024-03-24 |  | New Orders |  | Low |  | 3 | [7 empty] | TRUE
| Zone M3 - Level 03 - The Mound - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 03 - The Mound - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-20 | 2024-02-26 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| Zone M4 - Level 03 - The Mound - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 03 - The Mound - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-11 | 2024-04-01 |  | New Orders |  | Low |  | 22 | [7 empty] | TRUE
| Level 04 - The Mound - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | The Mound - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-22 | 2024-04-03 |  | New Orders |  | Low |  | 13 | [7 empty] | TRUE
| Zone M2 - Level 04 - The Mound - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 04 - The Mound - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-22 | 2024-04-01 |  | New Orders |  | Low |  | 11 | [7 empty] | TRUE
| Zone M3 - Level 04 - The Mound - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 04 - The Mound - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-26 | 2024-04-03 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| The Beach - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-28 | 2024-04-05 |  | New Orders |  | Low |  | 38 | [7 empty] | TRUE
| Level 00 - The Beach - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | The Beach - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-28 | 2024-04-05 |  | New Orders |  | Low |  | 38 | [7 empty] | TRUE
| Zone B1 - Level 00 - The Beach - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 00 - The Beach - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-28 | 2024-03-12 |  | New Orders |  | Low |  | 14 | [7 empty] | TRUE
| Zone B2 - Level 00 - The Beach - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 00 - The Beach - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-16 | 2024-03-30 |  | New Orders |  | Low |  | 15 | [7 empty] | TRUE
| Zone B3 - Level 00 - The Beach - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 00 - The Beach - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-29 | 2024-04-05 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| Zone B5/Mice - Level 00 - The Beach - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 00 - The Beach - Batch No.03 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-28 | 2024-03-28 |  | New Orders |  | Low |  | 30 | [7 empty] | TRUE
| Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-01 | 2024-10-19 |  | New Orders |  | Low |  | 202 | [7 empty] | TRUE
| The Mound - Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-01 | 2024-10-19 |  | New Orders |  | Low |  | 202 | [7 empty] | TRUE
| Level 01 - The Mound - Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | The Mound - Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-08-28 | 2024-09-10 |  | New Orders |  | Low |  | 14 | [7 empty] | TRUE
| Zone M3/SPA & Fitness - Level 01 - The Mound - Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 01 - The Mound - Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-08-28 | 2024-09-10 |  | New Orders |  | Low |  | 14 | [7 empty] | TRUE
| Level 04 - The Mound - Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | The Mound - Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-01 | 2024-04-07 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| Zone M4 - Level 04 - The Mound - Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 04 - The Mound - Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-01 | 2024-04-07 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| Level 05 & 06 - The Mound - Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | The Mound - Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-09-10 | 2024-10-19 |  | New Orders |  | Low |  | 40 | [7 empty] | TRUE
| Zone M2/Piazza - Level 05 & 06 - The Mound - Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 05 & 06 - The Mound - Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-09-10 | 2024-09-29 |  | New Orders |  | Low |  | 20 | [7 empty] | TRUE
| Zone M4/Piazza - Level 05 & 06 - The Mound - Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 05 & 06 - The Mound - Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-09-10 | 2024-10-19 |  | New Orders |  | Low |  | 40 | [7 empty] | TRUE
| The Beach - Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-06-04 | 2024-06-14 |  | New Orders |  | Low |  | 11 | [7 empty] | TRUE
| Level 00 - The Beach - Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | The Beach - Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-06-04 | 2024-06-14 |  | New Orders |  | Low |  | 11 | [7 empty] | TRUE
| Zone B3/Beach Bar & Pool Change - Level 00 - The Beach - Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 00 - The Beach - Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-06-04 | 2024-06-05 |  | New Orders |  | Low |  | 2 | [7 empty] | TRUE
| Zone B4/Pool Bar - Level 00 - The Beach - Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 00 - The Beach - Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-06-04 | 2024-06-14 |  | New Orders |  | Low |  | 11 | [7 empty] | TRUE
| Zone B4/Teen & Children Recreation - Level 00 - The Beach - Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 00 - The Beach - Batch No.04 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-06-04 | 2024-06-14 |  | New Orders |  | Low |  | 11 | [7 empty] | TRUE
| Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-09-27 | 2024-12-17 |  | New Orders |  | Low |  | 82 | [7 empty] | TRUE
| The Ring - Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-09-27 | 2024-12-17 |  | New Orders |  | Low |  | 82 | [7 empty] | TRUE
| Level 00 - The Ring - Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | The Ring - Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-09-27 | 2024-12-13 |  | New Orders |  | Low |  | 78 | [7 empty] | TRUE
| Zone R2 (Leave out Area) - Level 00 - The Ring - Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 00 - The Ring - Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-11-15 | 2024-12-13 |  | New Orders |  | Low |  | 29 | [7 empty] | TRUE
| Zone R3 (Leave out Area) - Level 00 - The Ring - Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 00 - The Ring - Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-09-27 | 2024-10-22 |  | New Orders |  | Low |  | 26 | [7 empty] | TRUE
| Level 01 - The Ring - Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | The Ring - Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-10-01 | 2024-12-17 |  | New Orders |  | Low |  | 78 | [7 empty] | TRUE
| Zone R2 (Leave out Area) - Level 01 - The Ring - Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 01 - The Ring - Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-11-20 | 2024-12-17 |  | New Orders |  | Low |  | 28 | [7 empty] | TRUE
| Zone R3 (Leave out Area) - Level 01 - The Ring - Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 01 - The Ring - Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-10-01 | 2024-10-25 |  | New Orders |  | Low |  | 25 | [7 empty] | TRUE
| The Tail - Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-10-05 | 2024-12-09 |  | New Orders |  | Low |  | 66 | [7 empty] | TRUE
| Level 01 - The Tail - Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | The Tail - Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-10-05 | 2024-11-04 |  | New Orders |  | Low |  | 31 | [7 empty] | TRUE
| Zone T1 - Level 01 - The Tail - Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 01 - The Tail - Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-10-05 | 2024-11-04 |  | New Orders |  | Low |  | 31 | [7 empty] | TRUE
| Level 02 - The Tail - Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | The Tail - Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-10-25 | 2024-12-09 |  | New Orders |  | Low |  | 46 | [7 empty] | TRUE
| Zone T2 - Level 02 - The Tail - Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | Level 02 - The Tail - Batch No.05 - Materials Fabrication & Delivery to Site - Materials Procurement | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-10-25 | 2024-12-09 |  | New Orders |  | Low |  | 46 | [7 empty] | TRUE
| Construction - |  | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-19 | 2025-03-25 |  | New Orders |  | Low |  | 463 | [7 empty] | TRUE
| The Mound - Construction | Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-12-05 |  | New Orders |  | Low |  | 311 | [7 empty] | TRUE
| Level 01 - The Mound - Construction | The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-10-19 | 2024-11-26 |  | New Orders |  | Low |  | 39 | [7 empty] | TRUE
| Zone M3 - Level 01 - The Mound - Construction | Level 01 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-10-19 | 2024-11-26 |  | New Orders |  | Low |  | 39 | [7 empty] | TRUE
| SPA & Fitness - Zone M3 - Level 01 - The Mound - Construction | Zone M3 - Level 01 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-10-19 | 2024-11-26 |  | New Orders |  | Low |  | 39 | [7 empty] | TRUE
| Level 02 - The Mound - Construction | The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-04-09 |  | New Orders |  | Low |  | 71 | [7 empty] | TRUE
| Zone M1 - Level 02 - The Mound - Construction | Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-02-26 |  | New Orders |  | Low |  | 28 | [7 empty] | TRUE
| M1 / L2 - Zone M1 - Level 02 - The Mound - Construction | Zone M1 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-02-12 |  | New Orders |  | Low |  | 14 | [7 empty] | TRUE
| S. K. L. - 1 - M1 / L2 - Zone M1 - Level 02 - The Mound - Construction | M1 / L2 - Zone M1 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-02-04 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - 2 - M1 / L2 - Zone M1 - Level 02 - The Mound - Construction | M1 / L2 - Zone M1 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-02-04 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - M1 / L2 - Zone M1 - Level 02 - The Mound - Construction | M1 / L2 - Zone M1 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-03 | 2024-02-07 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. L. - M1 / L2 - Zone M1 - Level 02 - The Mound - Construction | M1 / L2 - Zone M1 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-03 | 2024-02-07 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. R. - M1 / L2 - Zone M1 - Level 02 - The Mound - Construction | M1 / L2 - Zone M1 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-06 | 2024-02-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| JS. L. - M1 / L2 - Zone M1 - Level 02 - The Mound - Construction | M1 / L2 - Zone M1 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-06 | 2024-02-12 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| JS. R. - M1 / L2 - Zone M1 - Level 02 - The Mound - Construction | M1 / L2 - Zone M1 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-06 | 2024-02-12 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| M1 / M2 - Zone M1 - Level 02 - The Mound - Construction | Zone M1 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-13 | 2024-02-26 |  | New Orders |  | Low |  | 14 | [7 empty] | TRUE
| S. K. L. - M1 / M2 - Zone M1 - Level 02 - The Mound - Construction | M1 / M2 - Zone M1 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-13 | 2024-02-18 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - M1 / M2 - Zone M1 - Level 02 - The Mound - Construction | M1 / M2 - Zone M1 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-13 | 2024-02-18 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CL. - M1 / M2 - Zone M1 - Level 02 - The Mound - Construction | M1 / M2 - Zone M1 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-17 | 2024-02-21 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. CR. - M1 / M2 - Zone M1 - Level 02 - The Mound - Construction | M1 / M2 - Zone M1 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-17 | 2024-02-21 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. L. - M1 / M2 - Zone M1 - Level 02 - The Mound - Construction | M1 / M2 - Zone M1 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-20 | 2024-02-26 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| S. DQ. R. - M1 / M2 - Zone M1 - Level 02 - The Mound - Construction | M1 / M2 - Zone M1 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-20 | 2024-02-26 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| Zone M2 - Level 02 - The Mound - Construction | Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-07 | 2024-04-09 |  | New Orders |  | Low |  | 34 | [7 empty] | TRUE
| M2 / H2 - Zone M2 - Level 02 - The Mound - Construction | Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-07 | 2024-03-19 |  | New Orders |  | Low |  | 13 | [7 empty] | TRUE
| S. K. L. - 1 - M2 / H2 - Zone M2 - Level 02 - The Mound - Construction | M2 / H2 - Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-07 | 2024-03-12 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - 2 - M2 / H2 - Zone M2 - Level 02 - The Mound - Construction | M2 / H2 - Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-07 | 2024-03-12 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - M2 / H2 - Zone M2 - Level 02 - The Mound - Construction | M2 / H2 - Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-11 | 2024-03-16 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - M2 / H2 - Zone M2 - Level 02 - The Mound - Construction | M2 / H2 - Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-11 | 2024-03-16 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. R. - M2 / H2 - Zone M2 - Level 02 - The Mound - Construction | M2 / H2 - Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-14 | 2024-03-19 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| JS. L. - M2 / H2 - Zone M2 - Level 02 - The Mound - Construction | M2 / H2 - Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-14 | 2024-03-19 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| JS. R. - M2 / H2 - Zone M2 - Level 02 - The Mound - Construction | M2 / H2 - Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-14 | 2024-03-19 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| M2 / I2 - Zone M2 - Level 02 - The Mound - Construction | Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-20 | 2024-03-26 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| S. K. L. - M2 / I2 - Zone M2 - Level 02 - The Mound - Construction | M2 / I2 - Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-20 | 2024-03-25 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - M2 / I2 - Zone M2 - Level 02 - The Mound - Construction | M2 / I2 - Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-20 | 2024-03-25 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| 1BS. CL. 2 - M2 / I2 - Zone M2 - Level 02 - The Mound - Construction | M2 / I2 - Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-20 | 2024-03-26 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| 1BS. CR. 2 - M2 / I2 - Zone M2 - Level 02 - The Mound - Construction | M2 / I2 - Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-20 | 2024-03-26 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| M2 / J2 - Zone M2 - Level 02 - The Mound - Construction | Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-27 | 2024-04-09 |  | New Orders |  | Low |  | 14 | [7 empty] | TRUE
| S. K. L. - 1 - M2 / J2 - Zone M2 - Level 02 - The Mound - Construction | M2 / J2 - Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-27 | 2024-04-01 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - 2 - M2 / J2 - Zone M2 - Level 02 - The Mound - Construction | M2 / J2 - Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-27 | 2024-04-01 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - M2 / J2 - Zone M2 - Level 02 - The Mound - Construction | M2 / J2 - Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-27 | 2024-04-01 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - M2 / J2 - Zone M2 - Level 02 - The Mound - Construction | M2 / J2 - Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-31 | 2024-04-04 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. R. - M2 / J2 - Zone M2 - Level 02 - The Mound - Construction | M2 / J2 - Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-31 | 2024-04-04 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| JS. L. - M2 / J2 - Zone M2 - Level 02 - The Mound - Construction | M2 / J2 - Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-03 | 2024-04-09 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| JS. R. - M2 / J2 - Zone M2 - Level 02 - The Mound - Construction | M2 / J2 - Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-03 | 2024-04-09 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| M2 / K2 - Zone M2 - Level 02 - The Mound - Construction | Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-27 | 2024-04-06 |  | New Orders |  | Low |  | 11 | [7 empty] | TRUE
| S. K. L. - M2 / K2 - Zone M2 - Level 02 - The Mound - Construction | M2 / K2 - Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-27 | 2024-04-01 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. R. - M2 / K2 - Zone M2 - Level 02 - The Mound - Construction | M2 / K2 - Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-27 | 2024-04-01 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| 1BS. CL. 1 - M2 / K2 - Zone M2 - Level 02 - The Mound - Construction | M2 / K2 - Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-31 | 2024-04-06 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| 1BS. CR. 1 - M2 / K2 - Zone M2 - Level 02 - The Mound - Construction | M2 / K2 - Zone M2 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-31 | 2024-04-06 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| Zone M3 - Level 02 - The Mound - Construction | Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-03-11 |  | New Orders |  | Low |  | 42 | [7 empty] | TRUE
| M3 / E2 - Zone M3 - Level 02 - The Mound - Construction | Zone M3 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-02-11 |  | New Orders |  | Low |  | 13 | [7 empty] | TRUE
| S. K. L. - 1 - M3 / E2 - Zone M3 - Level 02 - The Mound - Construction | M3 / E2 - Zone M3 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-02-04 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - 2 - M3 / E2 - Zone M3 - Level 02 - The Mound - Construction | M3 / E2 - Zone M3 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-02-04 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - 1 - M3 / E2 - Zone M3 - Level 02 - The Mound - Construction | M3 / E2 - Zone M3 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-03 | 2024-02-07 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. R. - 2 - M3 / E2 - Zone M3 - Level 02 - The Mound - Construction | M3 / E2 - Zone M3 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-03 | 2024-02-07 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. CL. - M3 / E2 - Zone M3 - Level 02 - The Mound - Construction | M3 / E2 - Zone M3 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-06 | 2024-02-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CR. - M3 / E2 - Zone M3 - Level 02 - The Mound - Construction | M3 / E2 - Zone M3 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-06 | 2024-02-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| M3 / F2 - Zone M3 - Level 02 - The Mound - Construction | Zone M3 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-12 | 2024-02-27 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| S. K. R. - M3 / F2 - Zone M3 - Level 02 - The Mound - Construction | M3 / F2 - Zone M3 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-12 | 2024-02-17 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - M3 / F2 - Zone M3 - Level 02 - The Mound - Construction | M3 / F2 - Zone M3 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-12 | 2024-02-17 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. R. - M3 / F2 - Zone M3 - Level 02 - The Mound - Construction | M3 / F2 - Zone M3 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-15 | 2024-02-20 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| JS. L. - M3 / F2 - Zone M3 - Level 02 - The Mound - Construction | M3 / F2 - Zone M3 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-15 | 2024-02-21 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| JS. R. - M3 / F2 - Zone M3 - Level 02 - The Mound - Construction | M3 / F2 - Zone M3 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-20 | 2024-02-27 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| M3 / G2 - Zone M3 - Level 02 - The Mound - Construction | Zone M3 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-28 | 2024-03-11 |  | New Orders |  | Low |  | 13 | [7 empty] | TRUE
| S. K. CL. - M3 / G2 - Zone M3 - Level 02 - The Mound - Construction | M3 / G2 - Zone M3 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-28 | 2024-03-04 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CR. - M3 / G2 - Zone M3 - Level 02 - The Mound - Construction | M3 / G2 - Zone M3 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-28 | 2024-03-04 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - M3 / G2 - Zone M3 - Level 02 - The Mound - Construction | M3 / G2 - Zone M3 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-03 | 2024-03-07 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. R. - M3 / G2 - Zone M3 - Level 02 - The Mound - Construction | M3 / G2 - Zone M3 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-06 | 2024-03-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| Zone M4 - Level 02 - The Mound - Construction | Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-20 | 2024-04-09 |  | New Orders |  | Low |  | 50 | [7 empty] | TRUE
| M4 / A2 - Zone M4 - Level 02 - The Mound - Construction | Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-20 | 2024-03-04 |  | New Orders |  | Low |  | 14 | [7 empty] | TRUE
| S. K. L. - 1 - M4 / A2 - Zone M4 - Level 02 - The Mound - Construction | M4 / A2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-20 | 2024-02-26 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| S. K. L. - 2 - M4 / A2 - Zone M4 - Level 02 - The Mound - Construction | M4 / A2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-20 | 2024-02-26 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| S. K. R. - 1 - M4 / A2 - Zone M4 - Level 02 - The Mound - Construction | M4 / A2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-25 | 2024-02-29 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. R. - 2 - M4 / A2 - Zone M4 - Level 02 - The Mound - Construction | M4 / A2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-25 | 2024-02-29 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. CL. - M4 / A2 - Zone M4 - Level 02 - The Mound - Construction | M4 / A2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-28 | 2024-03-04 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CR. - M4 / A2 - Zone M4 - Level 02 - The Mound - Construction | M4 / A2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-28 | 2024-03-04 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| M4 / B2 - Zone M4 - Level 02 - The Mound - Construction | Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-05 | 2024-03-26 |  | New Orders |  | Low |  | 22 | [7 empty] | TRUE
| S. K. R. - M4 / B2 - Zone M4 - Level 02 - The Mound - Construction | M4 / B2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-05 | 2024-03-10 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - M4 / B2 - Zone M4 - Level 02 - The Mound - Construction | M4 / B2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-09 | 2024-03-13 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. R. - M4 / B2 - Zone M4 - Level 02 - The Mound - Construction | M4 / B2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-12 | 2024-03-17 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| JS. L. - M4 / B2 - Zone M4 - Level 02 - The Mound - Construction | M4 / B2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-16 | 2024-03-21 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| JS. R. - M4 / B2 - Zone M4 - Level 02 - The Mound - Construction | M4 / B2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-20 | 2024-03-26 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| M4 / C2 - Zone M4 - Level 02 - The Mound - Construction | Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-28 | 2024-03-14 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| S. K. CL. - M4 / C2 - Zone M4 - Level 02 - The Mound - Construction | M4 / C2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-28 | 2024-03-04 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CR. - M4 / C2 - Zone M4 - Level 02 - The Mound - Construction | M4 / C2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-03 | 2024-03-07 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. L. - M4 / C2 - Zone M4 - Level 02 - The Mound - Construction | M4 / C2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-06 | 2024-03-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. R. - M4 / C2 - Zone M4 - Level 02 - The Mound - Construction | M4 / C2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-10 | 2024-03-14 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| M4 / D2 - Zone M4 - Level 02 - The Mound - Construction | Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-16 | 2024-03-27 |  | New Orders |  | Low |  | 12 | [7 empty] | TRUE
| S. K. CL. - M4 / D2 - Zone M4 - Level 02 - The Mound - Construction | M4 / D2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-16 | 2024-03-20 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. CR. - M4 / D2 - Zone M4 - Level 02 - The Mound - Construction | M4 / D2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-19 | 2024-03-24 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - M4 / D2 - Zone M4 - Level 02 - The Mound - Construction | M4 / D2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-23 | 2024-03-27 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. R. - M4 / D2 - Zone M4 - Level 02 - The Mound - Construction | M4 / D2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-23 | 2024-03-27 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| M4 / N2 - Zone M4 - Level 02 - The Mound - Construction | Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-28 | 2024-04-09 |  | New Orders |  | Low |  | 13 | [7 empty] | TRUE
| S. K. L. - 1 - M4 / N2 - Zone M4 - Level 02 - The Mound - Construction | M4 / N2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-28 | 2024-04-02 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - 2 - M4 / N2 - Zone M4 - Level 02 - The Mound - Construction | M4 / N2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-28 | 2024-04-02 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - 1 - M4 / N2 - Zone M4 - Level 02 - The Mound - Construction | M4 / N2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-01 | 2024-04-06 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - 2 - M4 / N2 - Zone M4 - Level 02 - The Mound - Construction | M4 / N2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-01 | 2024-04-06 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CL. - M4 / N2 - Zone M4 - Level 02 - The Mound - Construction | M4 / N2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-04 | 2024-04-09 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CR. - M4 / N2 - Zone M4 - Level 02 - The Mound - Construction | M4 / N2 - Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-04 | 2024-04-09 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| M4/Balustrade - Zone M4 - Level 02 - The Mound - Construction | Zone M4 - Level 02 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-25 | 2024-04-09 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| Level 03 - The Mound - Construction | The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-06 | 2024-06-01 |  | New Orders |  | Low |  | 88 | [7 empty] | TRUE
| Zone M1 - Level 03 - The Mound - Construction | Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-06 | 2024-04-20 |  | New Orders |  | Low |  | 46 | [7 empty] | TRUE
| M1 / I3 - Zone M1 - Level 03 - The Mound - Construction | Zone M1 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-06 | 2024-03-18 |  | New Orders |  | Low |  | 13 | [7 empty] | TRUE
| S. DQ. L. - M1 / I3 - Zone M1 - Level 03 - The Mound - Construction | M1 / I3 - Zone M1 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-06 | 2024-03-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. R. - M1 / I3 - Zone M1 - Level 03 - The Mound - Construction | M1 / I3 - Zone M1 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-06 | 2024-03-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| 1BS. CL. 1 - M1 / I3 - Zone M1 - Level 03 - The Mound - Construction | M1 / I3 - Zone M1 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-10 | 2024-03-18 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| 1BS. CR. 1 - M1 / I3 - Zone M1 - Level 03 - The Mound - Construction | M1 / I3 - Zone M1 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-10 | 2024-03-18 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| M1 / J3 - Zone M1 - Level 03 - The Mound - Construction | Zone M1 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-19 | 2024-04-20 |  | New Orders |  | Low |  | 33 | [7 empty] | TRUE
| S. K. L. - 1 - M1 / J3 - Zone M1 - Level 03 - The Mound - Construction | M1 / J3 - Zone M1 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-19 | 2024-03-24 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - 2 - M1 / J3 - Zone M1 - Level 03 - The Mound - Construction | M1 / J3 - Zone M1 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-19 | 2024-03-24 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - 3 - M1 / J3 - Zone M1 - Level 03 - The Mound - Construction | M1 / J3 - Zone M1 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-25 | 2024-03-30 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - 1 - M1 / J3 - Zone M1 - Level 03 - The Mound - Construction | M1 / J3 - Zone M1 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-31 | 2024-04-04 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. R. - 2 - M1 / J3 - Zone M1 - Level 03 - The Mound - Construction | M1 / J3 - Zone M1 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-31 | 2024-04-04 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. CL. - M1 / J3 - Zone M1 - Level 03 - The Mound - Construction | M1 / J3 - Zone M1 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-06 | 2024-04-14 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| S. K. CR. - M1 / J3 - Zone M1 - Level 03 - The Mound - Construction | M1 / J3 - Zone M1 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-06 | 2024-04-14 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| S. DQ. R. - M1 / J3 - Zone M1 - Level 03 - The Mound - Construction | M1 / J3 - Zone M1 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-15 | 2024-04-20 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| Zone M2 - Level 03 - The Mound - Construction | Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-11 | 2024-05-11 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| M2 / G3 - Zone M2 - Level 03 - The Mound - Construction | Zone M2 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-11 | 2024-04-09 |  | New Orders |  | Low |  | 30 | [7 empty] | TRUE
| S. K. L. - M2 / G3 - Zone M2 - Level 03 - The Mound - Construction | M2 / G3 - Zone M2 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-11 | 2024-03-16 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - M2 / G3 - Zone M2 - Level 03 - The Mound - Construction | M2 / G3 - Zone M2 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-14 | 2024-03-19 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CL. - M2 / G3 - Zone M2 - Level 03 - The Mound - Construction | M2 / G3 - Zone M2 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-18 | 2024-03-23 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CR. - M2 / G3 - Zone M2 - Level 03 - The Mound - Construction | M2 / G3 - Zone M2 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-21 | 2024-03-26 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - 1 - M2 / G3 - Zone M2 - Level 03 - The Mound - Construction | M2 / G3 - Zone M2 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-25 | 2024-03-30 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - 2 - M2 / G3 - Zone M2 - Level 03 - The Mound - Construction | M2 / G3 - Zone M2 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-28 | 2024-04-02 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. R. - 1 - M2 / G3 - Zone M2 - Level 03 - The Mound - Construction | M2 / G3 - Zone M2 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-01 | 2024-04-06 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. R. - 2 - M2 / G3 - Zone M2 - Level 03 - The Mound - Construction | M2 / G3 - Zone M2 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-04 | 2024-04-09 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| M2 / H3 - Zone M2 - Level 03 - The Mound - Construction | Zone M2 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-14 | 2024-05-06 |  | New Orders |  | Low |  | 23 | [7 empty] | TRUE
| S. K. L. - 1 - M2 / H3 - Zone M2 - Level 03 - The Mound - Construction | M2 / H3 - Zone M2 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-14 | 2024-04-18 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. L. - 2 - M2 / H3 - Zone M2 - Level 03 - The Mound - Construction | M2 / H3 - Zone M2 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-17 | 2024-04-22 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - 1 - M2 / H3 - Zone M2 - Level 03 - The Mound - Construction | M2 / H3 - Zone M2 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-21 | 2024-04-25 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. R. - 2 - M2 / H3 - Zone M2 - Level 03 - The Mound - Construction | M2 / H3 - Zone M2 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-24 | 2024-04-29 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CL. - M2 / H3 - Zone M2 - Level 03 - The Mound - Construction | M2 / H3 - Zone M2 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-28 | 2024-05-02 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. CR. - M2 / H3 - Zone M2 - Level 03 - The Mound - Construction | M2 / H3 - Zone M2 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-01 | 2024-05-06 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| M2 / Gourmet Bistro Café - Zone M2 - Level 03 - The Mound - Construction | Zone M2 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-20 | 2024-05-11 |  | New Orders |  | Low |  | 22 | [7 empty] | TRUE
| Zone M3 - Level 03 - The Mound - Construction | Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-06 | 2024-05-05 |  | New Orders |  | Low |  | 61 | [7 empty] | TRUE
| M3 / D3 - Zone M3 - Level 03 - The Mound - Construction | Zone M3 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-06 | 2024-03-24 |  | New Orders |  | Low |  | 19 | [7 empty] | TRUE
| S. K. L. - M3 / D3 - Zone M3 - Level 03 - The Mound - Construction | M3 / D3 - Zone M3 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-06 | 2024-03-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - M3 / D3 - Zone M3 - Level 03 - The Mound - Construction | M3 / D3 - Zone M3 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-10 | 2024-03-14 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| 1BS. CL. 2 - M3 / D3 - Zone M3 - Level 03 - The Mound - Construction | M3 / D3 - Zone M3 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-13 | 2024-03-19 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| 1BS. CR. 2 - M3 / D3 - Zone M3 - Level 03 - The Mound - Construction | M3 / D3 - Zone M3 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-18 | 2024-03-24 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| M3 / E3 - Zone M3 - Level 03 - The Mound - Construction | Zone M3 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-25 | 2024-04-09 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| S. K. L. - M3 / E3 - Zone M3 - Level 03 - The Mound - Construction | M3 / E3 - Zone M3 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-25 | 2024-03-30 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - M3 / E3 - Zone M3 - Level 03 - The Mound - Construction | M3 / E3 - Zone M3 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-25 | 2024-03-30 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CL. - M3 / E3 - Zone M3 - Level 03 - The Mound - Construction | M3 / E3 - Zone M3 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-28 | 2024-04-02 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CR. - M3 / E3 - Zone M3 - Level 03 - The Mound - Construction | M3 / E3 - Zone M3 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-28 | 2024-04-02 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - M3 / E3 - Zone M3 - Level 03 - The Mound - Construction | M3 / E3 - Zone M3 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-01 | 2024-04-06 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. R. - M3 / E3 - Zone M3 - Level 03 - The Mound - Construction | M3 / E3 - Zone M3 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-04 | 2024-04-09 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| M3 / F3 - Zone M3 - Level 03 - The Mound - Construction | Zone M3 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-14 | 2024-05-05 |  | New Orders |  | Low |  | 22 | [7 empty] | TRUE
| S. K. L. - 1 - M3 / F3 - Zone M3 - Level 03 - The Mound - Construction | M3 / F3 - Zone M3 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-14 | 2024-04-18 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. L. - 2 - M3 / F3 - Zone M3 - Level 03 - The Mound - Construction | M3 / F3 - Zone M3 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-14 | 2024-04-18 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. L. - 3 - M3 / F3 - Zone M3 - Level 03 - The Mound - Construction | M3 / F3 - Zone M3 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-17 | 2024-04-22 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - M3 / F3 - Zone M3 - Level 03 - The Mound - Construction | M3 / F3 - Zone M3 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-17 | 2024-04-22 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - M3 / F3 - Zone M3 - Level 03 - The Mound - Construction | M3 / F3 - Zone M3 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-21 | 2024-04-25 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. R. - 1 - M3 / F3 - Zone M3 - Level 03 - The Mound - Construction | M3 / F3 - Zone M3 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-21 | 2024-04-25 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. R. - 2 - M3 / F3 - Zone M3 - Level 03 - The Mound - Construction | M3 / F3 - Zone M3 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-24 | 2024-04-29 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| J. S. SL. - M3 / F3 - Zone M3 - Level 03 - The Mound - Construction | M3 / F3 - Zone M3 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-24 | 2024-04-30 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| J. S. SR. - M3 / F3 - Zone M3 - Level 03 - The Mound - Construction | M3 / F3 - Zone M3 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-29 | 2024-05-05 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| Zone M4 - Level 03 - The Mound - Construction | Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-30 | 2024-06-01 |  | New Orders |  | Low |  | 64 | [7 empty] | TRUE
| M4 / A3 - Zone M4 - Level 03 - The Mound - Construction | Zone M4 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-30 | 2024-04-20 |  | New Orders |  | Low |  | 22 | [7 empty] | TRUE
| S. K. L. - M4 / A3 - Zone M4 - Level 03 - The Mound - Construction | M4 / A3 - Zone M4 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-30 | 2024-04-06 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| S. DQ. R. - M4 / A3 - Zone M4 - Level 03 - The Mound - Construction | M4 / A3 - Zone M4 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-02 | 2024-04-07 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| 1BS. CL. 1 - M4 / A3 - Zone M4 - Level 03 - The Mound - Construction | M4 / A3 - Zone M4 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-06 | 2024-04-15 |  | New Orders |  | Low |  | 10 | [7 empty] | TRUE
| 1BS. CR. 1 - M4 / A3 - Zone M4 - Level 03 - The Mound - Construction | M4 / A3 - Zone M4 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-14 | 2024-04-20 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| M4 / B3 - Zone M4 - Level 03 - The Mound - Construction | Zone M4 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-21 | 2024-05-07 |  | New Orders |  | Low |  | 17 | [7 empty] | TRUE
| S. K. R. - M4 / B3 - Zone M4 - Level 03 - The Mound - Construction | M4 / B3 - Zone M4 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-21 | 2024-04-25 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. CR. - M4 / B3 - Zone M4 - Level 03 - The Mound - Construction | M4 / B3 - Zone M4 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-24 | 2024-04-29 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - M4 / B3 - Zone M4 - Level 03 - The Mound - Construction | M4 / B3 - Zone M4 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-28 | 2024-05-02 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. R. - M4 / B3 - Zone M4 - Level 03 - The Mound - Construction | M4 / B3 - Zone M4 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-28 | 2024-05-02 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| JS. L. - M4 / B3 - Zone M4 - Level 03 - The Mound - Construction | M4 / B3 - Zone M4 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-01 | 2024-05-07 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| M4 / C3 - Zone M4 - Level 03 - The Mound - Construction | Zone M4 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-08 | 2024-05-18 |  | New Orders |  | Low |  | 11 | [7 empty] | TRUE
| S. K. L. - M4 / C3 - Zone M4 - Level 03 - The Mound - Construction | M4 / C3 - Zone M4 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-08 | 2024-05-13 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. R. - M4 / C3 - Zone M4 - Level 03 - The Mound - Construction | M4 / C3 - Zone M4 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-08 | 2024-05-13 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| 1BS. CL. 1 - M4 / C3 - Zone M4 - Level 03 - The Mound - Construction | M4 / C3 - Zone M4 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-12 | 2024-05-18 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| 1BS. CR. 1 - M4 / C3 - Zone M4 - Level 03 - The Mound - Construction | M4 / C3 - Zone M4 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-12 | 2024-05-18 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| M4 / K3 - Zone M4 - Level 03 - The Mound - Construction | Zone M4 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-19 | 2024-06-01 |  | New Orders |  | Low |  | 14 | [7 empty] | TRUE
| S. K. R. - M4 / K3 - Zone M4 - Level 03 - The Mound - Construction | M4 / K3 - Zone M4 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-19 | 2024-05-23 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. L. - M4 / K3 - Zone M4 - Level 03 - The Mound - Construction | M4 / K3 - Zone M4 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-22 | 2024-05-27 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. R. - M4 / K3 - Zone M4 - Level 03 - The Mound - Construction | M4 / K3 - Zone M4 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-22 | 2024-05-27 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| JS. L. - M4 / K3 - Zone M4 - Level 03 - The Mound - Construction | M4 / K3 - Zone M4 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-26 | 2024-06-01 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| JS. R. - M4 / K3 - Zone M4 - Level 03 - The Mound - Construction | M4 / K3 - Zone M4 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-26 | 2024-06-01 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| M4/Balustrade - Zone M4 - Level 03 - The Mound - Construction | Zone M4 - Level 03 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-19 | 2024-05-27 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| Level 04 - The Mound - Construction | The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-06 | 2024-06-03 |  | New Orders |  | Low |  | 59 | [7 empty] | TRUE
| Zone M1 - Level 04 - The Mound - Construction | Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-06 | 2024-05-01 |  | New Orders |  | Low |  | 26 | [7 empty] | TRUE
| M1 / F4 - Zone M1 - Level 04 - The Mound - Construction | Zone M1 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-06 | 2024-05-01 |  | New Orders |  | Low |  | 26 | [7 empty] | TRUE
| S. K. L. - M1 / F4 - Zone M1 - Level 04 - The Mound - Construction | M1 / F4 - Zone M1 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-06 | 2024-04-14 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| S. K. R. - M1 / F4 - Zone M1 - Level 04 - The Mound - Construction | M1 / F4 - Zone M1 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-09 | 2024-04-17 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| S. K. CL. - M1 / F4 - Zone M1 - Level 04 - The Mound - Construction | M1 / F4 - Zone M1 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-16 | 2024-04-21 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CR. - M1 / F4 - Zone M1 - Level 04 - The Mound - Construction | M1 / F4 - Zone M1 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-20 | 2024-04-24 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. L. - M1 / F4 - Zone M1 - Level 04 - The Mound - Construction | M1 / F4 - Zone M1 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-23 | 2024-04-28 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. R. - M1 / F4 - Zone M1 - Level 04 - The Mound - Construction | M1 / F4 - Zone M1 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-27 | 2024-05-01 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| Zone M2 - Level 04 - The Mound - Construction | Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-06 | 2024-05-20 |  | New Orders |  | Low |  | 45 | [7 empty] | TRUE
| M2 / D4 - Zone M2 - Level 04 - The Mound - Construction | Zone M2 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-06 | 2024-05-01 |  | New Orders |  | Low |  | 26 | [7 empty] | TRUE
| S. K. L. - M2 / D4 - Zone M2 - Level 04 - The Mound - Construction | M2 / D4 - Zone M2 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-06 | 2024-04-14 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| S. K. R. - M2 / D4 - Zone M2 - Level 04 - The Mound - Construction | M2 / D4 - Zone M2 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-09 | 2024-04-17 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| S. K. CL. - M2 / D4 - Zone M2 - Level 04 - The Mound - Construction | M2 / D4 - Zone M2 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-16 | 2024-04-21 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CR. - M2 / D4 - Zone M2 - Level 04 - The Mound - Construction | M2 / D4 - Zone M2 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-20 | 2024-04-24 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. L. - M2 / D4 - Zone M2 - Level 04 - The Mound - Construction | M2 / D4 - Zone M2 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-23 | 2024-04-28 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. R. - M2 / D4 - Zone M2 - Level 04 - The Mound - Construction | M2 / D4 - Zone M2 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-27 | 2024-05-01 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| M2 / E4 - Zone M2 - Level 04 - The Mound - Construction | Zone M2 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-02 | 2024-05-20 |  | New Orders |  | Low |  | 19 | [7 empty] | TRUE
| S. DQ. L. - M2 / E4 - Zone M2 - Level 04 - The Mound - Construction | M2 / E4 - Zone M2 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-02 | 2024-05-07 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. R. - M2 / E4 - Zone M2 - Level 04 - The Mound - Construction | M2 / E4 - Zone M2 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-06 | 2024-05-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| 1BS. CL. 2 - M2 / E4 - Zone M2 - Level 04 - The Mound - Construction | M2 / E4 - Zone M2 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-09 | 2024-05-15 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| 1BS. CR. 2 - M2 / E4 - Zone M2 - Level 04 - The Mound - Construction | M2 / E4 - Zone M2 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-14 | 2024-05-20 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| Zone M3 - Level 04 - The Mound - Construction | Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-06 | 2024-05-09 |  | New Orders |  | Low |  | 34 | [7 empty] | TRUE
| M3 / C4 - Zone M3 - Level 04 - The Mound - Construction | Zone M3 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-06 | 2024-05-09 |  | New Orders |  | Low |  | 34 | [7 empty] | TRUE
| S. K. L. - M3 / C4 - Zone M3 - Level 04 - The Mound - Construction | M3 / C4 - Zone M3 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-06 | 2024-04-14 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| S. K. R. - 1 - M3 / C4 - Zone M3 - Level 04 - The Mound - Construction | M3 / C4 - Zone M3 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-09 | 2024-04-17 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| S. K. R. - 2 - M3 / C4 - Zone M3 - Level 04 - The Mound - Construction | M3 / C4 - Zone M3 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-16 | 2024-04-21 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - 3 - M3 / C4 - Zone M3 - Level 04 - The Mound - Construction | M3 / C4 - Zone M3 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-20 | 2024-04-24 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. CR. - M3 / C4 - Zone M3 - Level 04 - The Mound - Construction | M3 / C4 - Zone M3 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-23 | 2024-04-28 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - 1 - M3 / C4 - Zone M3 - Level 04 - The Mound - Construction | M3 / C4 - Zone M3 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-27 | 2024-05-01 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. L. - 2 - M3 / C4 - Zone M3 - Level 04 - The Mound - Construction | M3 / C4 - Zone M3 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-30 | 2024-05-05 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| JS. L. - M3 / C4 - Zone M3 - Level 04 - The Mound - Construction | M3 / C4 - Zone M3 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-04 | 2024-05-09 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| Zone M4 - Level 04 - The Mound - Construction | Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-06 | 2024-06-03 |  | New Orders |  | Low |  | 59 | [7 empty] | TRUE
| M4 / A4 - Zone M4 - Level 04 - The Mound - Construction | Zone M4 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-06 | 2024-04-27 |  | New Orders |  | Low |  | 22 | [7 empty] | TRUE
| S. K. L. - M4 / A4 - Zone M4 - Level 04 - The Mound - Construction | M4 / A4 - Zone M4 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-06 | 2024-04-15 |  | New Orders |  | Low |  | 10 | [7 empty] | TRUE
| S. DQ. R. - M4 / A4 - Zone M4 - Level 04 - The Mound - Construction | M4 / A4 - Zone M4 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-09 | 2024-04-17 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| 1BS. CL. 1 - M4 / A4 - Zone M4 - Level 04 - The Mound - Construction | M4 / A4 - Zone M4 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-16 | 2024-04-22 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| 1BS. CR. 1 - M4 / A4 - Zone M4 - Level 04 - The Mound - Construction | M4 / A4 - Zone M4 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-21 | 2024-04-27 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| M4 / B4 - Zone M4 - Level 04 - The Mound - Construction | Zone M4 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-28 | 2024-05-15 |  | New Orders |  | Low |  | 18 | [7 empty] | TRUE
| S. K. L. - M4 / B4 - Zone M4 - Level 04 - The Mound - Construction | M4 / B4 - Zone M4 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-28 | 2024-05-04 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| S. DQ. R. - M4 / B4 - Zone M4 - Level 04 - The Mound - Construction | M4 / B4 - Zone M4 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-01 | 2024-05-06 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| 1BS. CL. 2 - M4 / B4 - Zone M4 - Level 04 - The Mound - Construction | M4 / B4 - Zone M4 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-05 | 2024-05-11 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| 1BS. CR. 2 - M4 / B4 - Zone M4 - Level 04 - The Mound - Construction | M4 / B4 - Zone M4 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-09 | 2024-05-15 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| M4 / G4 - Zone M4 - Level 04 - The Mound - Construction | Zone M4 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-16 | 2024-06-03 |  | New Orders |  | Low |  | 19 | [7 empty] | TRUE
| S. K. R. - M4 / G4 - Zone M4 - Level 04 - The Mound - Construction | M4 / G4 - Zone M4 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-16 | 2024-05-21 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - M4 / G4 - Zone M4 - Level 04 - The Mound - Construction | M4 / G4 - Zone M4 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-20 | 2024-05-25 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| 1BS. CL. 2 - M4 / G4 - Zone M4 - Level 04 - The Mound - Construction | M4 / G4 - Zone M4 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-23 | 2024-05-29 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| 1BS. CR. 2 - M4 / G4 - Zone M4 - Level 04 - The Mound - Construction | M4 / G4 - Zone M4 - Level 04 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-28 | 2024-06-03 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| Level 05 & 06 - The Mound - Construction | The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-09-28 | 2024-12-05 |  | New Orders |  | Low |  | 69 | [7 empty] | TRUE
| Zone M2 - Level 05 & 06 - The Mound - Construction | Level 05 & 06 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-09-28 | 2024-10-31 |  | New Orders |  | Low |  | 34 | [7 empty] | TRUE
| M2 / Piazza - Zone M2 - Level 05 & 06 - The Mound - Construction | Zone M2 - Level 05 & 06 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-09-28 | 2024-10-31 |  | New Orders |  | Low |  | 34 | [7 empty] | TRUE
| Zone M4 - Level 05 & 06 - The Mound - Construction | Level 05 & 06 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-11-02 | 2024-12-05 |  | New Orders |  | Low |  | 34 | [7 empty] | TRUE
| M4 / Piazza - Zone M4 - Level 05 & 06 - The Mound - Construction | Zone M4 - Level 05 & 06 - The Mound - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-11-02 | 2024-12-05 |  | New Orders |  | Low |  | 34 | [7 empty] | TRUE
| The Ring - Construction | Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-19 | 2025-02-19 |  | New Orders |  | Low |  | 429 | [7 empty] | TRUE
| Level 00 - The Ring - Construction | The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-19 | 2025-01-18 |  | New Orders |  | Low |  | 397 | [7 empty] | TRUE
| Zone R2 (Mackup / Benchmark) - Level 00 - The Ring - Construction | Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-19 | 2024-01-03 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| R2 / J0 - Zone R2 (Mackup / Benchmark) - Level 00 - The Ring - Construction | Zone R2 (Mackup / Benchmark) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-19 | 2024-01-03 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| S. K. L. - 1 - R2 / J0 - Zone R2 (Mackup / Benchmark) - Level 00 - The Ring - Construction | R2 / J0 - Zone R2 (Mackup / Benchmark) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-19 | 2024-01-03 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| S. K. L. - 2 - R2 / J0 - Zone R2 (Mackup / Benchmark) - Level 00 - The Ring - Construction | R2 / J0 - Zone R2 (Mackup / Benchmark) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-19 | 2024-01-03 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| S. K. L. - 3 - R2 / J0 - Zone R2 (Mackup / Benchmark) - Level 00 - The Ring - Construction | R2 / J0 - Zone R2 (Mackup / Benchmark) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-19 | 2024-01-03 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| S. K. R. - 1 - R2 / J0 - Zone R2 (Mackup / Benchmark) - Level 00 - The Ring - Construction | R2 / J0 - Zone R2 (Mackup / Benchmark) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-19 | 2024-01-03 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| S. K. R. - 2 - R2 / J0 - Zone R2 (Mackup / Benchmark) - Level 00 - The Ring - Construction | R2 / J0 - Zone R2 (Mackup / Benchmark) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-19 | 2024-01-03 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| S. K. CL. - R2 / J0 - Zone R2 (Mackup / Benchmark) - Level 00 - The Ring - Construction | R2 / J0 - Zone R2 (Mackup / Benchmark) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-19 | 2024-01-03 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| S. K. CR. - R2 / J0 - Zone R2 (Mackup / Benchmark) - Level 00 - The Ring - Construction | R2 / J0 - Zone R2 (Mackup / Benchmark) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-19 | 2024-01-03 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| S. DQ. R. - R2 / J0 - Zone R2 (Mackup / Benchmark) - Level 00 - The Ring - Construction | R2 / J0 - Zone R2 (Mackup / Benchmark) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-19 | 2024-01-03 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| Zone R1 - Level 00 - The Ring - Construction | Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-04-16 |  | New Orders |  | Low |  | 78 | [7 empty] | TRUE
| R1 / M0 - Zone R1 - Level 00 - The Ring - Construction | Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-02-29 |  | New Orders |  | Low |  | 31 | [7 empty] | TRUE
| S. K. L. - 1 - R1 / M0 - Zone R1 - Level 00 - The Ring - Construction | R1 / M0 - Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-02-04 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - 2 - R1 / M0 - Zone R1 - Level 00 - The Ring - Construction | R1 / M0 - Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-03 | 2024-02-07 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. L. - 3 - R1 / M0 - Zone R1 - Level 00 - The Ring - Construction | R1 / M0 - Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-06 | 2024-02-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - 1 - R1 / M0 - Zone R1 - Level 00 - The Ring - Construction | R1 / M0 - Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-10 | 2024-02-14 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. R. - 2 - R1 / M0 - Zone R1 - Level 00 - The Ring - Construction | R1 / M0 - Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-13 | 2024-02-18 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CL. - R1 / M0 - Zone R1 - Level 00 - The Ring - Construction | R1 / M0 - Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-17 | 2024-02-21 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. CR. - R1 / M0 - Zone R1 - Level 00 - The Ring - Construction | R1 / M0 - Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-20 | 2024-02-26 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| S. DQ. R. - R1 / M0 - Zone R1 - Level 00 - The Ring - Construction | R1 / M0 - Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-25 | 2024-02-29 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| R1 / N0 - Zone R1 - Level 00 - The Ring - Construction | Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-02 | 2024-03-31 |  | New Orders |  | Low |  | 30 | [7 empty] | TRUE
| S. K. L. - 1 - R1 / N0 - Zone R1 - Level 00 - The Ring - Construction | R1 / N0 - Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-02 | 2024-03-06 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. L. - 2 - R1 / N0 - Zone R1 - Level 00 - The Ring - Construction | R1 / N0 - Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-05 | 2024-03-10 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - 3 - R1 / N0 - Zone R1 - Level 00 - The Ring - Construction | R1 / N0 - Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-09 | 2024-03-13 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. R. - 1 - R1 / N0 - Zone R1 - Level 00 - The Ring - Construction | R1 / N0 - Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-12 | 2024-03-17 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - 2 - R1 / N0 - Zone R1 - Level 00 - The Ring - Construction | R1 / N0 - Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-16 | 2024-03-20 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. CL. - R1 / N0 - Zone R1 - Level 00 - The Ring - Construction | R1 / N0 - Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-19 | 2024-03-24 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CR. - R1 / N0 - Zone R1 - Level 00 - The Ring - Construction | R1 / N0 - Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-23 | 2024-03-27 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. R. - R1 / N0 - Zone R1 - Level 00 - The Ring - Construction | R1 / N0 - Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-26 | 2024-03-31 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| R1 / O0 - Zone R1 - Level 00 - The Ring - Construction | Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-01 | 2024-04-16 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| S. K. L. - R1 / O0 - Zone R1 - Level 00 - The Ring - Construction | R1 / O0 - Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-01 | 2024-04-06 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - 1 - R1 / O0 - Zone R1 - Level 00 - The Ring - Construction | R1 / O0 - Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-01 | 2024-04-06 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - 2 - R1 / O0 - Zone R1 - Level 00 - The Ring - Construction | R1 / O0 - Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-04 | 2024-04-09 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CL. - R1 / O0 - Zone R1 - Level 00 - The Ring - Construction | R1 / O0 - Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-08 | 2024-04-16 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| S. K. CR. - R1 / O0 - Zone R1 - Level 00 - The Ring - Construction | R1 / O0 - Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-08 | 2024-04-16 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| S. DQ. L. - R1 / O0 - Zone R1 - Level 00 - The Ring - Construction | R1 / O0 - Zone R1 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-08 | 2024-04-16 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| Zone R2 - Level 00 - The Ring - Construction | Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-03-19 |  | New Orders |  | Low |  | 50 | [7 empty] | TRUE
| R2 / I0 - Zone R2 - Level 00 - The Ring - Construction | Zone R2 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-02-24 |  | New Orders |  | Low |  | 26 | [7 empty] | TRUE
| S. K. L. - R2 / I0 - Zone R2 - Level 00 - The Ring - Construction | R2 / I0 - Zone R2 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-02-04 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - R2 / I0 - Zone R2 - Level 00 - The Ring - Construction | R2 / I0 - Zone R2 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-03 | 2024-02-07 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. CR. - R2 / I0 - Zone R2 - Level 00 - The Ring - Construction | R2 / I0 - Zone R2 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-06 | 2024-02-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - 1 - R2 / I0 - Zone R2 - Level 00 - The Ring - Construction | R2 / I0 - Zone R2 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-10 | 2024-02-14 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. L. - 2 - R2 / I0 - Zone R2 - Level 00 - The Ring - Construction | R2 / I0 - Zone R2 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-13 | 2024-02-18 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| 2BS - R2 / I0 - Zone R2 - Level 00 - The Ring - Construction | R2 / I0 - Zone R2 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-17 | 2024-02-24 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| R2 / L0 - Zone R2 - Level 00 - The Ring - Construction | Zone R2 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-25 | 2024-03-19 |  | New Orders |  | Low |  | 24 | [7 empty] | TRUE
| S. K. L. - 1 - R2 / L0 - Zone R2 - Level 00 - The Ring - Construction | R2 / L0 - Zone R2 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-25 | 2024-02-29 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. L. - 2 - R2 / L0 - Zone R2 - Level 00 - The Ring - Construction | R2 / L0 - Zone R2 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-28 | 2024-03-04 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - R2 / L0 - Zone R2 - Level 00 - The Ring - Construction | R2 / L0 - Zone R2 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-03 | 2024-03-07 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. CR. - R2 / L0 - Zone R2 - Level 00 - The Ring - Construction | R2 / L0 - Zone R2 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-06 | 2024-03-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - R2 / L0 - Zone R2 - Level 00 - The Ring - Construction | R2 / L0 - Zone R2 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-10 | 2024-03-14 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| 2BS - R2 / L0 - Zone R2 - Level 00 - The Ring - Construction | R2 / L0 - Zone R2 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-13 | 2024-03-19 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-10 | 2025-01-18 |  | New Orders |  | Low |  | 40 | [7 empty] | TRUE
| R2 / H0 - Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-10 | 2025-01-01 |  | New Orders |  | Low |  | 23 | [7 empty] | TRUE
| S. K. L. - R2 / H0 - Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | R2 / H0 - Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-10 | 2024-12-17 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| S. K. R. - R2 / H0 - Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | R2 / H0 - Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-14 | 2024-12-18 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. CL. - R2 / H0 - Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | R2 / H0 - Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-17 | 2024-12-22 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CR. - R2 / H0 - Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | R2 / H0 - Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-21 | 2024-12-25 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. L. - R2 / H0 - Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | R2 / H0 - Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-24 | 2024-12-29 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. R. - R2 / H0 - Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | R2 / H0 - Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-28 | 2025-01-01 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| R2 / K0 - Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-02 | 2025-01-18 |  | New Orders |  | Low |  | 17 | [7 empty] | TRUE
| S. K. CL. - R2 / K0 - Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | R2 / K0 - Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-02 | 2025-01-07 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CR. - R2 / K0 - Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | R2 / K0 - Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-06 | 2025-01-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - R2 / K0 - Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | R2 / K0 - Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-09 | 2025-01-14 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. R. - R2 / K0 - Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | R2 / K0 - Zone R2 (Leave out Area) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-13 | 2025-01-18 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| Zone R3 - Level 00 - The Ring - Construction | Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-04-14 |  | New Orders |  | Low |  | 76 | [7 empty] | TRUE
| R3 / E0 - Zone R3 - Level 00 - The Ring - Construction | Zone R3 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-02-29 |  | New Orders |  | Low |  | 31 | [7 empty] | TRUE
| S. K. L. - 1 - R3 / E0 - Zone R3 - Level 00 - The Ring - Construction | R3 / E0 - Zone R3 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-02-04 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - 2 - R3 / E0 - Zone R3 - Level 00 - The Ring - Construction | R3 / E0 - Zone R3 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-03 | 2024-02-07 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. L. - 3 - R3 / E0 - Zone R3 - Level 00 - The Ring - Construction | R3 / E0 - Zone R3 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-06 | 2024-02-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - 1 - R3 / E0 - Zone R3 - Level 00 - The Ring - Construction | R3 / E0 - Zone R3 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-10 | 2024-02-14 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. R. - 2 - R3 / E0 - Zone R3 - Level 00 - The Ring - Construction | R3 / E0 - Zone R3 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-13 | 2024-02-18 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CL. - R3 / E0 - Zone R3 - Level 00 - The Ring - Construction | R3 / E0 - Zone R3 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-17 | 2024-02-21 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. CR. - R3 / E0 - Zone R3 - Level 00 - The Ring - Construction | R3 / E0 - Zone R3 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-20 | 2024-02-26 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| S. DQ. R. - R3 / E0 - Zone R3 - Level 00 - The Ring - Construction | R3 / E0 - Zone R3 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-25 | 2024-02-29 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| R3 / F0 - Zone R3 - Level 00 - The Ring - Construction | Zone R3 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-02 | 2024-03-23 |  | New Orders |  | Low |  | 22 | [7 empty] | TRUE
| S. K. R. - R3 / F0 - Zone R3 - Level 00 - The Ring - Construction | R3 / F0 - Zone R3 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-02 | 2024-03-06 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. L. - R3 / F0 - Zone R3 - Level 00 - The Ring - Construction | R3 / F0 - Zone R3 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-05 | 2024-03-10 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. R. - R3 / F0 - Zone R3 - Level 00 - The Ring - Construction | R3 / F0 - Zone R3 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-09 | 2024-03-13 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| JS. L. - R3 / F0 - Zone R3 - Level 00 - The Ring - Construction | R3 / F0 - Zone R3 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-12 | 2024-03-18 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| JS. R. - R3 / F0 - Zone R3 - Level 00 - The Ring - Construction | R3 / F0 - Zone R3 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-17 | 2024-03-23 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| R3 / Speciality Restaurant - Zone R3 - Level 00 - The Ring - Construction | Zone R3 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-24 | 2024-04-14 |  | New Orders |  | Low |  | 22 | [7 empty] | TRUE
| Zone R3 (Leave out Area) - Level 00 - The Ring - Construction | Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-10 | 2025-01-07 |  | New Orders |  | Low |  | 29 | [7 empty] | TRUE
| R3 / D0 - Zone R3 (Leave out Area) - Level 00 - The Ring - Construction | Zone R3 (Leave out Area) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-10 | 2025-01-07 |  | New Orders |  | Low |  | 29 | [7 empty] | TRUE
| S. K. L. - 1 - R3 / D0 - Zone R3 (Leave out Area) - Level 00 - The Ring - Construction | R3 / D0 - Zone R3 (Leave out Area) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-10 | 2024-12-15 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - 2 - R3 / D0 - Zone R3 (Leave out Area) - Level 00 - The Ring - Construction | R3 / D0 - Zone R3 (Leave out Area) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-14 | 2024-12-18 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. R. - R3 / D0 - Zone R3 (Leave out Area) - Level 00 - The Ring - Construction | R3 / D0 - Zone R3 (Leave out Area) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-17 | 2024-12-22 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - R3 / D0 - Zone R3 (Leave out Area) - Level 00 - The Ring - Construction | R3 / D0 - Zone R3 (Leave out Area) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-21 | 2024-12-25 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. R. - R3 / D0 - Zone R3 (Leave out Area) - Level 00 - The Ring - Construction | R3 / D0 - Zone R3 (Leave out Area) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-24 | 2024-12-29 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| JS. L. - R3 / D0 - Zone R3 (Leave out Area) - Level 00 - The Ring - Construction | R3 / D0 - Zone R3 (Leave out Area) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-28 | 2025-01-02 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| JS. R. - R3 / D0 - Zone R3 (Leave out Area) - Level 00 - The Ring - Construction | R3 / D0 - Zone R3 (Leave out Area) - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-01 | 2025-01-07 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| Zone R4 - Level 00 - The Ring - Construction | Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-04-14 |  | New Orders |  | Low |  | 76 | [7 empty] | TRUE
| R4 / A0 - Zone R4 - Level 00 - The Ring - Construction | Zone R4 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-02-14 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| S. K. CL. - R4 / A0 - Zone R4 - Level 00 - The Ring - Construction | R4 / A0 - Zone R4 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-02-04 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CR. - R4 / A0 - Zone R4 - Level 00 - The Ring - Construction | R4 / A0 - Zone R4 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-03 | 2024-02-07 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. L. - R4 / A0 - Zone R4 - Level 00 - The Ring - Construction | R4 / A0 - Zone R4 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-06 | 2024-02-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. R. - R4 / A0 - Zone R4 - Level 00 - The Ring - Construction | R4 / A0 - Zone R4 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-10 | 2024-02-14 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| R4 / B0 - Zone R4 - Level 00 - The Ring - Construction | Zone R4 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-15 | 2024-03-17 |  | New Orders |  | Low |  | 32 | [7 empty] | TRUE
| S. K. L. - 1 - R4 / B0 - Zone R4 - Level 00 - The Ring - Construction | R4 / B0 - Zone R4 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-15 | 2024-02-20 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - 2 - R4 / B0 - Zone R4 - Level 00 - The Ring - Construction | R4 / B0 - Zone R4 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-19 | 2024-02-25 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| S. K. L. - 3 - R4 / B0 - Zone R4 - Level 00 - The Ring - Construction | R4 / B0 - Zone R4 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-24 | 2024-02-28 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. R. - 1 - R4 / B0 - Zone R4 - Level 00 - The Ring - Construction | R4 / B0 - Zone R4 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-27 | 2024-03-03 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - 2 - R4 / B0 - Zone R4 - Level 00 - The Ring - Construction | R4 / B0 - Zone R4 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-02 | 2024-03-06 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. CL. - R4 / B0 - Zone R4 - Level 00 - The Ring - Construction | R4 / B0 - Zone R4 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-05 | 2024-03-10 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CR. - R4 / B0 - Zone R4 - Level 00 - The Ring - Construction | R4 / B0 - Zone R4 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-09 | 2024-03-13 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. R. - R4 / B0 - Zone R4 - Level 00 - The Ring - Construction | R4 / B0 - Zone R4 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-12 | 2024-03-17 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| R4 / C0 - Zone R4 - Level 00 - The Ring - Construction | Zone R4 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-18 | 2024-04-14 |  | New Orders |  | Low |  | 28 | [7 empty] | TRUE
| S. K. L. - R4 / C0 - Zone R4 - Level 00 - The Ring - Construction | R4 / C0 - Zone R4 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-18 | 2024-03-23 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - R4 / C0 - Zone R4 - Level 00 - The Ring - Construction | R4 / C0 - Zone R4 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-21 | 2024-03-26 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CR. - R4 / C0 - Zone R4 - Level 00 - The Ring - Construction | R4 / C0 - Zone R4 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-25 | 2024-03-30 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - 1 - R4 / C0 - Zone R4 - Level 00 - The Ring - Construction | R4 / C0 - Zone R4 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-28 | 2024-04-02 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - 2 - R4 / C0 - Zone R4 - Level 00 - The Ring - Construction | R4 / C0 - Zone R4 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-01 | 2024-04-06 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| 2BS - R4 / C0 - Zone R4 - Level 00 - The Ring - Construction | R4 / C0 - Zone R4 - Level 00 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-04 | 2024-04-14 |  | New Orders |  | Low |  | 11 | [7 empty] | TRUE
| Level 01 - The Ring - Construction | The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-19 | 2025-02-19 |  | New Orders |  | Low |  | 429 | [7 empty] | TRUE
| Zone R2 (Mackup / Benchmark) - Level 01 - The Ring - Construction | Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-19 | 2024-01-03 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| R2 / J1 - Zone R2 (Mackup / Benchmark) - Level 01 - The Ring - Construction | Zone R2 (Mackup / Benchmark) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-19 | 2024-01-03 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| S. K. L. - 1 - R2 / J1 - Zone R2 (Mackup / Benchmark) - Level 01 - The Ring - Construction | R2 / J1 - Zone R2 (Mackup / Benchmark) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-19 | 2024-01-03 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| S. K. L. - 2 - R2 / J1 - Zone R2 (Mackup / Benchmark) - Level 01 - The Ring - Construction | R2 / J1 - Zone R2 (Mackup / Benchmark) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-19 | 2024-01-03 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| S. K. L. - 3 - R2 / J1 - Zone R2 (Mackup / Benchmark) - Level 01 - The Ring - Construction | R2 / J1 - Zone R2 (Mackup / Benchmark) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-19 | 2024-01-03 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| S. K. R. - 1 - R2 / J1 - Zone R2 (Mackup / Benchmark) - Level 01 - The Ring - Construction | R2 / J1 - Zone R2 (Mackup / Benchmark) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-19 | 2024-01-03 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| S. K. R. - 2 - R2 / J1 - Zone R2 (Mackup / Benchmark) - Level 01 - The Ring - Construction | R2 / J1 - Zone R2 (Mackup / Benchmark) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-19 | 2024-01-03 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| S. K. CL. - R2 / J1 - Zone R2 (Mackup / Benchmark) - Level 01 - The Ring - Construction | R2 / J1 - Zone R2 (Mackup / Benchmark) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-19 | 2024-01-03 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| S. K. CR. - R2 / J1 - Zone R2 (Mackup / Benchmark) - Level 01 - The Ring - Construction | R2 / J1 - Zone R2 (Mackup / Benchmark) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-19 | 2024-01-03 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| S. DQ. R. - R2 / J1 - Zone R2 (Mackup / Benchmark) - Level 01 - The Ring - Construction | R2 / J1 - Zone R2 (Mackup / Benchmark) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2023-12-19 | 2024-01-03 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| Zone R1 - Level 01 - The Ring - Construction | Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-12 | 2024-05-01 |  | New Orders |  | Low |  | 80 | [7 empty] | TRUE
| R1 / M1 - Zone R1 - Level 01 - The Ring - Construction | Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-12 | 2024-03-20 |  | New Orders |  | Low |  | 38 | [7 empty] | TRUE
| S. K. L. - 1 - R1 / M1 - Zone R1 - Level 01 - The Ring - Construction | R1 / M1 - Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-12 | 2024-02-21 |  | New Orders |  | Low |  | 10 | [7 empty] | TRUE
| S. K. L. - 2 - R1 / M1 - Zone R1 - Level 01 - The Ring - Construction | R1 / M1 - Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-15 | 2024-02-21 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| S. K. L. - 3 - R1 / M1 - Zone R1 - Level 01 - The Ring - Construction | R1 / M1 - Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-19 | 2024-02-25 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| S. K. R. - 1 - R1 / M1 - Zone R1 - Level 01 - The Ring - Construction | R1 / M1 - Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-26 | 2024-03-02 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - 2 - R1 / M1 - Zone R1 - Level 01 - The Ring - Construction | R1 / M1 - Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-29 | 2024-03-05 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CL. - R1 / M1 - Zone R1 - Level 01 - The Ring - Construction | R1 / M1 - Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-06 | 2024-03-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CR. - R1 / M1 - Zone R1 - Level 01 - The Ring - Construction | R1 / M1 - Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-10 | 2024-03-14 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. R. - R1 / M1 - Zone R1 - Level 01 - The Ring - Construction | R1 / M1 - Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-16 | 2024-03-20 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| R1 / N1 - Zone R1 - Level 01 - The Ring - Construction | Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-21 | 2024-04-20 |  | New Orders |  | Low |  | 31 | [7 empty] | TRUE
| S. K. L. - 1 - R1 / N1 - Zone R1 - Level 01 - The Ring - Construction | R1 / N1 - Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-21 | 2024-03-26 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - 2 - R1 / N1 - Zone R1 - Level 01 - The Ring - Construction | R1 / N1 - Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-21 | 2024-03-26 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - 3 - R1 / N1 - Zone R1 - Level 01 - The Ring - Construction | R1 / N1 - Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-25 | 2024-03-30 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - 1 - R1 / N1 - Zone R1 - Level 01 - The Ring - Construction | R1 / N1 - Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-31 | 2024-04-04 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. R. - 2 - R1 / N1 - Zone R1 - Level 01 - The Ring - Construction | R1 / N1 - Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-31 | 2024-04-04 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. CL. - R1 / N1 - Zone R1 - Level 01 - The Ring - Construction | R1 / N1 - Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-06 | 2024-04-14 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| S. K. CR. - R1 / N1 - Zone R1 - Level 01 - The Ring - Construction | R1 / N1 - Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-06 | 2024-04-14 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| S. DQ. R. - R1 / N1 - Zone R1 - Level 01 - The Ring - Construction | R1 / N1 - Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-15 | 2024-04-20 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| R1 / O1 - Zone R1 - Level 01 - The Ring - Construction | Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-21 | 2024-05-01 |  | New Orders |  | Low |  | 11 | [7 empty] | TRUE
| S. K. L. - R1 / O1 - Zone R1 - Level 01 - The Ring - Construction | R1 / O1 - Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-21 | 2024-04-25 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. R. - 1 - R1 / O1 - Zone R1 - Level 01 - The Ring - Construction | R1 / O1 - Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-21 | 2024-04-25 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. R. - 2 - R1 / O1 - Zone R1 - Level 01 - The Ring - Construction | R1 / O1 - Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-24 | 2024-04-29 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CL. - R1 / O1 - Zone R1 - Level 01 - The Ring - Construction | R1 / O1 - Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-24 | 2024-05-01 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| S. K. CR. - R1 / O1 - Zone R1 - Level 01 - The Ring - Construction | R1 / O1 - Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-24 | 2024-05-01 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| S. DQ. L. - R1 / O1 - Zone R1 - Level 01 - The Ring - Construction | R1 / O1 - Zone R1 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-24 | 2024-05-01 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| Zone R2 - Level 01 - The Ring - Construction | Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-03-16 |  | New Orders |  | Low |  | 47 | [7 empty] | TRUE
| R2 / I1 - Zone R2 - Level 01 - The Ring - Construction | Zone R2 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-02-21 |  | New Orders |  | Low |  | 23 | [7 empty] | TRUE
| S. K. L. - R2 / I1 - Zone R2 - Level 01 - The Ring - Construction | R2 / I1 - Zone R2 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-30 | 2024-02-04 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - R2 / I1 - Zone R2 - Level 01 - The Ring - Construction | R2 / I1 - Zone R2 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-03 | 2024-02-07 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. CR. - R2 / I1 - Zone R2 - Level 01 - The Ring - Construction | R2 / I1 - Zone R2 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-06 | 2024-02-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - 1 - R2 / I1 - Zone R2 - Level 01 - The Ring - Construction | R2 / I1 - Zone R2 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-06 | 2024-02-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - 2 - R2 / I1 - Zone R2 - Level 01 - The Ring - Construction | R2 / I1 - Zone R2 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-10 | 2024-02-14 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| 2BS - R2 / I1 - Zone R2 - Level 01 - The Ring - Construction | R2 / I1 - Zone R2 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-15 | 2024-02-21 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| R2 / L1 - Zone R2 - Level 01 - The Ring - Construction | Zone R2 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-24 | 2024-03-16 |  | New Orders |  | Low |  | 22 | [7 empty] | TRUE
| S. K. L. - 1 - R2 / L1 - Zone R2 - Level 01 - The Ring - Construction | R2 / L1 - Zone R2 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-24 | 2024-02-28 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. L. - 2 - R2 / L1 - Zone R2 - Level 01 - The Ring - Construction | R2 / L1 - Zone R2 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-24 | 2024-02-28 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. R. - R2 / L1 - Zone R2 - Level 01 - The Ring - Construction | R2 / L1 - Zone R2 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-27 | 2024-03-03 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CR. - R2 / L1 - Zone R2 - Level 01 - The Ring - Construction | R2 / L1 - Zone R2 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-04 | 2024-03-09 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - R2 / L1 - Zone R2 - Level 01 - The Ring - Construction | R2 / L1 - Zone R2 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-04 | 2024-03-09 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| 2BS - R2 / L1 - Zone R2 - Level 01 - The Ring - Construction | R2 / L1 - Zone R2 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-10 | 2024-03-16 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-24 | 2025-02-19 |  | New Orders |  | Low |  | 58 | [7 empty] | TRUE
| R2 / H1 - Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-24 | 2025-01-27 |  | New Orders |  | Low |  | 35 | [7 empty] | TRUE
| S. K. L. - R2 / H1 - Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | R2 / H1 - Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-24 | 2024-12-29 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - R2 / H1 - Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | R2 / H1 - Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-30 | 2025-01-04 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CL. - R2 / H1 - Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | R2 / H1 - Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-05 | 2025-01-09 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. CR. - R2 / H1 - Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | R2 / H1 - Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-11 | 2025-01-15 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. L. - R2 / H1 - Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | R2 / H1 - Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-16 | 2025-01-21 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. R. - R2 / H1 - Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | R2 / H1 - Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-22 | 2025-01-27 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| R2 / K1 - Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-28 | 2025-02-19 |  | New Orders |  | Low |  | 23 | [7 empty] | TRUE
| S. K. CL. - R2 / K1 - Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | R2 / K1 - Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-28 | 2025-02-02 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CR. - R2 / K1 - Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | R2 / K1 - Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-03 | 2025-02-08 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - R2 / K1 - Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | R2 / K1 - Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-09 | 2025-02-13 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. R. - R2 / K1 - Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | R2 / K1 - Zone R2 (Leave out Area) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-15 | 2025-02-19 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| Zone R3 - Level 01 - The Ring - Construction | Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-12 | 2024-05-02 |  | New Orders |  | Low |  | 81 | [7 empty] | TRUE
| R3 / E1 - Zone R3 - Level 01 - The Ring - Construction | Zone R3 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-12 | 2024-03-10 |  | New Orders |  | Low |  | 28 | [7 empty] | TRUE
| S. K. L. - 1 - R3 / E1 - Zone R3 - Level 01 - The Ring - Construction | R3 / E1 - Zone R3 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-12 | 2024-02-20 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| S. K. L. - 2 - R3 / E1 - Zone R3 - Level 01 - The Ring - Construction | R3 / E1 - Zone R3 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-12 | 2024-02-20 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| S. K. L. - 3 - R3 / E1 - Zone R3 - Level 01 - The Ring - Construction | R3 / E1 - Zone R3 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-12 | 2024-02-20 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| S. K. R. - 1 - R3 / E1 - Zone R3 - Level 01 - The Ring - Construction | R3 / E1 - Zone R3 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-21 | 2024-02-27 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| S. K. R. - 2 - R3 / E1 - Zone R3 - Level 01 - The Ring - Construction | R3 / E1 - Zone R3 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-21 | 2024-02-27 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| S. K. CL. - R3 / E1 - Zone R3 - Level 01 - The Ring - Construction | R3 / E1 - Zone R3 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-28 | 2024-03-04 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CR. - R3 / E1 - Zone R3 - Level 01 - The Ring - Construction | R3 / E1 - Zone R3 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-28 | 2024-03-04 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. R. - R3 / E1 - Zone R3 - Level 01 - The Ring - Construction | R3 / E1 - Zone R3 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-05 | 2024-03-10 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| R3 / F1 - Zone R3 - Level 01 - The Ring - Construction | Zone R3 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-11 | 2024-04-14 |  | New Orders |  | Low |  | 35 | [7 empty] | TRUE
| S. K. R. - R3 / F1 - Zone R3 - Level 01 - The Ring - Construction | R3 / F1 - Zone R3 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-11 | 2024-03-16 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - R3 / F1 - Zone R3 - Level 01 - The Ring - Construction | R3 / F1 - Zone R3 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-17 | 2024-03-21 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. R. - R3 / F1 - Zone R3 - Level 01 - The Ring - Construction | R3 / F1 - Zone R3 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-23 | 2024-03-27 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| JS. L. - R3 / F1 - Zone R3 - Level 01 - The Ring - Construction | R3 / F1 - Zone R3 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-28 | 2024-04-03 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| JS. R. - R3 / F1 - Zone R3 - Level 01 - The Ring - Construction | R3 / F1 - Zone R3 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-04 | 2024-04-14 |  | New Orders |  | Low |  | 11 | [7 empty] | TRUE
| R3 / G1 - Zone R3 - Level 01 - The Ring - Construction | Zone R3 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-15 | 2024-05-02 |  | New Orders |  | Low |  | 18 | [7 empty] | TRUE
| S. K. L. - R3 / G1 - Zone R3 - Level 01 - The Ring - Construction | R3 / G1 - Zone R3 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-15 | 2024-04-20 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. R. - R3 / G1 - Zone R3 - Level 01 - The Ring - Construction | R3 / G1 - Zone R3 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-21 | 2024-04-25 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| 1BS. CL. 1 - R3 / G1 - Zone R3 - Level 01 - The Ring - Construction | R3 / G1 - Zone R3 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-27 | 2024-05-02 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| 1BS. CR. 1 - R3 / G1 - Zone R3 - Level 01 - The Ring - Construction | R3 / G1 - Zone R3 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-27 | 2024-05-02 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| Zone R3 (Leave out Area) - Level 01 - The Ring - Construction | Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-24 | 2025-01-29 |  | New Orders |  | Low |  | 37 | [7 empty] | TRUE
| R3 / D1 - Zone R3 (Leave out Area) - Level 01 - The Ring - Construction | Zone R3 (Leave out Area) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-24 | 2025-01-29 |  | New Orders |  | Low |  | 37 | [7 empty] | TRUE
| S. K. L. - 1 - R3 / D1 - Zone R3 (Leave out Area) - Level 01 - The Ring - Construction | R3 / D1 - Zone R3 (Leave out Area) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-24 | 2024-12-29 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - 2 - R3 / D1 - Zone R3 (Leave out Area) - Level 01 - The Ring - Construction | R3 / D1 - Zone R3 (Leave out Area) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-24 | 2024-12-29 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - R3 / D1 - Zone R3 (Leave out Area) - Level 01 - The Ring - Construction | R3 / D1 - Zone R3 (Leave out Area) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-30 | 2025-01-04 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - R3 / D1 - Zone R3 (Leave out Area) - Level 01 - The Ring - Construction | R3 / D1 - Zone R3 (Leave out Area) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-05 | 2025-01-09 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. DQ. R. - R3 / D1 - Zone R3 (Leave out Area) - Level 01 - The Ring - Construction | R3 / D1 - Zone R3 (Leave out Area) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-11 | 2025-01-15 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| JS. L. - R3 / D1 - Zone R3 (Leave out Area) - Level 01 - The Ring - Construction | R3 / D1 - Zone R3 (Leave out Area) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-16 | 2025-01-22 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| JS. R. - R3 / D1 - Zone R3 (Leave out Area) - Level 01 - The Ring - Construction | R3 / D1 - Zone R3 (Leave out Area) - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-23 | 2025-01-29 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| Zone R4 - Level 01 - The Ring - Construction | Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-12 | 2024-05-04 |  | New Orders |  | Low |  | 83 | [7 empty] | TRUE
| R4 / A1 - Zone R4 - Level 01 - The Ring - Construction | Zone R4 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-12 | 2024-02-27 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| S. K. CL. - R4 / A1 - Zone R4 - Level 01 - The Ring - Construction | R4 / A1 - Zone R4 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-12 | 2024-02-20 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| S. K. CR. - R4 / A1 - Zone R4 - Level 01 - The Ring - Construction | R4 / A1 - Zone R4 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-12 | 2024-02-20 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| S. DQ. L. - R4 / A1 - Zone R4 - Level 01 - The Ring - Construction | R4 / A1 - Zone R4 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-21 | 2024-02-27 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| S. DQ. R. - R4 / A1 - Zone R4 - Level 01 - The Ring - Construction | R4 / A1 - Zone R4 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-21 | 2024-02-27 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| R4 / B1 - Zone R4 - Level 01 - The Ring - Construction | Zone R4 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-28 | 2024-03-31 |  | New Orders |  | Low |  | 33 | [7 empty] | TRUE
| S. K. L. - 1 - R4 / B1 - Zone R4 - Level 01 - The Ring - Construction | R4 / B1 - Zone R4 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-28 | 2024-03-04 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - 2 - R4 / B1 - Zone R4 - Level 01 - The Ring - Construction | R4 / B1 - Zone R4 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-28 | 2024-03-04 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - 3 - R4 / B1 - Zone R4 - Level 01 - The Ring - Construction | R4 / B1 - Zone R4 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-03 | 2024-03-07 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. R. - 1 - R4 / B1 - Zone R4 - Level 01 - The Ring - Construction | R4 / B1 - Zone R4 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-09 | 2024-03-13 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. R. - 2 - R4 / B1 - Zone R4 - Level 01 - The Ring - Construction | R4 / B1 - Zone R4 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-09 | 2024-03-13 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. CL. - R4 / B1 - Zone R4 - Level 01 - The Ring - Construction | R4 / B1 - Zone R4 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-14 | 2024-03-19 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. CR. - R4 / B1 - Zone R4 - Level 01 - The Ring - Construction | R4 / B1 - Zone R4 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-20 | 2024-03-25 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. R. - R4 / B1 - Zone R4 - Level 01 - The Ring - Construction | R4 / B1 - Zone R4 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-26 | 2024-03-31 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| R4 / C1 - Zone R4 - Level 01 - The Ring - Construction | Zone R4 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-01 | 2024-05-04 |  | New Orders |  | Low |  | 34 | [7 empty] | TRUE
| S. K. L. - R4 / C1 - Zone R4 - Level 01 - The Ring - Construction | R4 / C1 - Zone R4 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-01 | 2024-04-06 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - R4 / C1 - Zone R4 - Level 01 - The Ring - Construction | R4 / C1 - Zone R4 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-07 | 2024-04-15 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| S. K. CR. - R4 / C1 - Zone R4 - Level 01 - The Ring - Construction | R4 / C1 - Zone R4 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-16 | 2024-04-21 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - 1 - R4 / C1 - Zone R4 - Level 01 - The Ring - Construction | R4 / C1 - Zone R4 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-22 | 2024-04-27 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - 2 - R4 / C1 - Zone R4 - Level 01 - The Ring - Construction | R4 / C1 - Zone R4 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-28 | 2024-05-02 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| 2BS - R4 / C1 - Zone R4 - Level 01 - The Ring - Construction | R4 / C1 - Zone R4 - Level 01 - The Ring - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-28 | 2024-05-04 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| The Beach - Construction | Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-29 | 2024-07-08 |  | New Orders |  | Low |  | 71 | [7 empty] | TRUE
| Level 00 - The Beach - Construction | The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-29 | 2024-07-08 |  | New Orders |  | Low |  | 71 | [7 empty] | TRUE
| Zone B1 - Level 00 - The Beach - Construction | Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-29 | 2024-05-12 |  | New Orders |  | Low |  | 14 | [7 empty] | TRUE
| B1 / GB - Zone B1 - Level 00 - The Beach - Construction | Zone B1 - Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-29 | 2024-05-12 |  | New Orders |  | Low |  | 14 | [7 empty] | TRUE
| 1BS. BL - B1 / GB - Zone B1 - Level 00 - The Beach - Construction | B1 / GB - Zone B1 - Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-29 | 2024-05-06 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| 1BS. BR - B1 / GB - Zone B1 - Level 00 - The Beach - Construction | B1 / GB - Zone B1 - Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-05 | 2024-05-12 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| Zone B2 - Level 00 - The Beach - Construction | Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-29 | 2024-06-03 |  | New Orders |  | Low |  | 36 | [7 empty] | TRUE
| B1 / CB - Zone B2 - Level 00 - The Beach - Construction | Zone B2 - Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-29 | 2024-05-06 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| 2BS. B - B1 / CB - Zone B2 - Level 00 - The Beach - Construction | B1 / CB - Zone B2 - Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-29 | 2024-05-06 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| B1 / DB - Zone B2 - Level 00 - The Beach - Construction | Zone B2 - Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-05 | 2024-05-12 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| 3BS. B - B1 / DB - Zone B2 - Level 00 - The Beach - Construction | B1 / DB - Zone B2 - Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-05 | 2024-05-12 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| B1 / EB - Zone B2 - Level 00 - The Beach - Construction | Zone B2 - Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-13 | 2024-05-20 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| 3BS. B - B1 / EB - Zone B2 - Level 00 - The Beach - Construction | B1 / EB - Zone B2 - Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-13 | 2024-05-20 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| B1 / FB - Zone B2 - Level 00 - The Beach - Construction | Zone B2 - Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-21 | 2024-06-03 |  | New Orders |  | Low |  | 14 | [7 empty] | TRUE
| J. S. BL. - B1 / FB - Zone B2 - Level 00 - The Beach - Construction | B1 / FB - Zone B2 - Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-21 | 2024-05-28 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| J. S. BR. - B1 / FB - Zone B2 - Level 00 - The Beach - Construction | B1 / FB - Zone B2 - Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-27 | 2024-06-03 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| Zone B3 - Level 00 - The Beach - Construction | Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-06-04 | 2024-07-07 |  | New Orders |  | Low |  | 34 | [7 empty] | TRUE
| B3 / AB - Zone B3 - Level 00 - The Beach - Construction | Zone B3 - Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-06-04 | 2024-06-22 |  | New Orders |  | Low |  | 19 | [7 empty] | TRUE
| J. S. BL. - B3 / AB - Zone B3 - Level 00 - The Beach - Construction | B3 / AB - Zone B3 - Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-06-04 | 2024-06-11 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| J. S. BR. - B3 / AB - Zone B3 - Level 00 - The Beach - Construction | B3 / AB - Zone B3 - Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-06-10 | 2024-06-22 |  | New Orders |  | Low |  | 13 | [7 empty] | TRUE
| B3 / BB - Zone B3 - Level 00 - The Beach - Construction | Zone B3 - Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-06-23 | 2024-06-30 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| 2BS. B - B3 / BB - Zone B3 - Level 00 - The Beach - Construction | B3 / BB - Zone B3 - Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-06-23 | 2024-06-30 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| B3 / Beach Bar & Pool Change - Zone B3 - Level 00 - The Beach - Construction | Zone B3 - Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-07-01 | 2024-07-07 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| Zone B4 - Level 00 - The Beach - Construction | Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-06-09 | 2024-07-08 |  | New Orders |  | Low |  | 30 | [7 empty] | TRUE
| B4 / Pool Bar - Zone B4 - Level 00 - The Beach - Construction | Zone B4 - Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-06-09 | 2024-07-04 |  | New Orders |  | Low |  | 26 | [7 empty] | TRUE
| B4 / Teen & Children Recreation - Zone B4 - Level 00 - The Beach - Construction | Zone B4 - Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-06-09 | 2024-07-08 |  | New Orders |  | Low |  | 30 | [7 empty] | TRUE
| Zone B5 - Level 00 - The Beach - Construction | Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-29 | 2024-06-30 |  | New Orders |  | Low |  | 63 | [7 empty] | TRUE
| B5 / Mice - Zone B5 - Level 00 - The Beach - Construction | Zone B5 - Level 00 - The Beach - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-29 | 2024-06-30 |  | New Orders |  | Low |  | 63 | [7 empty] | TRUE
| The Tail - Construction | Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-15 | 2025-03-25 |  | New Orders |  | Low |  | 70 | [7 empty] | TRUE
| Zone T1 Guestrooms (M03) - The Tail - Construction | The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-15 | 2025-03-25 |  | New Orders |  | Low |  | 70 | [7 empty] | TRUE
| Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-15 | 2025-03-17 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-15 | 2025-03-17 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| T1 / P1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-15 | 2025-01-30 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| S. K. L. - T1 / P1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / P1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-15 | 2025-01-20 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - 1 - T1 / P1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / P1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-19 | 2025-01-23 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. R. - 2 - T1 / P1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / P1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-22 | 2025-01-27 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - 3 - T1 / P1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / P1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-26 | 2025-01-30 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. R. - 4 - T1 / P1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / P1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-26 | 2025-01-30 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| JS. L. - T1 / P1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / P1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-26 | 2025-01-30 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| T1 / Q1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-01 | 2025-02-06 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - T1 / Q1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / Q1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-01 | 2025-02-05 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| JS. R. - T1 / Q1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / Q1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-01 | 2025-02-06 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| T1 / R1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-08 | 2025-02-12 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. L. - T1 / R1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / R1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-08 | 2025-02-12 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. R. - 1 - T1 / R1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / R1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-08 | 2025-02-12 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. R. - 2 - T1 / R1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / R1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-08 | 2025-02-12 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| T1 / S1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-13 | 2025-02-19 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| S. K. L. - 1 - T1 / S1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / S1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-13 | 2025-02-18 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - 2 - T1 / S1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / S1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-13 | 2025-02-18 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - T1 / S1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / S1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-13 | 2025-02-18 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| JS. R. - T1 / S1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / S1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-13 | 2025-02-19 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| T1 / T1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-20 | 2025-02-27 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| S. K. R. - 1 - T1 / T1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / T1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-20 | 2025-02-26 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| S. K. L. - 1 - T1 / T1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / T1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-20 | 2025-02-26 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| S. K. L. - 2 - T1 / T1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / T1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-20 | 2025-02-26 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| S. K. R. - 2 - T1 / T1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / T1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-20 | 2025-02-26 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| JS. R. - T1 / T1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / T1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-20 | 2025-02-27 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| T1 / U1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-01 | 2025-03-05 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. L. - 1 - T1 / U1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / U1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-01 | 2025-03-05 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. L. - 2 - T1 / U1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / U1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-01 | 2025-03-05 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. L. - 3 - T1 / U1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / U1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-01 | 2025-03-05 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. L. - 4 - T1 / U1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / U1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-01 | 2025-03-05 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. R. - 1 - T1 / U1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / U1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-01 | 2025-03-05 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. R. - 2 - T1 / U1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / U1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-01 | 2025-03-05 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. R. - 3 - T1 / U1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / U1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-01 | 2025-03-05 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| S. K. R. - 4 - T1 / U1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / U1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-01 | 2025-03-05 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| T1 / V1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-06 | 2025-03-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - 1 - T1 / V1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / V1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-06 | 2025-03-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - 2 - T1 / V1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / V1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-06 | 2025-03-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - 3 - T1 / V1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / V1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-06 | 2025-03-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - T1 / V1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / V1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-06 | 2025-03-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - T1 / V1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / V1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-06 | 2025-03-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| T1 / W1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-12 | 2025-03-17 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - 1 - T1 / W1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / W1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-12 | 2025-03-17 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - 2 - T1 / W1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / W1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-12 | 2025-03-17 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - 3 - T1 / W1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / W1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-12 | 2025-03-17 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - T1 / W1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | T1 / W1 - Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-12 | 2025-03-17 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-29 | 2025-03-25 |  | New Orders |  | Low |  | 56 | [7 empty] | TRUE
| Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-29 | 2025-03-25 |  | New Orders |  | Low |  | 56 | [7 empty] | TRUE
| T2 / P2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-29 | 2025-02-04 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| JS. L. - T2 / P2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | T2 / P2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-29 | 2025-02-04 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| T2 / Q2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-05 | 2025-02-11 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| S. DQ. L. - T2 / Q2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | T2 / Q2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-05 | 2025-02-10 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| JS. R. - T2 / Q2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | T2 / Q2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-05 | 2025-02-11 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| T2 / R2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-12 | 2025-02-18 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| S. DQ. R. - T2 / R2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | T2 / R2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-12 | 2025-02-17 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| 1BS. CL. 1 - T2 / R2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | T2 / R2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-12 | 2025-02-18 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| T2 / S2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-19 | 2025-02-26 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| S. DQ. R. - T2 / S2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | T2 / S2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-19 | 2025-02-25 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| JS. R. - T2 / S2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | T2 / S2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-19 | 2025-02-26 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| 1BS. CL. 1 - T2 / S2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | T2 / S2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-19 | 2025-02-26 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| T2 / T2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-27 | 2025-03-05 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| S. K. L. - T2 / T2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | T2 / T2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-27 | 2025-03-04 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. R. - T2 / T2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | T2 / T2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-27 | 2025-03-04 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| JS. R. - T2 / T2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | T2 / T2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-27 | 2025-03-05 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| 1BS. CL. 1 - T2 / T2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | T2 / T2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-27 | 2025-03-05 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| T2 / U2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-06 | 2025-03-12 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| S. K. L. - T2 / U2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | T2 / U2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-06 | 2025-03-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. R. - T2 / U2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | T2 / U2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-06 | 2025-03-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - T2 / U2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | T2 / U2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-06 | 2025-03-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. R. - T2 / U2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | T2 / U2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-06 | 2025-03-11 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| 1BS. CL. 1 - T2 / U2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | T2 / U2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-06 | 2025-03-12 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| 1BS. CR. 1 - T2 / U2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | T2 / U2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-06 | 2025-03-12 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| T2 / V2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-13 | 2025-03-19 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| S. K. L. - T2 / V2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | T2 / V2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-13 | 2025-03-18 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. L. - T2 / V2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | T2 / V2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-13 | 2025-03-18 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| 2BS - T2 / V2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | T2 / V2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-13 | 2025-03-19 |  | New Orders |  | Low |  | 7 | [7 empty] | TRUE
| T2 / W2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-20 | 2025-03-25 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. K. L. - T2 / W2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | T2 / W2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-20 | 2025-03-25 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| S. DQ. R. - T2 / W2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | T2 / W2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-20 | 2025-03-25 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| 1BS. CL. 1 - T2 / W2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | T2 / W2 - Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Construction | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-20 | 2025-03-25 |  | New Orders |  | Low |  | 6 | [7 empty] | TRUE
| Close-Out / Handing Over - |  | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-04 | 2025-07-26 |  | New Orders |  | Low |  | 570 | [7 empty] | TRUE
| Testing & Commissioning - Close-Out / Handing Over | Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-04 | 2025-04-09 |  | New Orders |  | Low |  | 462 | [7 empty] | TRUE
| The Mound - Testing & Commissioning - Close-Out / Handing Over | Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-12 | 2024-12-16 |  | New Orders |  | Low |  | 309 | [7 empty] | TRUE
| Level 01 - The Mound - Testing & Commissioning - Close-Out / Handing Over | The Mound - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-11-27 | 2024-12-05 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| Zone M3 - Level 01 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Level 01 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-11-27 | 2024-12-05 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| Level 02 - The Mound - Testing & Commissioning - Close-Out / Handing Over | The Mound - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-12 | 2024-04-22 |  | New Orders |  | Low |  | 71 | [7 empty] | TRUE
| Zone M1 - Level 02 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Level 02 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-13 | 2024-03-06 |  | New Orders |  | Low |  | 23 | [7 empty] | TRUE
| Zone M2 - Level 02 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Level 02 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-20 | 2024-04-22 |  | New Orders |  | Low |  | 34 | [7 empty] | TRUE
| Zone M3 - Level 02 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Level 02 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-12 | 2024-03-20 |  | New Orders |  | Low |  | 38 | [7 empty] | TRUE
| Zone M4 - Level 02 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Level 02 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-05 | 2024-04-22 |  | New Orders |  | Low |  | 49 | [7 empty] | TRUE
| Level 03 - The Mound - Testing & Commissioning - Close-Out / Handing Over | The Mound - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-19 | 2024-06-10 |  | New Orders |  | Low |  | 84 | [7 empty] | TRUE
| Zone M1 - Level 03 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Level 03 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-19 | 2024-04-29 |  | New Orders |  | Low |  | 42 | [7 empty] | TRUE
| Zone M2 - Level 03 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Level 03 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-14 | 2024-05-20 |  | New Orders |  | Low |  | 37 | [7 empty] | TRUE
| Zone M3 - Level 03 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Level 03 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-25 | 2024-05-14 |  | New Orders |  | Low |  | 51 | [7 empty] | TRUE
| Zone M4 - Level 03 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Level 03 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-21 | 2024-06-10 |  | New Orders |  | Low |  | 51 | [7 empty] | TRUE
| Level 04 - The Mound - Testing & Commissioning - Close-Out / Handing Over | The Mound - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-28 | 2024-06-12 |  | New Orders |  | Low |  | 46 | [7 empty] | TRUE
| Zone M1 - Level 04 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Level 04 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-02 | 2024-05-12 |  | New Orders |  | Low |  | 11 | [7 empty] | TRUE
| Zone M2 - Level 04 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Level 04 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-02 | 2024-05-29 |  | New Orders |  | Low |  | 28 | [7 empty] | TRUE
| Zone M3 - Level 04 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Level 04 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-12 | 2024-05-20 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| Zone M4 - Level 04 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Level 04 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-28 | 2024-06-12 |  | New Orders |  | Low |  | 46 | [7 empty] | TRUE
| Level 05 & 06 - The Mound - Testing & Commissioning - Close-Out / Handing Over | The Mound - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-11-03 | 2024-12-16 |  | New Orders |  | Low |  | 44 | [7 empty] | TRUE
| Zone M2 - Level 05 & 06 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Level 05 & 06 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-11-03 | 2024-11-11 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| Zone M4 - Level 05 & 06 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Level 05 & 06 - The Mound - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-08 | 2024-12-16 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| The Ring - Testing & Commissioning - Close-Out / Handing Over | Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-04 | 2025-03-02 |  | New Orders |  | Low |  | 424 | [7 empty] | TRUE
| Level 00 - The Ring - Testing & Commissioning - Close-Out / Handing Over | The Ring - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-04 | 2025-01-27 |  | New Orders |  | Low |  | 390 | [7 empty] | TRUE
| Zone R2 (Mackup / Benchmark) - Level 00 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Level 00 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-04 | 2024-01-08 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| Zone R1 - Level 00 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Level 00 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-03 | 2024-04-25 |  | New Orders |  | Low |  | 54 | [7 empty] | TRUE
| Zone R2 - Level 00 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Level 00 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-25 | 2024-03-28 |  | New Orders |  | Low |  | 33 | [7 empty] | TRUE
| Zone R2 (Leave out Area) - Level 00 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Level 00 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-02 | 2025-01-27 |  | New Orders |  | Low |  | 26 | [7 empty] | TRUE
| Zone R3 - Level 00 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Level 00 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-03 | 2024-04-23 |  | New Orders |  | Low |  | 52 | [7 empty] | TRUE
| Zone R3 (Leave out Area) - Level 00 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Level 00 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-08 | 2025-01-16 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| Zone R4 - Level 00 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Level 00 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-15 | 2024-04-23 |  | New Orders |  | Low |  | 69 | [7 empty] | TRUE
| Level 01 - The Ring - Testing & Commissioning - Close-Out / Handing Over | The Ring - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-04 | 2025-03-02 |  | New Orders |  | Low |  | 424 | [7 empty] | TRUE
| Zone R2 (Mackup / Benchmark) - Level 01 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Level 01 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-04 | 2024-01-08 |  | New Orders |  | Low |  | 5 | [7 empty] | TRUE
| Zone R1 - Level 01 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Level 01 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-21 | 2024-05-12 |  | New Orders |  | Low |  | 53 | [7 empty] | TRUE
| Zone R2 - Level 01 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Level 01 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-25 | 2024-03-25 |  | New Orders |  | Low |  | 30 | [7 empty] | TRUE
| Zone R2 (Leave out Area) - Level 01 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Level 01 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-28 | 2025-03-02 |  | New Orders |  | Low |  | 34 | [7 empty] | TRUE
| Zone R3 - Level 01 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Level 01 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-11 | 2024-05-13 |  | New Orders |  | Low |  | 64 | [7 empty] | TRUE
| Zone R3 (Leave out Area) - Level 01 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Level 01 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-30 | 2025-02-09 |  | New Orders |  | Low |  | 11 | [7 empty] | TRUE
| Zone R4 - Level 01 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Level 01 - The Ring - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-28 | 2024-05-13 |  | New Orders |  | Low |  | 76 | [7 empty] | TRUE
| The Beach - Testing & Commissioning - Close-Out / Handing Over | Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-07 | 2024-07-17 |  | New Orders |  | Low |  | 72 | [7 empty] | TRUE
| Level 00 - The Beach - Testing & Commissioning - Close-Out / Handing Over | The Beach - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-07 | 2024-07-17 |  | New Orders |  | Low |  | 72 | [7 empty] | TRUE
| Zone B1 - Level 00 - The Beach - Testing & Commissioning - Close-Out / Handing Over | Level 00 - The Beach - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-13 | 2024-05-21 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| Zone B2 - Level 00 - The Beach - Testing & Commissioning - Close-Out / Handing Over | Level 00 - The Beach - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-07 | 2024-06-12 |  | New Orders |  | Low |  | 37 | [7 empty] | TRUE
| Zone B3 - Level 00 - The Beach - Testing & Commissioning - Close-Out / Handing Over | Level 00 - The Beach - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-06-23 | 2024-07-16 |  | New Orders |  | Low |  | 24 | [7 empty] | TRUE
| Zone B4 - Level 00 - The Beach - Testing & Commissioning - Close-Out / Handing Over | Level 00 - The Beach - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-07-07 | 2024-07-17 |  | New Orders |  | Low |  | 11 | [7 empty] | TRUE
| Zone B5 - Level 00 - The Beach - Testing & Commissioning - Close-Out / Handing Over | Level 00 - The Beach - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-07-01 | 2024-07-09 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| The Tail - Testing & Commissioning - Close-Out / Handing Over | Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-02 | 2025-04-09 |  | New Orders |  | Low |  | 67 | [7 empty] | TRUE
| Zone T1 Guestrooms (M03) - The Tail - Testing & Commissioning - Close-Out / Handing Over | The Tail - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-02 | 2025-04-09 |  | New Orders |  | Low |  | 67 | [7 empty] | TRUE
| Level 01 - Zone T1 Guestrooms (M03) - The Tail - Testing & Commissioning - Close-Out / Handing Over | Zone T1 Guestrooms (M03) - The Tail - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-02 | 2025-03-26 |  | New Orders |  | Low |  | 53 | [7 empty] | TRUE
| Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Testing & Commissioning - Close-Out / Handing Over | Level 01 - Zone T1 Guestrooms (M03) - The Tail - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-02 | 2025-03-26 |  | New Orders |  | Low |  | 53 | [7 empty] | TRUE
| Level 02 - Zone T1 Guestrooms (M03) - The Tail - Testing & Commissioning - Close-Out / Handing Over | Zone T1 Guestrooms (M03) - The Tail - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-05 | 2025-04-09 |  | New Orders |  | Low |  | 64 | [7 empty] | TRUE
| Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Testing & Commissioning - Close-Out / Handing Over | Level 02 - Zone T1 Guestrooms (M03) - The Tail - Testing & Commissioning - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-05 | 2025-04-09 |  | New Orders |  | Low |  | 64 | [7 empty] | TRUE
| Snagging / De-Snagging - Close-Out / Handing Over | Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-09 | 2025-04-20 |  | New Orders |  | Low |  | 468 | [7 empty] | TRUE
| The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-21 | 2024-12-25 |  | New Orders |  | Low |  | 309 | [7 empty] | TRUE
| Level 01 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-08 | 2024-12-16 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| Zone M3 - Level 01 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Level 01 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-08 | 2024-12-16 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| SPA & Fitness - Zone M3 - Level 01 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Zone M3 - Level 01 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-08 | 2024-12-16 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| Level 02 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-21 | 2024-05-01 |  | New Orders |  | Low |  | 71 | [7 empty] | TRUE
| Zone M1 - Level 02 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Level 02 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-25 | 2024-03-17 |  | New Orders |  | Low |  | 22 | [7 empty] | TRUE
| Zone M2 - Level 02 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Level 02 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-31 | 2024-05-01 |  | New Orders |  | Low |  | 32 | [7 empty] | TRUE
| Zone M3 - Level 02 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Level 02 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-21 | 2024-03-31 |  | New Orders |  | Low |  | 40 | [7 empty] | TRUE
| Zone M4 - Level 02 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Level 02 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-14 | 2024-05-01 |  | New Orders |  | Low |  | 49 | [7 empty] | TRUE
| Level 03 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-28 | 2024-06-24 |  | New Orders |  | Low |  | 89 | [7 empty] | TRUE
| Zone M1 - Level 03 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Level 03 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-28 | 2024-05-08 |  | New Orders |  | Low |  | 42 | [7 empty] | TRUE
| Zone M2 - Level 03 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Level 03 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-23 | 2024-05-29 |  | New Orders |  | Low |  | 37 | [7 empty] | TRUE
| Zone M3 - Level 03 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Level 03 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-03 | 2024-05-23 |  | New Orders |  | Low |  | 51 | [7 empty] | TRUE
| Zone M4 - Level 03 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Level 03 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-30 | 2024-06-24 |  | New Orders |  | Low |  | 56 | [7 empty] | TRUE
| Level 04 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-07 | 2024-06-26 |  | New Orders |  | Low |  | 51 | [7 empty] | TRUE
| Zone M1 - Level 04 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Level 04 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-13 | 2024-05-21 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| Zone M2 - Level 04 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Level 04 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-13 | 2024-06-09 |  | New Orders |  | Low |  | 28 | [7 empty] | TRUE
| Zone M3 - Level 04 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Level 04 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-21 | 2024-05-29 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| Zone M4 - Level 04 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Level 04 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-07 | 2024-06-26 |  | New Orders |  | Low |  | 51 | [7 empty] | TRUE
| Level 05 & 06 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-11-12 | 2024-12-25 |  | New Orders |  | Low |  | 44 | [7 empty] | TRUE
| Zone M2 - Level 05 & 06 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Level 05 & 06 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-11-12 | 2024-11-20 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| Zone M4 - Level 05 & 06 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Level 05 & 06 - The Mound - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-17 | 2024-12-25 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-09 | 2025-03-11 |  | New Orders |  | Low |  | 428 | [7 empty] | TRUE
| Level 00 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-09 | 2025-02-05 |  | New Orders |  | Low |  | 394 | [7 empty] | TRUE
| Zone R2 (Mackup / Benchmark) - Level 00 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Level 00 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-09 | 2024-01-11 |  | New Orders |  | Low |  | 3 | [7 empty] | TRUE
| Zone R1 - Level 00 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Level 00 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-12 | 2024-05-06 |  | New Orders |  | Low |  | 56 | [7 empty] | TRUE
| Zone R2 - Level 00 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Level 00 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-05 | 2024-04-08 |  | New Orders |  | Low |  | 35 | [7 empty] | TRUE
| Zone R2 (Leave out Area) - Level 00 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Level 00 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-13 | 2025-02-05 |  | New Orders |  | Low |  | 24 | [7 empty] | TRUE
| Zone R3 - Level 00 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Level 00 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-12 | 2024-05-02 |  | New Orders |  | Low |  | 52 | [7 empty] | TRUE
| Zone R3 (Leave out Area) - Level 00 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Level 00 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-19 | 2025-01-27 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| Zone R4 - Level 00 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Level 00 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-02-27 | 2024-05-02 |  | New Orders |  | Low |  | 66 | [7 empty] | TRUE
| Level 01 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-09 | 2025-03-11 |  | New Orders |  | Low |  | 428 | [7 empty] | TRUE
| Zone R2 (Mackup / Benchmark) - Level 01 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Level 01 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-09 | 2024-01-11 |  | New Orders |  | Low |  | 3 | [7 empty] | TRUE
| Zone R1 - Level 01 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Level 01 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-01 | 2024-05-21 |  | New Orders |  | Low |  | 51 | [7 empty] | TRUE
| Zone R2 - Level 01 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Level 01 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-05 | 2024-04-03 |  | New Orders |  | Low |  | 30 | [7 empty] | TRUE
| Zone R2 (Leave out Area) - Level 01 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Level 01 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-06 | 2025-03-11 |  | New Orders |  | Low |  | 34 | [7 empty] | TRUE
| Zone R3 - Level 01 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Level 01 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-20 | 2024-05-22 |  | New Orders |  | Low |  | 64 | [7 empty] | TRUE
| Zone R3 (Leave out Area) - Level 01 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Level 01 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-10 | 2025-02-18 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| Zone R4 - Level 01 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Level 01 - The Ring - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-10 | 2024-05-22 |  | New Orders |  | Low |  | 74 | [7 empty] | TRUE
| The Beach - Snagging / De-Snagging - Close-Out / Handing Over | Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-16 | 2024-07-28 |  | New Orders |  | Low |  | 74 | [7 empty] | TRUE
| Level 00 - The Beach - Snagging / De-Snagging - Close-Out / Handing Over | The Beach - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-16 | 2024-07-28 |  | New Orders |  | Low |  | 74 | [7 empty] | TRUE
| Zone B1 - Level 00 - The Beach - Snagging / De-Snagging - Close-Out / Handing Over | Level 00 - The Beach - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-22 | 2024-05-30 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| Zone B2 - Level 00 - The Beach - Snagging / De-Snagging - Close-Out / Handing Over | Level 00 - The Beach - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-16 | 2024-06-26 |  | New Orders |  | Low |  | 42 | [7 empty] | TRUE
| Zone B3 - Level 00 - The Beach - Snagging / De-Snagging - Close-Out / Handing Over | Level 00 - The Beach - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-07-02 | 2024-07-25 |  | New Orders |  | Low |  | 24 | [7 empty] | TRUE
| Zone B4 - Level 00 - The Beach - Snagging / De-Snagging - Close-Out / Handing Over | Level 00 - The Beach - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-07-16 | 2024-07-28 |  | New Orders |  | Low |  | 13 | [7 empty] | TRUE
| Zone B5 - Level 00 - The Beach - Snagging / De-Snagging - Close-Out / Handing Over | Level 00 - The Beach - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-07-10 | 2024-07-18 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| The Tail - Snagging / De-Snagging - Close-Out / Handing Over | Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-11 | 2025-04-20 |  | New Orders |  | Low |  | 69 | [7 empty] | TRUE
| Zone T1 Guestrooms (M03) - The Tail - Snagging / De-Snagging - Close-Out / Handing Over | The Tail - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-11 | 2025-04-20 |  | New Orders |  | Low |  | 69 | [7 empty] | TRUE
| Level 01 - Zone T1 Guestrooms (M03) - The Tail - Snagging / De-Snagging - Close-Out / Handing Over | Zone T1 Guestrooms (M03) - The Tail - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-11 | 2025-04-10 |  | New Orders |  | Low |  | 59 | [7 empty] | TRUE
| Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Snagging / De-Snagging - Close-Out / Handing Over | Level 01 - Zone T1 Guestrooms (M03) - The Tail - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-11 | 2025-04-10 |  | New Orders |  | Low |  | 59 | [7 empty] | TRUE
| Level 02 - Zone T1 Guestrooms (M03) - The Tail - Snagging / De-Snagging - Close-Out / Handing Over | Zone T1 Guestrooms (M03) - The Tail - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-16 | 2025-04-20 |  | New Orders |  | Low |  | 64 | [7 empty] | TRUE
| Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Snagging / De-Snagging - Close-Out / Handing Over | Level 02 - Zone T1 Guestrooms (M03) - The Tail - Snagging / De-Snagging - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-16 | 2025-04-20 |  | New Orders |  | Low |  | 64 | [7 empty] | TRUE
| Authorities Inspections / Approvals - Close-Out / Handing Over | Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-05-12 | 2025-06-01 |  | New Orders |  | Low |  | 21 | [7 empty] | TRUE
| Close-out Documentation - Close-Out / Handing Over | Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-13 | 2025-05-11 |  | New Orders |  | Low |  | 485 | [7 empty] | TRUE
| As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-13 | 2025-05-11 |  | New Orders |  | Low |  | 485 | [7 empty] | TRUE
| Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-13 | 2025-04-27 |  | New Orders |  | Low |  | 471 | [7 empty] | TRUE
| The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-04 | 2025-01-02 |  | New Orders |  | Low |  | 305 | [7 empty] | TRUE
| Level 01 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-17 | 2024-12-24 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| Zone M3 - Level 01 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 01 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-17 | 2024-12-24 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| Level 02 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-04 | 2024-05-09 |  | New Orders |  | Low |  | 67 | [7 empty] | TRUE
| Zone M1 - Level 02 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 02 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-05 | 2024-03-25 |  | New Orders |  | Low |  | 21 | [7 empty] | TRUE
| Zone M2 - Level 02 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 02 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-09 | 2024-05-09 |  | New Orders |  | Low |  | 31 | [7 empty] | TRUE
| Zone M3 - Level 02 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 02 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-04 | 2024-04-08 |  | New Orders |  | Low |  | 36 | [7 empty] | TRUE
| Zone M4 - Level 02 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 02 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-25 | 2024-05-09 |  | New Orders |  | Low |  | 46 | [7 empty] | TRUE
| Level 03 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-08 | 2024-06-30 |  | New Orders |  | Low |  | 84 | [7 empty] | TRUE
| Zone M1 - Level 03 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 03 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-08 | 2024-05-16 |  | New Orders |  | Low |  | 39 | [7 empty] | TRUE
| Zone M2 - Level 03 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 03 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-02 | 2024-06-06 |  | New Orders |  | Low |  | 36 | [7 empty] | TRUE
| Zone M3 - Level 03 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 03 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-16 | 2024-06-01 |  | New Orders |  | Low |  | 47 | [7 empty] | TRUE
| Zone M4 - Level 03 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 03 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-09 | 2024-06-30 |  | New Orders |  | Low |  | 53 | [7 empty] | TRUE
| Level 04 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-16 | 2024-07-04 |  | New Orders |  | Low |  | 50 | [7 empty] | TRUE
| Zone M1 - Level 04 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 04 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-22 | 2024-05-29 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| Zone M2 - Level 04 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 04 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-22 | 2024-06-22 |  | New Orders |  | Low |  | 32 | [7 empty] | TRUE
| Zone M3 - Level 04 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 04 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-30 | 2024-06-06 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| Zone M4 - Level 04 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 04 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-16 | 2024-07-04 |  | New Orders |  | Low |  | 50 | [7 empty] | TRUE
| Level 05 & 06 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-11-21 | 2025-01-02 |  | New Orders |  | Low |  | 43 | [7 empty] | TRUE
| Zone M2 - Level 05 & 06 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 05 & 06 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-11-21 | 2024-11-28 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| Zone M4 - Level 05 & 06 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 05 & 06 - The Mound - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-26 | 2025-01-02 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-13 | 2025-03-19 |  | New Orders |  | Low |  | 432 | [7 empty] | TRUE
| Level 00 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-13 | 2025-02-13 |  | New Orders |  | Low |  | 398 | [7 empty] | TRUE
| Zone R2 (Mackup / Benchmark) - Level 00 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-13 | 2024-01-15 |  | New Orders |  | Low |  | 3 | [7 empty] | TRUE
| Zone R1 - Level 00 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-21 | 2024-05-14 |  | New Orders |  | Low |  | 55 | [7 empty] | TRUE
| Zone R2 - Level 00 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-14 | 2024-04-20 |  | New Orders |  | Low |  | 38 | [7 empty] | TRUE
| Zone R2 (Leave out Area) - Level 00 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-22 | 2025-02-13 |  | New Orders |  | Low |  | 23 | [7 empty] | TRUE
| Zone R3 - Level 00 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-21 | 2024-05-11 |  | New Orders |  | Low |  | 52 | [7 empty] | TRUE
| Zone R3 (Leave out Area) - Level 00 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-28 | 2025-02-04 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| Zone R4 - Level 00 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-07 | 2024-05-11 |  | New Orders |  | Low |  | 66 | [7 empty] | TRUE
| Level 01 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-13 | 2025-03-19 |  | New Orders |  | Low |  | 432 | [7 empty] | TRUE
| Zone R2 (Mackup / Benchmark) - Level 01 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 01 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-13 | 2024-01-15 |  | New Orders |  | Low |  | 3 | [7 empty] | TRUE
| Zone R1 - Level 01 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 01 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-14 | 2024-05-29 |  | New Orders |  | Low |  | 46 | [7 empty] | TRUE
| Zone R2 - Level 01 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 01 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-14 | 2024-04-15 |  | New Orders |  | Low |  | 33 | [7 empty] | TRUE
| Zone R2 (Leave out Area) - Level 01 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 01 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-17 | 2025-03-19 |  | New Orders |  | Low |  | 31 | [7 empty] | TRUE
| Zone R3 - Level 01 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 01 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-30 | 2024-05-30 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Zone R3 (Leave out Area) - Level 01 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 01 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-19 | 2025-02-27 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| Zone R4 - Level 01 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 01 - The Ring - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-19 | 2024-05-30 |  | New Orders |  | Low |  | 73 | [7 empty] | TRUE
| The Beach - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-27 | 2024-08-05 |  | New Orders |  | Low |  | 71 | [7 empty] | TRUE
| Level 00 - The Beach - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | The Beach - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-27 | 2024-08-05 |  | New Orders |  | Low |  | 71 | [7 empty] | TRUE
| Zone B1 - Level 00 - The Beach - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Beach - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-06-01 | 2024-06-08 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| Zone B2 - Level 00 - The Beach - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Beach - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-27 | 2024-07-04 |  | New Orders |  | Low |  | 39 | [7 empty] | TRUE
| Zone B3 - Level 00 - The Beach - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Beach - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-07-11 | 2024-08-03 |  | New Orders |  | Low |  | 24 | [7 empty] | TRUE
| Zone B4 - Level 00 - The Beach - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Beach - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-07-25 | 2024-08-05 |  | New Orders |  | Low |  | 12 | [7 empty] | TRUE
| Zone B5 - Level 00 - The Beach - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Beach - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-07-20 | 2024-07-27 |  | New Orders |  | Low |  | 8 | [7 empty] | TRUE
| The Tail - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-20 | 2025-04-27 |  | New Orders |  | Low |  | 67 | [7 empty] | TRUE
| Zone T1 Guestrooms (M03) - The Tail - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | The Tail - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-20 | 2025-04-27 |  | New Orders |  | Low |  | 67 | [7 empty] | TRUE
| Level 01 - Zone T1 Guestrooms (M03) - The Tail - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Zone T1 Guestrooms (M03) - The Tail - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-20 | 2025-04-19 |  | New Orders |  | Low |  | 59 | [7 empty] | TRUE
| Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 01 - Zone T1 Guestrooms (M03) - The Tail - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-20 | 2025-04-19 |  | New Orders |  | Low |  | 59 | [7 empty] | TRUE
| Level 02 - Zone T1 Guestrooms (M03) - The Tail - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Zone T1 Guestrooms (M03) - The Tail - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-25 | 2025-04-27 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 02 - Zone T1 Guestrooms (M03) - The Tail - Preparation & Submission - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-25 | 2025-04-27 |  | New Orders |  | Low |  | 62 | [7 empty] | TRUE
| Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-16 | 2025-05-11 |  | New Orders |  | Low |  | 482 | [7 empty] | TRUE
| The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-12 | 2025-01-16 |  | New Orders |  | Low |  | 311 | [7 empty] | TRUE
| Level 00 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-25 | 2025-01-02 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| Zone M3 - Level 00 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-25 | 2025-01-02 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| Level 02 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-12 | 2024-05-23 |  | New Orders |  | Low |  | 73 | [7 empty] | TRUE
| Zone M1 - Level 02 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 02 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-13 | 2024-04-08 |  | New Orders |  | Low |  | 27 | [7 empty] | TRUE
| Zone M2 - Level 02 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 02 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-21 | 2024-05-20 |  | New Orders |  | Low |  | 30 | [7 empty] | TRUE
| Zone M3 - Level 02 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 02 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-12 | 2024-04-24 |  | New Orders |  | Low |  | 44 | [7 empty] | TRUE
| Zone M4 - Level 02 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 02 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-02 | 2024-05-23 |  | New Orders |  | Low |  | 52 | [7 empty] | TRUE
| Level 03 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-21 | 2024-07-14 |  | New Orders |  | Low |  | 85 | [7 empty] | TRUE
| Zone M1 - Level 03 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 03 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-21 | 2024-05-30 |  | New Orders |  | Low |  | 40 | [7 empty] | TRUE
| Zone M2 - Level 03 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 03 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-12 | 2024-06-25 |  | New Orders |  | Low |  | 45 | [7 empty] | TRUE
| Zone M3 - Level 03 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 03 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-24 | 2024-06-13 |  | New Orders |  | Low |  | 51 | [7 empty] | TRUE
| Zone M4 - Level 03 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 03 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-19 | 2024-07-14 |  | New Orders |  | Low |  | 57 | [7 empty] | TRUE
| Level 04 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-26 | 2024-07-18 |  | New Orders |  | Low |  | 54 | [7 empty] | TRUE
| Zone M1 - Level 04 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 04 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-30 | 2024-06-12 |  | New Orders |  | Low |  | 14 | [7 empty] | TRUE
| Zone M2 - Level 04 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 04 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-30 | 2024-07-04 |  | New Orders |  | Low |  | 36 | [7 empty] | TRUE
| Zone M3 - Level 04 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 04 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-06-09 | 2024-06-25 |  | New Orders |  | Low |  | 17 | [7 empty] | TRUE
| Zone M4 - Level 04 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 04 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-05-26 | 2024-07-18 |  | New Orders |  | Low |  | 54 | [7 empty] | TRUE
| Level 05 & 06 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-01 | 2025-01-16 |  | New Orders |  | Low |  | 47 | [7 empty] | TRUE
| Zone M2 - Level 05 & 06 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 05 & 06 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-12-01 | 2024-12-12 |  | New Orders |  | Low |  | 12 | [7 empty] | TRUE
| Zone M4 - Level 05 & 06 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 05 & 06 - The Mound - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-05 | 2025-01-16 |  | New Orders |  | Low |  | 12 | [7 empty] | TRUE
| The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-16 | 2025-04-08 |  | New Orders |  | Low |  | 449 | [7 empty] | TRUE
| Level 00 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-16 | 2025-02-27 |  | New Orders |  | Low |  | 409 | [7 empty] | TRUE
| Zone R2 (Mackup / Benchmark) - Level 00 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-16 | 2024-01-24 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| Zone R1 - Level 00 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-31 | 2024-05-28 |  | New Orders |  | Low |  | 59 | [7 empty] | TRUE
| Zone R2 - Level 00 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-24 | 2024-05-02 |  | New Orders |  | Low |  | 40 | [7 empty] | TRUE
| Zone R2 (Leave out Area) - Level 00 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-01-30 | 2025-02-27 |  | New Orders |  | Low |  | 29 | [7 empty] | TRUE
| Zone R3 - Level 00 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-31 | 2024-05-23 |  | New Orders |  | Low |  | 54 | [7 empty] | TRUE
| Zone R3 (Leave out Area) - Level 00 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-05 | 2025-02-18 |  | New Orders |  | Low |  | 14 | [7 empty] | TRUE
| Zone R4 - Level 00 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-17 | 2024-05-23 |  | New Orders |  | Low |  | 68 | [7 empty] | TRUE
| Level 01 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-16 | 2025-04-08 |  | New Orders |  | Low |  | 449 | [7 empty] | TRUE
| Zone R2 (Mackup / Benchmark) - Level 01 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 01 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-01-16 | 2024-01-24 |  | New Orders |  | Low |  | 9 | [7 empty] | TRUE
| Zone R1 - Level 01 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 01 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-22 | 2024-06-12 |  | New Orders |  | Low |  | 52 | [7 empty] | TRUE
| Zone R2 - Level 01 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 01 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-24 | 2024-04-29 |  | New Orders |  | Low |  | 37 | [7 empty] | TRUE
| Zone R2 (Leave out Area) - Level 01 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 01 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-02-26 | 2025-04-08 |  | New Orders |  | Low |  | 42 | [7 empty] | TRUE
| Zone R3 - Level 01 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 01 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-04-07 | 2024-06-13 |  | New Orders |  | Low |  | 68 | [7 empty] | TRUE
| Zone R3 (Leave out Area) - Level 01 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 01 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-02 | 2025-03-13 |  | New Orders |  | Low |  | 12 | [7 empty] | TRUE
| Zone R4 - Level 01 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 01 - The Ring - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-03-27 | 2024-06-13 |  | New Orders |  | Low |  | 79 | [7 empty] | TRUE
| The Beach - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-06-04 | 2024-08-19 |  | New Orders |  | Low |  | 77 | [7 empty] | TRUE
| Level 00 - The Beach - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | The Beach - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-06-04 | 2024-08-19 |  | New Orders |  | Low |  | 77 | [7 empty] | TRUE
| Zone B1 - Level 00 - The Beach - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Beach - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-06-09 | 2024-06-25 |  | New Orders |  | Low |  | 17 | [7 empty] | TRUE
| Zone B2 - Level 00 - The Beach - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Beach - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-06-04 | 2024-07-18 |  | New Orders |  | Low |  | 45 | [7 empty] | TRUE
| Zone B3 - Level 00 - The Beach - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Beach - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-07-21 | 2024-08-15 |  | New Orders |  | Low |  | 26 | [7 empty] | TRUE
| Zone B4 - Level 00 - The Beach - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Beach - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-08-04 | 2024-08-19 |  | New Orders |  | Low |  | 16 | [7 empty] | TRUE
| Zone B5 - Level 00 - The Beach - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 00 - The Beach - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2024-07-28 | 2024-08-08 |  | New Orders |  | Low |  | 12 | [7 empty] | TRUE
| The Tail - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-02 | 2025-05-11 |  | New Orders |  | Low |  | 71 | [7 empty] | TRUE
| Zone T1 Guestrooms (M03) - The Tail - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | The Tail - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-02 | 2025-05-11 |  | New Orders |  | Low |  | 71 | [7 empty] | TRUE
| Level 01 - Zone T1 Guestrooms (M03) - The Tail - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Zone T1 Guestrooms (M03) - The Tail - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-02 | 2025-05-01 |  | New Orders |  | Low |  | 61 | [7 empty] | TRUE
| Zone T1 - Level 01 - Zone T1 Guestrooms (M03) - The Tail - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 01 - Zone T1 Guestrooms (M03) - The Tail - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-02 | 2025-05-01 |  | New Orders |  | Low |  | 61 | [7 empty] | TRUE
| Level 02 - Zone T1 Guestrooms (M03) - The Tail - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Zone T1 Guestrooms (M03) - The Tail - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-05 | 2025-05-11 |  | New Orders |  | Low |  | 68 | [7 empty] | TRUE
| Zone T2 - Level 02 - Zone T1 Guestrooms (M03) - The Tail - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Level 02 - Zone T1 Guestrooms (M03) - The Tail - Review & Approval by DAR / TRSDC - As-Built Drawings - Close-out Documentation - Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-03-05 | 2025-05-11 |  | New Orders |  | Low |  | 68 | [7 empty] | TRUE
| Demobilization - Close-Out / Handing Over | Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-06-02 | 2025-06-21 |  | New Orders |  | Low |  | 20 | [7 empty] | TRUE
| Taking Over Certificate (TOC) - Close-Out / Handing Over | Close-Out / Handing Over | Alu Systems Co | 10259 - HC1 ¦ Aluminum & Glazing-Alusystems-BL-R01 | THE RED SEA REAL ESTATE COMPANY | 2025-06-22 | 2025-07-26 |  | New Orders |  | Low |  | 35 | [7 empty] | TRUE